GOVERNMENT OF ANGOLA

GOVERNMENT OF BOTSWANA

GOVERNMENT OF NAMIBIA

GLOBAL ENVIRONMENT FACILITY (GEF)

UNITED NATIONS DEVELOPMENT PROGRAMME (UNDP)

FOOD AND AGRICULTURE ORGANIZATION OF THE UNITED NATIONS (FAO)

INTERIM EVALUATION

OF THE

ENVIRONMENTAL PROTECTION AND SUSTAINABLE MANAGEMENT

OF THE OKAVANGO RIVER BASIN PROJECT (RAF/00/G33/A/1G/12)

Philip Tortell and Nii Boi Ayibotele

Luanda, Windhoek, Gaborone, December 2006

ACKNOWLEDGEMENTS

The evaluation team would like to acknowledge the assistance it received from various individuals and organizations in carrying out the evaluation.

Firstly, we would like to mention the many people in Angola, Botswana and Namibia that we met with.  We are grateful to the OKACOM Commissioners and the OBSC members who shared their experiences of OKACOM’s operations and clarified the procedures of the Commission.  Public officials in ministries dealing with energy, water, environment, agriculture, forestry, wildlife and local government provided valuable information by describing how their work is related to the Okavango River Basin in their respective countries and provided documents and reports which enhanced the team’s understanding of the project – the team is indebted to them.  The NGOs responsible for organizing the Basin-wide Forum provided insightful information and documentation about how communities are organized at grassroots level to participate in the management of natural resources of the Basin – we thank them.

Secondly, the team would like to express its appreciation to all who responded to the draft report with comments either verbally or in writing.  This enabled us to modify our views where appropriate to reflect the realities on the ground and to amend statements so as to bring out their true meaning and intent.  The written comments of the past Project Manager, the interim Project Manager and the FAO are particularly acknowledged with gratitude.

The team would also like to thank FAO (at Headquarters in Rome, the Regional Office in Accra and the Country Office in Luanda) for providing background documentation and other information through written comments and telephone conferences.  The PMU in Luanda was helpful by providing documentation on the project, arranging the schedule of appointments, assisting with logistics and sharing with the team its office and facilities while we were in Luanda.  The team is grateful for this assistance.

The team is also very grateful to the UNDP family.  We thank the UNDP-GEF Regional Office in Pretoria for the detailed initial and subsequent briefings and extensive documentation provided and also for responding to the incessant questions raised by the team during the mission.  The careful facilitation of appointments by the UNDP Country Office in Windhoek is also gratefully acknowledged.  Furthermore, the insights provided by the UNDP Country Offices in each of Luanda, Windhoek and Gaborone are similarly acknowledged.

Finally, the team is very grateful to the IRBM Project Manager and his staff, as well as to USAID, for sharing with the team the work they have done in the Basin and which has a bearing on EPSMO, and their experience in working in the three riparian countries.  The OKACOM Interim Secretariat under the same project, provided us with extensive information on the Secretariat, arranged various appointments and assisted us with other logistics both in Botswana as well as for the final presentation meeting in Pretoria – the team is indeed grateful.

THE EVALUATION TEAM

Philip Tortell

### Consultant

### Environmental Management Limited

P O  Box 27 433,  Wellington,  NEW ZEALAND

Tel  +64-4-384 4133,   Fax  +64-4-384 4022,   Email  <tortell@attglobal.net>

Nii Boi Ayibotele

Consultant

Nii Consult

P.O. Box Os 981, Osu, Accra, GHANA

Tel +233-21-761007,    Fax +233-21-761008,   Email  <ayibotele@ghana.com>

CONTENTS

ACRONYMS AND ABBREVIATIONS						  5

EXECUTIVE SUMMARY								  6

1		INTRODUCTION								10

1.1	Background									10

1.2	Purpose of the evaluation							10

1.3	Key issues addressed								11

1.4	Methodology of the evaluation							11

1.4.1	Mission schedule							11

1.4.2	The approach adopted						11

1.4.3	Documents reviewed and consulted					12

1.4.4	Consultations								12

2		THE PROJECT AND ITS DEVELOPMENT CONTEXT			13

2.1	Project start and duration							13

2.2	Problems that the project seeks to address					13

2.3	Overall and Immediate Objectives of the project				14

2.4	Main stakeholders								14

2.5	Results expected 								15

3	FINDINGS : PROJECT FORMULATION					16

3.1	Ownership									16

3.2	Project logic and design							16

3.3	Linkages between the project and other interventions				17

3.4	Implementation and institutional framework 					18

3.5	Stakeholder participation in project formulation				19

3.6	Conclusions on project formulation and design				19

4	FINDINGS : PROJECT IMPLEMENTATION					20

4.1	Project governance								20

4.1.1	General governance issues						20

4.1.2	Policy and guidance – the Project Steering Committee		21

4.1.3	Role of UNDP as the Implementing Agency				22

4.1.4	Role of OKACOM							23

4.1.5	Conclusions on project governance					24

4.2	Project administration								26

4.2.1	The role of FAO as the Executing Agency				26

4.2.2	The disbursement process						27

4.2.3	The recruitment process						28

4.2.4	Travel authorization							29

4.2.5	Conclusions on project administration				30

4.3	Project management								30

4.3.1	The PMU and the NCUs						30

4.3.2	Project personnel							32

4.3.3	Special relationship with OKACOM					32

4.3.4	Project performance monitoring					32

4.3.5	Conclusions on project management					33

4.4	State of the budget and financial viability					34

4.5	Coordination with other initiatives						37

4.6	Lessons learnt									38

5	FINDINGS : RESULTS AND IMPACTS					38

5.1	Progress to date								38

5.2	Project impacts and sustainability						39

5.3	Stakeholder involvement in implementation					40

5.4	Conclusions on results								41

6	COLLECTED CONCLUSIONS						42

7	RECOMMENDATIONS : WHERE TO FROM HERE?			47

ANNEXES

1	Independent Evaluation Terms of Reference

2	Mission Schedule

3	Documents reviewed and consulted

4	Persons met and consulted

5	Proposed Terms of Reference for the Project Steering Committee (PSC)

6	Financial management tables as supplied by FAO

7	PMU Summary Report on Progress

ACRONYMS AND ABBREVIATIONS

APR		Annual Programme Review

CTA		Chief Technical Adviser

DWA		Department of Water Affairs, Botswana

DNA		Direcçäo Naçional de Águas, Angola

EA		Environmental Assessment

EA		Executing Agency

EPSMO	Environmental Protection & Sustainable Management of the Okavango Basin Project

EU		European Union, also EC – European Commission

FAO		Food and Agriculture Organization of the United Nations

GEF		Global Environment Facility

GTZ		Deutsche Gesellschaft fur Technische Zusammenarbeit (German Aid Agency)

GWP		Global Water Partnership

IA		Implementing Agency

IMP		Integrated Management Plan

IRBM		Integrated River Basin Management Project

IWRM		Integrated Water Resources Management

LogFrame	Logical Framework Matrix

MEA		Ministério da Energia e Águas, Angola

NCU		National Coordination Unit

NGO		Non-Government Organisation

NWRMR	Namibian Water Resources Management Review

OBSC		Okavango Basin Steering Committee

OKACOM	Permanent Okavango River Basin Commission

ORB		Okavango River Basin

PDF-B		Preparatory Development Facility – Phase B (GEF)

PIR 		Project Implementation Review

PM		Project Manager

PMU		Project Management Unit

ProDoc		Project Document

PSC		Project Steering Committee

SADC		Southern Africa Development Community

SAP		Strategic Action Programme

SBAA		Standard Basic Assistance Agreement (UNDP with Governments)

SBEAA		Standard Basic Executing Agency Agreement (UNDP with FAO)

SIDA		Swedish International Development Agency

TDA		Transboundary Diagnostic Analysis

TPR 		Tri-partite Review

UNESCO	United Nations Educational, Scientific and Cultural Organization

UNDP		United Nations Development Programme

UNOPS	United Nations Office for Project Services

USAID		United States Agency for International Development

EXECUTIVE SUMMARY

INTRODUCTION

This is the Interim Evaluation Report for the GEF/UNDP/FAO Environmental Protection and Sustainable Management of the Okavango River Basin Project (EPSMO) which started in November 2004 after many delays.  The EPSMO followed a Preparatory Phase which ran from 1997 to 2000 in response to an approach to GEF by the Governments of Angola, Namibia and Botswana, through their Permanent Okavango River Basin Commission (OKACOM).  EPSMO will undertake a Transboundary Diagnostic Analysis (TDA), and formulate a Strategic Action Programme (SAP), setting the stage for long term investment activities to protect the ecological integrity of the Basin.  This will address the critical transboundary elements of the Environmental Assessment and Integrated Management Plan originally proposed by OKACOM,

The project is being carried out in the three riparian countries namely, Angola, Namibia and Botswana.   UNDP is the Implementing Agency on behalf of GEF and it, in turn, has contracted FAO to serve as the Executing Agency.  OKACOM is identified as the project’s Coordinating Agency while Angola has accepted to serve as the host for the PMU.

This project is facing serious difficulties.  The expectations of various stakeholders are in harmony, but the means of achieving the project objectives are the subject of contention.  Roles and responsibilities are not clear, the procedures of the Implementing Agency and the Executing Agency are not well understood, project governance is weak, the inception phase got bogged down in secondary activities, delivery rate is well below normal, the Project Manager has resigned, and project activities are currently halted.

The fundamental issue addressed by the evaluation team is whether the project is still viable.  An abandoned project is not good for stakeholders, however, a project which proceeds and fails, is even worse.  In determining whether the project should go ahead, and if so, how, the evaluation team attempted to address the barriers that have thus far prevented this project from progressing towards its goals.

FINDINGS

Project ownership

The evaluation team is impressed by the high degree of ownership shown in this project by OKACOM and others in the three riparian countries.  But this may have been at the expense of ownership by the three Governments.  Country level involvement in project implementation has been effected almost exclusively by the OKACOM Commissioners and the OBSC members and this is especially true of the Angolan Commissioners and OBSC members.  While the evaluation team accepts the fact that the PMU will remain in Luanda, there needs to be a clear understanding by all stakeholders that the professional independence of the PM and the PMU is not to be questioned except through the PSC.  The PM and PMU must be independent of any one government in the execution of their duties.

Project governance, administration and management

EPSMO was meant to be steered by a Project Steering Committee (PSC) comprising representatives of OKACOM, UNDP and FAO.  However, the PSC failed to live up to expectations mainly as a result of the confusion that exists regarding roles and responsibilities of individual stakeholders as well as a lack of clear understanding of the objectives, constraints, procedures and processes of the GEF and UNDP.  The PSC must be recognized and supported by all stakeholders as the highest governance body for the project.  As such, it must have both the authority and the power to set policy for the project and to monitor its performance.  By confirming and accepting that the PSC is the highest body for governance of the project, and that issues and disagreements must be brought to the PSC for resolution, the stakeholders will avoid issues becoming personalized, which has been a major contributing factor to the problems faced by the project.  This report makes recommendations on the structure and function of the PSC including membership and Terms of Reference.

FAO has been responsible for the administration of the project and it established the office of Budget Holder in its regional office for Africa in Accra.  The comparative advantage that FAO was meant to bring to this project is not significant, in that the most unique component is the technical element and this could have been obtained on contract, separately from the administrative element which could have been more efficiently carried out by an organization with support systems attuned to those of UNDP.

The evaluation team has recommended that FAO procedures for disbursements, recruitment and travel need to change to reflect the specific needs of the project because the alternative is project failure.  In particular, the PM must be given the utmost level of delegation and flexibility and then supported to get on with the job he/she has been engaged to perform.  The evaluation team is heartened by the indication received from FAO that it is ready to implement measures to streamline project administration and particularly to assign a high level of delegation and empowerment to the PM.

As implementing agency, UNDP must be more proactive, and in particular the country offices need to be more engaged.  Of these, the Principal Country Office in Angola must assume the lead role in supporting and monitoring the project through the PMU.   In addition, UNDP needs to take a more assertive stance in its requirements of FAO in the delivery of its contractual obligations and these need to be the subject of a formal Memorandum of Understanding between UNDP and FAO.

Day-to-day management of the project was entrusted to a Project Management Unit (PMU), headed by the Project Manager.  The establishment of the PMU in Luanda was in accordance with an OKACOM/Governments decision.  The evaluation team accepts the sentiments behind the OKACOM decision to place the PMU in Angola, but agrees with many stakeholders that Luanda is a difficult place to work in.   These difficulties need to be kept in mind when UNDP, FAO and the Government of Angola are considering the support necessary for the successful functioning of the PMU.

Monitoring progress towards the project’s objective

Progress by the project towards the achievement of its Objective and the three Components is unsatisfactory and no long term impacts or outcomes can be claimed as yet.  The project has under performed and failed to deliver the outputs expected in the one year it operated.  However, if the project is restarted, and if the various measures recommended in this report are implemented, there is no reason why the targeted outcomes cannot be achieved.

Since the project had not really taken off, there was not much opportunity to use the LogFrame to good effect and measure up progress against the set indicators.  The ProDoc was of somewhat limited usefulness for project implementation and performance monitoring mainly because by the time the project got going, it was rather dated (it had been developed some 3-5 years earlier).  If the project is restarted, a more thorough review of the LogFrame Matrix will be required at the outset to reflect changed circumstances.  It is also essential that an effective monitoring plan is developed and stakeholders’ commitment to the confirmed/revised targets and indicators needs to be obtained  through a fresh project inception workshop with the active participation of national/regional key stakeholders.

Partnership arrangements

Two projects which had the closest working relationship with the EPSMO project were the “Okavango Improved River Basin Management Project” (IRBM) funded by USAID, and “Every River Has its People” (ERP) funded by SIDA.  While no formal agreement for collaboration was finalized, the three projects agreed in principle to coordinate their efforts and a list of indicative follow-up actions was drawn up.  If the project is restarted, it will need to reopen the productive dialogue with both these initiatives, update its commitment and collaborate effectively for mutual benefit.  There may even be merit in attempting to blend the three LogFrames of IRBM, ERP and EPSMO.

The distinguishing feature of the EPSMO project has been described as its creation of the holistic Basin-wide context within which other initiatives in the Basin can nest.  However, it cannot, and must not, do this in isolation and collaboration with these and other relevant initiatives in the Basin is an essential element in its implementation approach.

Stakeholder participation

Stakeholder involvement in project implementation has been patchy.  The evaluation team found that the involvement of key stakeholders has been too little by some (UNDP Country Offices) and too much by others (OKACOM).  The former is the result of inadequate resources, while the latter arose from a misunderstanding of roles and responsibilities.  The PMU was expected to develop a public participation plan but this did not materialise before project activities were halted and the involvement of communities and the public in project implementation has been non-existent.

Project implementation

If the project is restarted, the opportunity should be taken to rephase and rebudget the project, but not necessarily redesign it.   The focus of the project should be shifted from the capital cities to the Basin which is where the natural resources are and where those that rely on them, live, and the emphasis should be moved away from the TDA and more to the SAP component.  The TDA must be completed in the shortest possible time and while it must be able to provide a solid foundation for the SAP, if gaps are identified, it is not essential to wait until they are filled.  Gaps can be recorded and the SAP can provide the activities that will fill the gaps at the operational phase.

The work on the SAP should focus on the national level in the first instance and if it appears that the project will run out of time and/or financial resources to complete the Basin-wide SAP, the task can be handed over to the OKACOM Secretariat which will provide logistical coordination and administrative support while OBSC will provide the necessary technical input to consolidate the final SAP.  It will also be opportune to involve fully the three staff, one from each country, who will be seconded to the Secretariat according to the procedures as adopted by OKACOM for the Secretariat.

On the basis of the financial resources estimated to be remaining, and the time that has been estimated to be required for completion of the three Components, the evaluation team believes that financial resources are adequate for the completion of all targeted Outputs.  However, experience in the Basin indicates that the time that is allowed for mobilization, achieving consensus and gaining trust, is grossly underestimated.  Forging relationships and gaining trust takes time, a lot of time, and if the project is restarted, the stakeholders will need to accept that progress will be slow and that financial resources may need to be stretched to last as long as necessary.

SHOULD THE PROJECT BE RESTARTED?

If the Governments can demonstrate that there is still the political will to sustain the project and with a clearer understanding and acceptance of the various roles and responsibilities, the restructuring and acceptance of the PSC as the top body for project governance, the enhancement of support and monitoring by the Implementing Agency, the streamlining of the administrative procedures of the Executing Agency, and the removal of other barriers that have hindered it to date, the evaluation team believes that the project is viable and that if restarted it has a good chance of attaining its objectives successfully.

However, in order for this to happen, the recommendations made in this report must be accepted and implemented by all stakeholders as a package and all elements need to be implemented.  Failure to implement some of the proposed changes or taking more than 4-5 months in agreeing to do so, will jeopardise the success of the project.  If decisions are delayed there is a very real risk that the project may not survive.

1		INTRODUCTION

1.1	Background

The Okavango River Basin (ORB) remains one of the least human impacted basins on the African continent.  Mounting socio-economic pressures on the basin in the riparian countries, Angola, Botswana and Namibia, threaten to change its present character.  It is anticipated that in the long term this may result in irretrievable environmental breakdown and consequent loss of national and global benefits.  Maintaining these benefits requires agreement over the sharing of both the benefits and associated liabilities (to include those of an environmental and ecological nature) through joint management of the basin’s water resources.  The 1994 OKACOM Agreement, the 1995 SADC Protocol on Shared Watercourse Systems and the 1997 UN Convention on the Law of the Non-Navigational Uses of International Watercourses provide a framework for such an agreement.  Under the OKACOM Agreement, the riparian countries are working toward the implementation of an Integrated Management Plan (IMP) for the basin, based on an Environmental Assessment (EA).

To address the critical transboundary elements of the proposed EA and IMP, Stage I of GEF support will enable the completion of a Transboundary Diagnostic Analysis (TDA), and formulate a Strategic Action Programme (SAP).  This Project provides for these activities, and sets the stage for long term investment activities to protect the ecological integrity of the basin.  Specifically, the TDA will develop required physical and socio-economic models across the whole basin needed to facilitate joint management based on wide participation and the removal of institutional barriers.  The SAP will structure diverse inputs and identify specific resources necessary for implementation of the transboundary elements of the EA and the IMP.  A follow-on project will support implementation of the SAP.  The SAP will provide an essential monitoring and evaluation tool for the implementation phase.  The project provides for a process of formal endorsement of the SAP by the participating governments, support to the translation of SAP provisions into national policy and legislation, and the mobilisation of institutional and investment resources for its implementation.

1.2	Purpose of the evaluation

The project has reached the planned half way in its implementation phase and it has experienced some problems, to the extent that all new activities have been halted by UNDP/GEF.  It was therefore considered opportune to commission an independent, interim evaluation which, according to PIR-02, will “address delivery constraints, governance problems, and other issues that have afflicted the project”.  With this background, this evaluation is somewhat different from the standard mid-term evaluation conducted for UNDP/GEF projects – the emphasis is not on the assessment of progress with project activities, because there has been virtually no progress.  The focus is more on determining if there is still support for the project being revived, whether it is viable if it is revived, and with trying to identify solutions to the problems that have constrained the project.  In particular, governance and administrative arrangements, the extent of country ownership, stakeholder participation, financial management, monitoring and any lessons learnt, need to be reviewed.  The evaluation team was also required to examine the continuing relevance of the project in light of the initiation of other activities and the level of commitment to outcomes by all parties.

The evaluation was commissioned by UNDP and has been conducted according to guidance, rules and procedures for such evaluations established by UNDP and the Global Environment Facility.

The full Terms of Reference for the Independent Interim Evaluation are to be found in Annex 1.

1.3	Key issues addressed

Even before the evaluation had started it was evident that this project is facing serious difficulties.  The expectations of various stakeholders are in harmony, but the means of achieving the project objectives are the subject of contention.  Roles and responsibilities are not clear, procedures of the Implementing Agency and the Executing Agency are not well understood, project governance is weak, the inception phase got bogged down in secondary activities, delivery rate is well below normal, the Project Manager has resigned and project activities are currently halted.

The fundamental issue to be addressed is whether the project is viable.  An abandoned project is not good for stakeholders, however, a project which proceeds and fails, is even worse.

In determining whether the project should go ahead, and if so, how, the evaluation team attempted to address the barriers that have thus far prevented this project from progressing towards its goals.  These range from the adequacy of project formulation and implementation arrangements, to misunderstandings regarding standard procedures for the implementation of UNDP/GEF projects, ineffective project governance, complex administrative arrangements and a management vacuum with the resignation of the PM.

All these issues are addressed in this report.

1.4	Methodology of the evaluation

1.4.1	Mission schedule

The evaluation was conducted by a team of two independent evaluators.  The team commenced its work from homebase on 14 September 2006.  It then arrived in Pretoria on 18 September and after three days, travelled to Luanda, Angola, on 21 September.  The evaluation team spent seven days in Luanda and then travelled to Windhoek, Namibia, on 28 September.  After seven days in Windhoek, the evaluation team travelled to Botswana and visited Gaborone and Maun.  The team stayed in Botswana for 14 days, after which the team disbanded for the time being.

Following a period of just over four weeks, the evaluation team started work again on 28 November 2006 from homebase and reassembled in Pretoria on 01 December.  After some six days of redrafting and a final presentation, the mission ended on 08 December 2006.

A detailed schedule for the evaluation mission is in Annex 2.

1.4.2	The approach adopted

The evaluation process comprised three phases.  The first phase was one of data and information gathering.  It started with a review of relevant documents made available electronically by UNDP, FAO, the Project Management Unit and the OKACOM Interim Secretariat.  In addition, relevant websites were also visited and studied.  Soon after its arrival in Pretoria, the team received extensive briefings and additional documentation from the UNDP/GEF Regional Coordinator.  Following this, the team embarked on a broad programme of consultations with key stakeholders in each of the three riparian states namely, Angola, Namibia and Botswana.  The aim was to capture as broad a catchment of views and opinions as possible within the time available.

The second phase focused on analysis, discussion and drafting by the team.  During this phase, the team shared preliminary conclusions and drafts with key stakeholders and sought advice on any errors of fact, or omissions, or inaccuracies.  This phase concluded with the production of a preliminary draft version of the report which was released for comments by UNDP.

The third and final phase refined the draft in the light of the comments received, and produced this final report.  Information provided in the comments received was used substantially in revising the draft.  Where no specific source is given for information from one or other of the stakeholders, this information would have come from comments which are kept on file.

Guidance provided by GEF and UNDP, was adhered to by the team in undertaking this interim evaluation.  As noted in the Acknowledgements, the team benefited greatly from the wide spectrum of views, opinions and advice that it received during the course of its work.  However, the conclusions reached and the recommendations made, represent the independent views of the team members alone.

1.4.3	Documents reviewed and consulted

The evaluation team was provided with an initial list of documents in the Terms of Reference.  Further advice on relevant documents, as well as the documents themselves in most cases, were provided by UNDP, FAO, the  PMU and the OKACOM Interim Secretariat.  The evaluation team sought additional documentation to provide us with the background to the project, insights into project implementation and management, a record of project outputs, etc.  The full list of documents reviewed and/or consulted by the team is in Annex 3.

The annex also contains a short list of the websites that were visited and reviewed.

1.4.4	Consultations

Consultations by the evaluation team took place primarily in the three capital cities namely, Luanda, Windhoek and Gaborone.  However, brief visits were also undertaken to Pretoria and Maun and a number of meetings were held there as well.

The team consulted over 60 individuals in all.  These ranged from the key stakeholders (OKACOM Commissioners and OBSC members, UNDP and GEF) to project personnel (past and present), various government officials and technical specialists dealing with water and related issues, NGOs, and personnel from other projects working in the Okavango Basin.  Most meetings followed the same pattern, namely, a brief introduction on the purpose of the mission followed by an identification of the relationship that the consultee had with the project, if any, and his/her views on the project and its problems.   Particular emphasis was placed on the role and performance of the PSC, OKACOM, UNDP, FAO, the Project Manager and the Governments.  When appropriate, consultees were asked about their country’s policies, strategies, laws and regulations for sustainable water resources management.  A series of telephone consultations with key individuals was conducted and the team also posed written questions to some key stakeholders.  The evaluation team gave an undertaking that the sources of information will not be disclosed unless this was important for the report and in such cases, only with the agreement of the source.

A full list of persons met and consulted by the evaluation team is to be found in Annex 4.

2	THE PROJECT AND ITS DEVELOPMENT CONTEXT

This section deals specifically with the project as portrayed in the Project Document.

2.1	Project start and duration

OKACOM and its partners, through the three Governments of Angola, Namibia and Botswana, applied for GEF funding support in 1996.  This was approved and the GEF Preparatory Phase ran from 1997 to 2000.   The full project was approved by the GEF Council in August 2000 but it was only in April 2003 that it was rendered effective following signatures of the Project Document by all parties.  The full project suffered further delays and it only started in November 2004.

The project was planned to last for three years so it was expected to come to an end at the end of 2007.  However, the project faced a number of problems since initiation especially with the setting up of project operations, including the identification and rehabilitation of office space, the establishment of a field office, and staff recruitment.  Delays in this establishment phase have retarded other project interventions and delivery rate has been below 20%.

The Project Manager resigned in October 2005 (with effect from March 2006) and following the second PSC meeting in November 2005, UNDP decided to halt any new project activities pending the outcome of this evaluation.  Ideally, this should have been a collective decision by the PSC, however, in the circumstances, UNDP could not rely on the PSC.  If restarted, the project will have around 2-3 years to run.

2.2	Problems that the project seeks to address

According to the ProDoc, the draft TDA which was produced during the PDF-B phase, found that the natural resources of the basin are already subject to demands for water and land from agriculture, and urban and industrial development, from both within and outside the Basin.  These demands are already resulting in modified water quantity, quality and sediment flows and raise the issue of minimum requirements if the Basin is to continue to furnish its environmental benefits and maintain a critical stock of freshwater assets.  However, the national institutional and policy responses to date have focused exclusively on supply management and in financial, economic and environmental terms, this approach is not sustainable.  If these threats are not addressed through a coordinated management approach, irreversible changes in the Basin’s water balance, and hydrochemical and hydrogeomorphological impacts are anticipated.  Such changes will in turn impact the productivity and environmental integrity of the Basin as a whole.

The ProDoc identified the proximate cause of environmental degradation as three-fold – unplanned abstraction from watercourses and aquifers, increased effluent disposal and non-point pollution sources, and the accelerated erosion of land hydrogeomorphologically linked to the Basin.  But the root causes lie with patterns of socio-economic development – population growth, urbanisation and industrialisation.  Key factors in these trends include : over-grazing which is already resulting in accelerated land and soil degradation in Namibia and Botswana; unplanned development in Angola along de-mined transport corridors in the Cubango and Cuito sub-basins as the peace process re-settlement occurs; and pressure for new and increased abstraction of raw water to service urban expansion and irrigated agriculture.  It is anticipated that these factors will continue to accelerate new demand for raw surface and groundwater in the Basin and its immediate region, and accelerate the process of land use conversion for subsistence agriculture.

2.3	Overall and Immediate Objectives of the project

According to the ProDoc, the overall project objective is :

To alleviate imminent and long-term threats to the linked land and water systems of the Okavango River through the joint management of the Okavango River Basin water resources and the protection of its linked aquatic ecosystems, comprising all wetlands, fluvial and lacustrine systems, and their biological diversity.

A two-stage approach has been adopted.  Stage 1, the subject of this intervention, will involve the preparation of the SAP.  Stage 2, the subject of a subsequent intervention, will involve implementation of the SAP.

The ProDoc further explains that the purpose of the project during Stage 1 is threefold :

- First  -  to overcome current policy, institutional, human resource and information barriers and constraints to coordination and joint management of the Basin

- Second  -  to complete a transboundary analysis to underpin a programme of joint management

- Third  -  to facilitate the formulation of an implementable programme of joint management to address threats to the Basin’s linked land and water systems.  A Strategic Action Programme (SAP) approach will be used as the programming instrument for the project

These three “purposes” of the project provide the framework for the three Components of the project and can be considered as its three immediate objectives.

2.4	Main stakeholders

The ProDoc notes that many public organisations as well as individual scientific and research institutions and consultants have invested their resources in understanding and analysing the Okavango Basin.  The ProDoc also refers to schools, colleges, research institutions, and NGOs in the Basin as having a high degree of interest in an Okavango initiative.  However, it failed to identify specifically who the key stakeholders in the project were.  It then makes a commitment to involve various stakeholders in project monitoring, evaluation, and implementation through numerous consultations and workshops and improved internet access among stakeholders.  The ProDoc also dedicates an annex to the subject, entitled Public Involvement Plan Summary, and makes mention of ways in which to involve the stakeholders.  However, the evaluation team was informed that no Public Involvement Plan was prepared by the project before its activities were halted.

Based on their perceived degree of influence on the project and their expressed interest in it, the evaluation team identified the following as the key stakeholders for the purpose of consultations :

The OKACOM Commissioners, members of the OBSC, and the interim OKACOM Secretariat; GEF; FAO (at Rome HQ, at Accra Regional and at Country levels); UNDP Country Offices; personnel of the Project Management Unit, past and present and others associated with the project; the management, technical and scientific communities in each riparian State, especially those with responsibilities for water planning and management; and, local NGOs which have not been very involved to date.

2.5	Results expected

The ProDoc foresees the End of Project Situation as one where :

- Key institutional barriers to integrated management will have been overcome.

- Broad awareness about the state of the basin will have been raised at the national, regional and international levels.  This will draw attention of decision makers to the critical planning needs and guarantee political and financial support for SAP implementation.

- OKACOM will have been strengthened as both a political forum for involving key high level government officials to negotiate the sharing of transboundary water and as an initiator of policy shifts at national and regional level.

- There will be in place  -

- mechanisms for consultation, communication, and participation in all three riparian countries;

- an updateable knowledge base;

- policy initiatives launched and cross sectoral integration mechanisms established;

- a joint programme for management of the basin;

- natural resource management capacity built at regional and national level;

- finance mobilised for SAP implementation and beyond.

- The project will have demonstrated new collaborative approaches to transboundary water management that are based on open understanding and consensus while also fulfilling the countries’ stated desires to understand and protect the basin in order to meet a potentially divergent range of national interests including disparate levels of socio-economic development, nature conservation, and eco-tourism.

- Explicit links between this International Waters project and the GEF’s  biodiversity focal area are anticipated and will be articulated in the SAP.  This is particularly the case in Botswana where natural resource conservation activities will be promoted on the basis of the water resource management analysis carried out in the project.

In addition, the LogFrame Matrix in Annex 3 of the ProDoc, lists the following as indicators of the satisfactory achievement of the three components :

- Consultative fora established

- Enabling environment (policy, law institutions and human resources) enhanced

- Public and private sector capacity to implement SAP

- OKACOM review completed and internalised

- Completed TDA

- SAP endorsed and financed

Unfortunately, the project had made no significant progress towards any of the above targets or indicators by the time activities were halted.

3	FINDINGS : PROJECT FORMULATION

This section deals specifically with the formulation phase of the project as evidenced by the ProDoc and supplemented by additional information made available to the evaluation team.

3.1	Ownership

This is a project of the Governments of Angola, Botswana and Namibia whose relationship with the project is through their Permanent Okavango River Basin Commission (OKACOM).  As Pinheiro et. al. explain, it was OKACOM that developed the project concept and approached GEF through UNDP for assistance.

OKACOM is identified as the project’s Coordinating Agency while Angola is designated as the lead country in the ProDoc and accepted to serve as the host for the PMU.  From the indications available to the evaluation team, it can certainly be said that OKACOM sees itself as the project owner.   The evaluation team is impressed by the high degree of ownership shown in this project by OKACOM and others in the three riparian states.

However, the ProDoc leaves no doubt that GEF also sees itself as co-owner of the project when it states that “In all documentation, information, signage, and written and oral communication, this project will be referred to by the title “GEF Environmental Protection and Sustainable Management of the Okavango River Basin”.  All project documentation, information, signage, and written and oral communication material related to this project must carry such project title together with the logo of the Global Environment Facility (GEF) and the acknowledgement “This project is partially (fully) funded by a grant from the Global Environment Facility  (GEF).”  The GEF logo and the acknowledgement must be at least of equivalent size to any other logo or acknowledgement appearing on any documentation, information material, signature, or communication material and must appear first.”

The team feels that in effect this project is a partnership between GEF and the Governments through OKACOM and the benefits are mutual.

3.2	Project logic and design

The project logic for GEF is that there are global environmental benefits to be gained in addition to the national ones.  The global benefits will accrue through the transboundary nature of the work which will be implemented by the project for the TDA and the SAP.  However, this is not an evaluation of the GEF-ability of the project and the extent to which it satisfies the usual GEF requirements – these matters would have been addressed during the STAP review of the original project brief and the project would have been accepted as satisfying GEF criteria and requirements.

The project is designed according to the classical approach taken by GEF for this type of intervention.  According to the Training course on the TDA/SAP Approach in the GEF International Waters Programme, “the Transboundary Diagnostic Analysis (TDA) is a scientific and technical fact-finding analysis used to scale the relative importance of sources, causes and impacts of transboundary waters problems. It should be an objective assessment and not a negotiated document”.  On the other hand, the “SAP is a negotiated policy document which should identify policy, legal and institutional reforms and investments needed to address the priority transboundary problems”.   The evaluation team was told that it seems that GEF has only one model and that it is expected to fit all circumstances, and that this is not right.  The team was told that there is a need for different approaches to fit different circumstances such as those faced by Angola in the period immediately following a civil war.

At this first phase, the project design comprises the two main elements, namely the TDA and a SAP.   The TDA will provide the required physical and socio-economic models across the whole Basin needed to facilitate joint management based on wide participation and the removal of institutional barriers.  The SAP will structure diverse inputs and identify the specific resources necessary for implementation of the transboundary elements of the Environmental Assessment and the Integrated Management Plan which are targeted by OKACOM.  The second phase of the project, which will be the subject of a separate intervention, will support the implementation of the SAP.  The project provides for a process of formal endorsement of the SAP by the participating governments, support to the translation of SAP provisions into national policy and legislation, and the mobilisation of institutional and investment resources for its implementation.

According to the ProDoc, the TDA will provide an analysis of priority transboundary environmental problems, identify the scale and causes of degradation (proximate, intermediate and root), information gaps, policy distortions and institutional deficiencies.  The formulation of the SAP will be driven by a consultative process with stakeholders and enabled by policy, legal, institutional and financial commitments.  When finalised through a series of consultative workshops, the SAP approach will be instrumental in defining and driving the necessary policy and financial commitments in the short to medium term.  The SAP will establish clear priorities that are endorsed at the highest levels of each of the three governments and widely disseminated.  Priority transboundary concerns will be identified, as well as sectoral interventions (including, policy changes, programme development, regulatory reform and capacity-building investments) needed to resolve the transboundary problems as well as regional and national institutional mechanisms for implementing elements of the SAP.  Coordination of priorities with those identified under the climate change and biodiversity focal areas will be undertaken during the SAP formulation. The countries and the GEF will agree on the baseline environmental commitments (which should be funded domestically or through donors or loans) and activities that are additional for solving the transboundary priority problems.  A major donor conference will be held when the SAP is in the draft stage to facilitate international commitments to action.

As noted above, this is a standard approach adopted widely by GEF for its International Waters projects.  Presumably, the experience gained from past projects was the guide in setting the timescale for the project at three years.  However, in the circumstances the project faces, it seems that this timescale is unrealistic.  This issue is discussed further below, however, it is noted here as a possible design fault in the project and one which will require attention.

3.3	Linkages between the project and other interventions

The ProDoc refers to on-going initiatives in the Basin.  For example, in Angola it mentions that the World Bank was preparing a national Water Sector Development Project which was expected to channel resources for water supply and sanitation to major provincial capitals, Cabinda, Lubango, Lobito-Benguela, Luanda and Namibe, but it adds that none of these is in Cuando-Cubango province.

In Botswana the ProDoc reports that the Government is committed to the implementation of its 8th National Development Plan for the period 1997/8-2002/03 which anticipates various capital development projects and studies, some of which are related to water management in the vicinity of the Okavango Delta.  These national plans include; Major Village Water/Sanitation Development; Groundwater Studies and Protection; Hydrological Support including updating of the Okavango Forecasting Model; and International Water Planning and Development.

For Namibia, the ProDoc notes that the First National Development Plan for the period 1995/6-1999/2000, focuses on health and education sectors with a programme of rural water supply and sanitation supported by GTZ, and that additional community development activities were carried out by Namibian and international NGOs.  It also mentions that a World Bank/GTZ/UNDP Water Resource Management Review had been launched in early 1998 and that elements of this were to be directly related to transboundary water issues, including the Okavango.

The analysis of incremental costs in Annex 2 of the ProDoc is somewhat more extensive in its reference to on-going initiatives.  However, the main purpose of the discussion is to identify the value of the baseline.

Having mentioned these other initiatives, the ProDoc fails to identify linkages that the project may/should have with them, whether there are any mutual benefits to be gained from cooperation, or whether there are any lessons that could have arisen from them.

3.4	Implementation and institutional framework

The Project is executed by the Food and Agriculture Organization of the United Nations (FAO) on behalf of UNDP which is the GEF Implementing Agency and “Execution will be based on the rules and procedures established by the United Nations System”.

The figure below, taken from the ProDoc is meant to illustrate the relationships between the key stakeholders in terms of project governance.

General Framework for project implementation (from the Project Document)

The ProDoc noted that “OKACOM will continue in its role as the inter-governmental mechanism for co-ordination, delegating specific tasks to OBSC and linking high-level policy and decision-makers from the three Okavango basin countries”.  According to the ProDoc, the PSC “will have overall responsibility for the project and will provide management and financial guidance”.

The ProDoc noted also that the Project Management Unit (PMU) “will be appointed by the PSC and will work under its guidance to oversee day to day implementation of project activities”.  UNDP/GEF acceded to the decision by OKACOM that the PMU will be based in Luanda, Angola.

Specific line ministry coordination and multidisciplinary collaboration, including national NGOs, will be undertaken at country level by the National Co-ordination Units (NCUs).

The relationship between these layers of governance, as illustrated in the diagram above, is not accurate and it has led to misunderstandings.  Unfortunately, by showing the Governments, OKACOM and OBSC above the PSC, the diagram gave the wrong impression regarding the supreme nature of the PSC.

3.5	Stakeholder participation in project formulation

FAO advised the evaluation team that all Government inputs in project design and formulation were channelled exclusively through the OBSC, the delegated sub-committee of OKACOM.  National OBSC members were active in providing and facilitating much technical information during the PDF ‘B’ phase.  Formal meetings of OBSC were then used to review the draft TDA and negotiate and finalize the project brief and the project document.  The bulk of the support and input was noted as having come from Namibia.

The ProDoc reports that the consultation process set up during the PDF work provided a clear message that education, participation and consultation had to go hand in hand.  Both community members and leaders expressed the opinion that they would not be able to participate in the consultative process if they did not have a good grasp of all the issues.  Schools, colleges, research institutions, and NGOs in the basin expressed a high degree of interest in the initiative and a number of stakeholder meetings and consultations were held.  The project made provision for a significant education, training, and information effort to be included.

3.6	Conclusions on project formulation and design

The evaluation team concludes that the high level of ownership of the project by OKACOM and OBSC, together with the positive views of those working on parallel projects in the Basin, augur well for the success of the project if it were to be restarted.  Virtually all that we have spoken to said that the project must continue.  Many, especially those representing community level stakeholders and potential beneficiaries, have great expectations for the project.  The team detected some sadness and anguish that the project got to the point where its activities had to be halted, but we also felt that maybe stakeholders are now prepared to move on.  The team was told that “the project must not close – the people of the Okavango Basin need the project”.

This is a simple model which has been successfully applied in many other projects and as such, the project design is basically sound and, in principle, the project should be viable.   The original Objectives (or components) of the project are still valid and in spite of the initiatives that have been implemented in the meantime, the GEF project is still relevant since none have created the overarching and holistic context for management from a basin-wide perspective, that the GEF project is targeting in the Strategic Action Programme (SAP).

If the project is restarted, the opportunity should be taken to rephase and rebudget the project, but not necessarily redesign it.   Maybe the emphasis should be shifted away from the TDA and more to the SAP component.  The TDA must be completed in the shortest possible time and if gaps are identified, it should not be essential to wait until they are filled – gaps can be recorded and the SAP can provide the activities that will fill the gaps at the operational phase.  The team also feel that to the extent possible, the emphasis of the project should be shifted from the capital cities to the Basin which is where the natural resources are and where those that rely on them, live.  For example, the TDA activities that are to be carried out by the NCUs could be based in Menongue, Rundu and Maun respectively.

4	FINDINGS : PROJECT IMPLEMENTATION

This section reports the findings of the evaluation team on the manner in which the project has been implemented, administered and managed.

4.1	Project governance

4.1.1	General governance issues

Many of the problems with governance can be traced to the confusion that exists regarding roles and responsibilities of individual stakeholders as well as a lack of clear understanding of the objectives, constraints, procedures and processes of the GEF.

The three Governments agreed, contractually, to receive GEF funds and to abide by the procedures of the implementing agency, namely UNDP, according to their respective Standard Basic Assistance Agreements (SBAA) with UNDP.  These procedures comprise the legal basis for the project.  On its part, UNDP contracted a sister organization from within the UN family, FAO, to execute the project.

Angola was identified as the lead country in the ProDoc.  This is in respect of the UNDP Country Office and to a lesser extent, the FAO Country Office.   In reflection of this “centre of gravity” status of Angola, the Government of Angola and the Angolan OKACOM Commissioners were also assigned a lead role by their peers.  However, from the project governance perspective, Angola is but one of the three Governments that have equally committed themselves to the project.  Each of the three Governments has equal rights, responsibilities and powers in respect of the project.  It is therefore more accurate to refer to Angola as the host country (for the PMU) rather than the lead country, and this role does not comprise any direct project management responsibilities.

As discussed elsewhere, the implementation arrangements illustrated in the ProDoc created problems for the governance of the project since they could be interpreted as requiring the PSC to report to OKACOM.  The team believes that this was not intended since it would negate the position of the PSC as the highest governance body for the project.  Having said that, the special relationship that OKACOM has with this project, must be recognized and this is discussed in the following sections below.  This is borne out by the fact that country level involvement in project implementation has been effected almost exclusively by the OKACOM Commissioners and the OBSC members acting upon the mandate given them by their respective Governments.

4.1.2	Policy and guidance – the Project Steering Committee

The Project Steering Committee sets the policy for the project and provides guidance and directions to the Project Manager and other project stakeholders.  It also supports UNDP which maintains ultimate accountability to the GEF for the delivery of project products and the administration of project funds.  Project funds are administered as per the Standard Basic Assistance Agreements between UNDP and the Programme countries, which govern the use of UNDP funds.  UNDP and the three Governments form part of and respect PSC decisions and agreements.  If a situation arises where UNDP feels that its mandate or its accountability could be compromised by a decision of the PSC, it should attempt to resolve the matter by negotiation taking into account the signed ProDoc and the SBAA, before it considers other action.

The PSC must be recognized as the highest governance body for the project (see diagram on page 25).  Decisions made at the PSC are final and they must not be re-litigated, except by being brought back to the PSC.  Ideally, in spite of any disagreements around the PSC table, once a decision is made, it should be supported by all members when outside the meeting room.  It is important to provide a united, collective direction and guidance to the PM and others who are implementing the project.

From all accounts, the PSC, which met twice in the life of this project, has so far failed to perform as expected.  Problems were identified with the Terms of Reference provided by the ProDoc but attempts to overcome these problems did not succeed.

Annex 5 contains proposed new Terms of Reference for the PSC.  The proposed ToRs suggest that the PSC will comprise :

- One representative from each of the participating Governments : Angola, Botswana and Namibia (OKACOM Co-chairs or as the Governments so decide)

- One representative for UNDP at Country Office level (suggested Resident Representative or Country Director from Angola Country Office as the lead UNDP CO)

- One representative from UNDP/GEF Regional Coordination Unit

- One representative from FAO as Executing Agency

The following will also be invited / expected to attend meetings :

- Other members of OKACOM

- Project Manager – required to attend and report on progress

- Project Budget Holder – required to attend and present  financial account

- Members of OBSC to advise on technical issues that may arise

- Relevant representatives of related projects in the Okavango Basin to advise on cooperative and complementary activities

PSC members may nominate an identified alternate who will attend PSC meetings in the event that the designated representative is unable to attend.  Alternates will be expected to be fully briefed and able to make decisions on behalf of the permanent member.  It is also expected that the alternate will report back fully to the designated representative.

PSC business will be conducted on a consensus basis.

According to the proposed Rules of Procedure, the PSC, which will be co-chaired by the UNDP-Angola Resident Representative or Country Director as well as an OKACOM Commissioner, will meet at least every six months and more frequently if considered necessary.  Meetings will rotate between the participating countries, taking into account logistical and resource considerations.  The agenda for each meeting, which is to be prepared by the PM in consultation with the co-Chairs and which should reflect issues raised by members, should be available in good time to permit adequate consultation before the meeting.

4.1.3	Role of UNDP as the Implementing Agency

As implementing agency, UNDP is responsible to the GEF for the timely and cost-effective delivery of the agreed project outputs.  It achieves this through its understandings with the participating Governments and its contractual arrangement with FAO as executing agency.   UNDP has an obligation to ensure accountability, and its efforts in this respect are spearheaded by the Principal Project Country Office, which in the case of this project is its office in Angola.   Within the UNDP system, the Angola Country Office has been delegated with legal responsibility for the GEF funds.

The UNDP Resident Representative in Angola may approve, following consultation and agreement with the UNDP/GEF Regional Office and the Government signatories to the project document, revisions or additions to any of the annexes of the ProDoc, revisions which do not involve significant changes in the immediate objectives, outputs or activities of the project, and mandatory annual revisions which re-phase the delivery of agreed project inputs or increased expert or other costs due to inflation or to take into account agency expenditure flexibility.  The UNDP Resident Representative in Angola also chairs the Annual Tripartite Review, coordinates inputs from the participating UNDP Country Offices into the annual Project Implementation Review for submission to UNDP/GEF, ensures that project objectives are advanced through the policy dialogue with the Government of Angola, and undertakes official transmission of reports to the GEF focal points of the participating countries.

The UNDP Country Offices in Botswana and Namibia, have a lesser role than that of the Country Office in Angola, but they are still required to act as the project focal point, in coordination with the PMU and FAO, for all national stakeholders, ensuring prompt sharing and transparency of information, provide networking support services through the PSC by linking the project with relevant national initiatives, provide inputs into the annual GEF Project Implementation Review, maintain close links with the national FAO Offices, provide logistical support for national workshops, as needed, participate in the annual Tri-Partite Review, ensure that project objectives are advanced through UNDP’s policy dialogue with the Government, and undertake the official transmission of reports to country GEF focal points.

The work of the UNDP Country Offices is supported by the UNDP/GEF Regional Coordination Office, which also provides coordination within the whole UNDP/GEF portfolio of projects for the region.  More specifically, the UNDP/GEF Regional Office provides technical support to UNDP Country Offices and Government GEF Operational Focal Points, assists the executing agency with the recruitment of senior project personnel, approves the project inception report and terminal reports, reviews budget revisions prior to signature, follows up closely on implementation progress, assures the eligibility of project interventions in light of GEF policy guidance and approved project design, represents UNDP/GEF on the PSC, and approves Annual Project Implementation Reports, including performance ratings, for submission to GEF.   It was pointed out to the team that the GEF requirements can be quite onerous and bureaucratic at times and quite inflexible; and to some, UNDP appeared as if “dictating”.  It was suggested that if GEF’s approach could be flexible enough to reflect and respect local circumstances, it is likely that this will ease the somewhat critical views held by some stakeholders of UNDP/GEF.

From records of meetings and other documents made available to the evaluation team it would appear that the greater part of the UNDP input to the project proceedings has come from the UNDP/GEF Regional Office.  UNDP-Namibia also played an active role but the input from both the Principal Project Country Office in Angola and the Country Office in Botswana, has been somewhat limited.  The evaluation team was told that resources were limited in UNDP Country Offices and that this often hampered a higher degree of participation.  However, the team was also advised that as a GEF Implementing Agency, UNDP receives a fee aimed at reimbursing the costs of project development and supervision, and for monitoring project implementation.

UNDP-Angola needs to take a more proactive role in monitoring and supporting the project and in communicating with its sister offices in Gaborone and Windhoek.  In order to do this effectively, the office personnel resources dedicated to the environment theme will need to be strengthened.  A close working relationship with the PMU could be instrumental in reversing the weak delivery rate experienced by the project thus far and which is “dragging down” the Country Offices’ performance ratings.

UNDP advised the team that it has had difficulty with the administrative procedures that have been used by FAO in executing the project and which have contributed to the low delivery rate by the project.  These are discussed fully under Section 4.2 below where the role of FAO as executing agency is considered.  However, as quite rightly pointed out by FAO, UNDP clearly noted in correspondence that "where reference is made in the Project Document to the employment of UN system guidelines for administrative and other services, we would fully expect that FAO will use its own rules and procedures. This will include audit procedures. Note that FAO's responsibilities in this regard are governed by the Standard Basic Executing Agency Agreement (SBEAA) signed between FAO and UNDP”.  In the event, this generic understanding has not been adequate for this project and it is not enough for UNDP to say they are unhappy with the administrative processes applied by FAO.  There is a need for specific improvements, even if some FAO policies may need to be set aside – e.g. the involvement of a regional office and the frequency and formats of the financial reports.  It is essential that the agreed arrangements between UNDP and FAO are recorded in a formal Memorandum of Understanding specific to this project.

4.1.4		Role of OKACOM

The Permanent Okavango River Basin Water Commission (OKACOM) was established by the Governments of Angola, Botswana and Namibia in 1994.  According to Pinheiro et. al., the first major achievement of OKACOM, barely nine months after its formation, was to develop a proposal for a project to carry out an environmental assessment of the Okavango Basin and to develop an integrated water resources management strategy.   OKACOM set up OBSC originally to manage this project.

OKACOM approached the GEF, through UNDP, to help fund the proposed project and GEF made available project development funds to carry out a transboundary diagnostic analysis (TDA) and prepare a project brief.  After some delays, this was followed by further financial assistance by the GEF to the three riparian Governments to finalize the TDA and formulate a Strategic Action Programme (SAP).

Quite rightly, OKACOM sees this as its project and it has a high stake in it.  And, while from the UNDP/GEF perspective it is a project of the three riparian Governments it is evident that the Governments are working through OKACOM for the purpose of this project.

OKACOM decided to be represented on the PSC by the OBSC which was not empowered to make or support decisions.  OKACOM co-Chairs received reports from their OBSC colleagues following PSC meetings and at times may have felt that some decisions that had been finalized by the PSC required further investigations and discussion.  Unfortunately, this resulted in the decisions being reversed unilaterally by OKACOM following each of the two PSC meetings.  This has undermined the PSC, placed the PM in an untenable position, and jeopardised the role of UNDP as the organization accountable to GEF for the funding that has been received.

These misunderstandings may have arisen from the ProDoc where the role of OKACOM in project implementation is not entirely consistent.   For example, on page 11, the ProDoc says – “This initiative will be driven by OKACOM in which the countries transboundary technical and policy analysis functions are invested and who will be responsible for co-ordinating formulation of the SAP and its subsequent implementation”.  However, on page 20, it says - “The Project Steering Committee (PSC) will have overall responsibility for the project and will provide management and financial guidance. The PSC will be instrumental in feeding back initiatives and identifying investment opportunities in the SAP through the OBSC to OKACOM”.

Once again, on page 12 the ProDoc says – “To initiate all outputs, OKACOM will establish a small appropriate project executive office, a Project Management Unit (PMU), together with national counterparts in National Co-ordination Units (NCUs)”,  and this is followed on page21 by the statement that – “The Project Management Unit, (PMU) will be appointed by the PSC and will work under its guidance to oversee day to day implementation of project activities. The PMU will play the primary role in ensuring co-ordination of the project with other relevant activities in the region”.

Given that the PSC must be accepted by all stakeholders as the highest governance body for the project, and in recognition that OKACOM is the originator of the project concept and the most direct beneficiary of the project, the evaluation team believes that the three OKACOM Co-Chairs should serve as members of the PSC and that they take it in turn to co-chair the PSC meeting together with the UNDP Angola Resident Representative.

4.1.5	Conclusions on project governance

Many of the problems with governance can be traced to the confusion that exists regarding roles and responsibilities of individual stakeholders as well as a lack of clear understanding of the objectives, constraints, procedures and processes of the GEF.

The PSC must be recognized and supported by all stakeholders as the highest governance body for the project.  As such, it must have both the authority and the power to set policy for the project and to monitor its performance.  By confirming and accepting that the PSC is the highest body for governance of the project, and that issues and disagreements are brought to the PSC for resolution, stakeholders will avoid issues becoming personalized, which is what caused the downfall of the project.

The membership of the PSC must include all the key stakeholders, in particular the Governments of Angola, Botswana and Namibia represented by their OKACOM Co-Chairs or as the Governments may decide.  UNDP/GEF as the funding source, UNDP as the organization that is accountable for the GEF funds, and FAO which is the organization entrusted with the execution of the project, make up the other members of the PSC which will be co-chaired by UNDP and OKACOM and will conduct its business by consensus.  The Project Manager, with the support of the Project Budget Holder, will be required to attend PSC meetings and inform the PSC.  Other OKACOM Commissioners and OBSC members should also attend to assist with technical and other matters.  Likewise, NCU Coordinators (if available) and representatives from other related projects in the Basin would be welcome to attend and inform the PSC.

As implementing agency, UNDP must be more proactive, and in particular the country offices need to be more engaged.  Of these, the Principal Country Office in Angola must assume the lead role in supporting and monitoring the project through the PMU.  Furthermore, UNDP needs to take a more assertive stance in its requirements of FAO in the delivery of its contractual obligations and this needs to be the subject of a Memorandum of Understanding specific to this project.

The diagram on the following page illustrates the frameworks for project governance and project implementation, as proposed by the evaluation team showing proposed roles and responsibilities.

Project Governance and Implementation/Operational frameworks showing proposed roles and responsibilities

4.2	Project administration

4.2.1	The role of FAO as the Executing Agency

FAO has a contractual arrangement with UNDP to facilitate, support, administer and execute the project so as to achieve the stated objectives and outputs.  As the project Executing Agency, FAO has the overall responsibility and accountability for the delivery of all the technical, financial, operational and administrative services to achieve the stated outputs and objectives.

As it advised the evaluation team, FAO sees itself as having three roles in particular:

“Technical:  the technical role of FAO is to ensure that all project activities are conducted according to the highest technical standards and in a timely manner.  FAO deploys its subject specialists across the full range of project outputs. World class expertise in natural resource management, agricultural practice, economics and international water law are available in-house to respond to project requests.

Operational: the operational role can be summarized as to ensure effective and efficient project management in order to allow the implementation of all activities as envisaged in the project document, its annexes and annual work plans, in support of the technical role described above. This includes consultation with and substantive reporting to the parties involved.

Administrative: to support the technical and operational roles, including smooth implementation of all activities, from personnel to procurement, to general project administration, and financial services, including reporting on financial accountability. FAO rules and regulations are to be applied.”

The choice of FAO as executing agency has been questioned and it was felt that it may not be the best organization to be assigned the task.  According to the ProDoc, three criteria were applied for the selection of FAO as the executing agency.  Each of these is discussed below with the evaluation team’s observations.

1] Familiarity with rules and procedures prescribed by UNDP for project execution -

The evaluation team was advised that while FAO may have been familiar with the rules and procedures of UNDP, they finished up applying their own which are different and which were difficult to harmonize with those of UNDP.  It would seem that “familiarity” with the UNDP procedures is not enough and “similarity” may have been a more appropriate requirement.

2] Knowledge of the thematic focal areas, to be addressed by the Okavango IW project, particularly irrigation technology, agriculture within the context of river basin management and land degradation -

The evaluation team was told that FAO no doubt has knowledge of irrigation technology, agriculture and land degradation.  However, the likely scope of the SAP is broader than this and could include mining, tourism, biodiversity conservation, energy, etc.  Presumably, if this expertise is needed it cannot be expected to be provided by FAO in-house capacity and will be contracted in.  In the same way, so could expertise in irrigation, agriculture and land degradation had another organization been engaged as Executing Agency.

3] Operational presence in the region, with an office in Angola -

FAO has an office in each of Luanda, Windhoek and Gaborone.  While the Luanda office appears reasonably well-resourced, those in Windhoek and Botswana (the Country Representative is resident in Harare) are not adequately resourced and none of the offices seem to be empowered to contribute to the project either technically or operationally.

FAO decided to base the Budget Holder and administrative support for this project at its Regional Office in Accra, Ghana, following a corporate policy to decentralize field operations.  This created an additional administrative layer for project management and FAO did not identify any additional value contributed to the project by the regional office in Accra, when invited to do so.  Instead it listed the rationale for progressively decentralizing field operations, as follows:

- Project operations and the technical support should be brought closer to the concerned countries (as a guiding principle, FAO technical support should be made available from the office closest to the location where the project inputs are required, subject to the availability of the relevant technical expertise).

- The proximity between the BH and the project facilitates monitoring and operational backstopping.

- The BH develops a “regional” experience and can more easily apply the lessons learned of other projects in similar contexts.

- The decentralization has also helped reduce the indirect operations costs of the Organization which, as it is the case for other UN agencies, are not entirely recovered through the Project Servicing Cost (10% in the case of this project).

Based on this rationale it would be more in keeping with FAO policy and common sense to move the Budget Holder and all administrative support for this project to the FAO office in Luanda.  However, as noted above, FAO country offices do not appear to be sufficiently empowered to provide the necessary support to a regional project such as this.  In the circumstances, the evaluation team believes that the office of Budget Holder could be based at HQ in Rome thus bringing together the administrative and technical support to the project.  However, the evaluation team believes that what is more important, and regardless of where the Budget Holder is located, is that the PM is provided with the delegation, powers and flexibility to do the job.

As noted above, FAO charges a servicing fee known as the Project Servicing Cost, and this amounts to 10% of the project budget.  This is in common with all UN agencies and it covers administrative services (such as recruitment and servicing, procurement and contracts, budgeting, accounting, reporting, custody of funds, etc) as well as operational services (such as expert identification, supervision and monitoring, specifications for equipment, etc).

In addition, the ProDoc identified the sum of $150,000 as an in-kind contribution by FAO to the project.   According to FAO, this was the value of the contribution by the Lead Technical Unit which  “coordinated detailed review and advice from subject specialists in environmental economics, remote sensing, soils, integrated pest management, fisheries, forestry, water law and land tenure upon request from the Project Manager”.  This could not be ascertained and in any case the statement may be a bit premature since the project had not become fully operational before activities were halted by UNDP.

FAO also noted that the in-kind contribution “also includes the time provided by FAO technical staff, not charged directly to the project budget, for responding to direct technical requests from the Project Manager and his team. This can be estimated at 8 weeks per year (approximately equivalent to US$ 35,000/year) and includes the compilation of sub-national data sets and GIS products derived from FAO databases”.

FAO shared with the evaluation team a Director General’s Bulletin dated May 2006 outlining various delegations of authority and streamlining of administrative procedures which have arisen out of substantial efforts that have been underway in the organization to streamline the administrative processes.  This effort is continuing and is bound to lead to improved delivery mechanisms and enhanced chances of success for interventions.

4.2.2	The disbursement process

In response to a request from the evaluation team, FAO described its system of financial controls which is based on the “segregation of duties and determination of responsibilities and levels of authority, with detailed rules and procedures in force for all significant administrative and financial systems and processes”.   FAO noted the importance of the “separation of a budget holder’s responsibility for making expenditure decisions from the execution of administrative and financial actions to give effect to those decisions, including related payments. The execution of those transactions is itself subject to the separation of duties and limitations of authority depending on the nature and/ or value of the transaction or payment concerned and the office in which it will be carried out. These processes and transactions are in turn subject to review by internal and external auditors, including auditors engaged locally to review transactions carried out at FAO’s field offices”.

A key person is the budget holder (BH) who “has the responsibility to operate the project and manage project resources. He/ she may delegate responsibility for parts of the budget to other FAO personnel but remains responsible and accountable for all project resources. Project Managers/ CTAs will thus receive delegated authority to incur expenditures against the part of the annual work plan and related expenditure plan that are directly under their responsibility. This is done through a Field Budget Authorization (FBA)”.

In the case of this project, the Project Manager used the authority delegated to the FAO Office in Luanda with disbursements being made through the Imprest Account of the FAORs.  Had the Project Manager had an Imprest Account he would have had the delegated authority to “procure goods and services, including contracts with not-for-profit organizations using Letters of Agreement (LOAs) for up to US$25,000 per transaction”.

The evaluation team came across a UNEP/GEF/UNOPS regional project, in Africa, where the Regional Project Coordinator is advanced funds as and when required (on a cashflow forecast basis), but according to the Annual Work Plan and Budget.  The funds are deposited in an account operated by the Regional Project Coordinator who is required to account for the monies spent when making the next request for replenishment.  This is an admirable extreme in devolution, and it illustrates the extent of delegation and devolution that the UN system is able to implement.  FAO have advised the team that they are prepared to consider such a level of delegation.

The segregation of duties operated by FAO for its disbursement process may have evolved out of a need for strict checks and balances, but it creates a maze of authorities, responsibilities, reviews and approvals and it is no wonder that the system is being reviewed and streamlined.  It was alleged to the evaluation team that the FAO process is too cumbersome for the expeditious implementation of projects.  It is also very rigid and tends to stifle the performance of a Project Manager.  Perhaps if the system had to focus less on procedural minutiae and place more emphasis on the objective of the procedures, projects would be better served, delivery rates would go up and cost-effectiveness would rise.

4.2.3	The recruitment process

The recruitment process of the past Project Manager has been questioned by some stakeholders and FAO were therefore invited to explain the recruitment process in general and they reported as follows :

“The process applicable to all project personnel envisages identification of candidates, selection, recruitment and separation. All the steps have a number of variants depending on the type of personnel input.  All professional candidates must be technically cleared by a Technical Support Officer (Mr Burke in case of this project).

Candidates for the positions of Project Managers/CTAs, are usually identified through a roster search or through vacancy announcements. The Lead Technical Unit (LTU) usually prescreens, pre-selects and interviews the candidates and submits a shortlist to the BH (in this case Mr. De Lannoy in RAFR, Accra) for further action. Based on this shortlist, the BH prepares a submission to the regional Senior Field Staff Selection Panel (SFSSP) at the Regional Office that reviews the submission of the LTU/BH and confirms the shortlist but may also modify the ranking (our underlining). Once the SFSSP has agreed on the shortlist, the BH submits the shortlisted candidates to the FAOR for government clearance. Once government clearance is obtained, the RAF Personnel Officer submits an offer to the selected candidate and, if he/she accepts the proposal as well as the proposed remuneration, issues the contract. Throughout this process only the Personnel Officer has the authority to negotiate the conditions of the contract with the candidate. The Personnel Officer and related staff also provide personnel servicing to recruited staff.

The recruitment process applied by FAO for the recruitment of Project Managers appears thorough enough.  However, it could be very one-sided and internalised to FAO.  According to the ProDoc, “the Project Management Unit, (PMU) will be appointed by the PSC” and presumably this includes the Project Manager.  In the process applied by FAO, there was no input by the PSC and the only input from outside FAO is through the interviewing panel.  Unfortunately, the decision of the interviewing panel can be overturned by the regional Senior Field Staff Selection Panel (SFSSP).

The specifics of the recruitment of the PM for this project are discussed in Section 4.3.2 below.

4.2.4	Travel authorization

It was reported that travel authorization had to be issued each time the PM had to travel.  It was therefore decided to invite FAO to explain the Travel Authorization process and they replied as follows :

Staff member travel:   a) The staff member submits a request for travel authorization (TA) to RAF Travel Unit (TU) based on an approved travel plan (normally one week notice required), specifying route and days spent on mission; b) TU makes necessary checks, processes the TA in the System for approval by HQ. Once the TA is approved, the ticket is issued to the traveller and DSA paid before departure. The total time to process a travel application varies from 1 to 7 days (depending on internal routing).

The team was advised that in practice it usually took three weeks, and tickets and DSA were often issued at the last minute, following reminders, etc.

Consultant travel:   Following the identification of the consultant, upon agreement between the consultant and the FAO Personnel Officer on the remuneration, TORs, etc, and signature of the contract, the RAF Personnel Unit raises in the System a TA for the consultant to travel to the duty station. As soon as the request for a TA is received through the System by the Shared Services Centre (AFDS), the HQ travel unit issues the authorization that the ticket and DSA be provided (or a central travel agent issues a prepaid ticket to the consultant to travel to the duty station), DSA being usually paid at the duty station.  The total time to process travel usually varies from 1 to 7 days. Several issues can affect the processing time, including the requirement to obtain security clearances.

The above has some steps which appear superfluous (such as having to gain approval from HQ in Rome).  It also presupposes that the HQ travel unit and its travel agent know best, without any discussion with, or involvement of, the individual who is to travel.  It is a well-known fact that tickets issued at the point of origin are usually cheaper than those issued from afar and the use of a central travel agent in Rome may not be the most cost-effective option for an organization that is operating projects in all parts of the globe.  Neither is it possible to reflect changing circumstances easily and quickly.

It is a relief to note that in-country travel in accordance with the project document and work plan can be arranged by the FAO Country Office.  In the case of regional projects, FAO “can also issue “blanket” travel authorizations to allow for flexibility, particularly for multiple trips to the countries assisted by the project”.  The evaluation team was advised that FAO is prepared to consider such a “blanket” travel authorization to the new Project Manager, to cover all travel by project personnel to, from and within Angola, Namibia and Botswana, and including Johannesburg.  This will eliminate the need for further authorizations for travel in the conduct of project implementation and places the responsibility for these operational decisions where it should be – with the Project Manager, who is paid to make these decisions and be accountable for them.

4.2.5	Conclusions on project administration

The comparative advantage that FAO was meant to bring to this project is not significant, in that the most unique component is the technical element and this could have been obtained on contract (from FAO or elsewhere), separately from the administrative element which could have been more efficiently carried out by an organization with support systems attuned to those of UNDP.

FAO procedures for disbursements, recruitment and travel are acknowledged by FAO personnel themselves as not being easy – and they must change to reflect the needs of this project, because the alternative is project failure.  FAO has advised the team that the PM will be given the utmost level of delegation with regards to travel authorization; that the Budget Holder will be moved from Accra to Rome thus bringing together the administrative and technical support for the project; and, what is more important, and regardless of where the Budget Holder is located, FAO intends to provide the PM with the delegation, powers and flexibility to do the job.

With the procedural reforms within FAO currently underway in search of greater efficiency, FAO should use this project as a pilot to test a more devolved, delegated and less controlled system.  Existing procedural constraints could be set aside and a more devolved approach to project management could be adopted with streamlined procedures, higher degree of delegation (with accountability), higher levels of financial discretion, broader powers of recruitment and generally allowing greater flexibility to the Project Manager in a climate of mutual trust.

4.3	Project management

4.3.1	The PMU and the NCUs

According to the ProDoc, the Project Management Unit (PMU) “will be appointed by the PSC and will work under its guidance to oversee day to day implementation of project activities”.   A core team was envisaged led by the Project Manager and comprising “national programme co-ordinators [and] the best possible expertise from the riparian countries in water resources; natural resource management; environmental specialists (with emphasis on wetlands); and social and community development”.

UNDP has cooperation agreements with relevant national agencies, namely -  the Ministry of Energy and Water in Angola; the Ministry of Mines, Energy and Water Affairs in Botswana; and the Ministry of Agriculture, Water and Rural Development in Namibia.  Specific line ministry co-ordination and multi-disciplinary collaboration, including national NGOs, were expected to be undertaken at country level by the National Coordination Units (NCUs), which were seen as “the functional equivalents of inter-ministerial committees”.  Accommodation requirements for the NCUs were expected to be provided by the respective Governments.

The project provides financial support for the operation of the Angola NCU, but not for those in Namibia and Botswana.  The evaluation team was advised that the latter two governments saw this as part of their contribution in kind to the project.  However, the team believes that it is not in the best interests of the project to rely on in-house resources when there are real expenses accruing to national organizations.  The team recommends that consideration be given to the project providing support to cover actual expenses incurred by the NCUs of Botswana and Namibia for example for field work, meetings and travel to the Basin.  This is seen as a more equitable situation.

The NCUs have been established in both Angola and Namibia, but not in Botswana.  However, the evaluation team was informed of the significant initiative taken by Botswana through the Okavango Delta Management Plan Project which is nearing completion.  This project, with its Secretariat based in Maun, has coordinated the input of 12 sectors and has covered the work of the intended NCU, more or less.  It is also important to note that the Okavango Delta Management Plan Project employed an almost identical approach to that advocated by the TDA, but at the national level, and the result can also be said to come close to the intended SAP, even if in both cases this is limited to the Botswana sector of the Basin.

The ProDoc also recognizes that the PMU will be based in Luanda, Angola, in accordance with the OKACOM decision taken in June 2001.  The location of the PMU in Luanda has been questioned by many spoken to by the evaluation team.  They felt that Luanda is not an easy place to operate from and that this may have contributed significantly to the problems the project had to face.  The evaluation team accepts the sentiments behind the OKACOM decision to place the PMU in Angola, but agrees that Luanda is a difficult place to work from and that these difficulties need to be kept in mind when UNDP, FAO and the Government of Angola are considering the support necessary for the successful functioning of the PMU.  A good example of the approach that is needed was the budget revision which was undertaken to reflect the higher costs of locating the PMU in Luanda.

From what the evaluation team has been told, many stakeholders feel that the location of the PMU in Luanda is too far from the Okavango Basin and some felt that a more appropriate location would have been Menongue or Rundu.  However, while agreeing in principle, the evaluation team wonders whether the placement of the PMU at either of these two locations is realistic.

As host Government, Angola was expected to provide a suitable premises for the PMU as part of its contribution in-kind.  However, Angola could not meet this commitment and project funds had to be made available to provide the PMU with office accommodation.  Much delay ensued and misunderstandings regarding UN procurement procedures led to further difficulties which have been discussed at length in the PM’s Inception Report.  These have now been resolved and the PMU is now housed in its own premises.  The evaluation team believes that the current PMU premises is adequate to house the PM, the Basin Planner, the Finance Officer and the Administration Assistant who make up the core staff.  The evaluation team noted that the premises is not identified in any way with the project and suggests (unless there are any security or other extenuating circumstances) that appropriate signage should be erected to recognize the project and its key stakeholders.  This would be in keeping with the GEF requirement that its support be acknowledged through appropriate signage.

In view of the problems recounted above and the desirability for the PMU to be closer to the Basin, should the current premises become unavailable, consideration should be given to moving the PMU to Lubango or Huambo where, the evaluation team was told, conditions are not as difficult as in Luanda, which is closer to the Basin (in the case of Lubango, and in the Basin for Huambo) and from where Menongue is more accessible by road and air.

The project budget made provision for the purchase of a vehicle to be based with the PMU.  Supplementary project vehicles for field based project activities are to be provided by the participating government agencies.  In this connection, the evaluation team noticed that the project vehicle in Luanda only carried the FAO logo and nothing else.  This is contrary to GEF requirements on signage.

4.3.2	Project personnel

The project envisaged the recruitment of a Project Manager (also referred to as CTA), an Administrative Assistant, a Secretary and a Driver to make up the PMU.  In addition, the project also provides full-time salary support for the National Project Coordinator in Angola.  The Inception Report refers to the difficulties and delays encountered with these appointments which were delayed by the lack of accommodation and which in turn hindered the project from making progress.

The recruitment process applied by FAO for the Project Manager position has been described above.  The appointment was initially questioned by some OKACOM Commissioners on the basis of its transparency and perceived bias, however, these reservations were later withdrawn and the appointment was allowed to stand.  In the event, the appointee only served for one year and declined the renewal of his contract and resigned.

The evaluation team wishes to suggest that for the recruitment of a replacement Project Manager, the interviewing panel should comprise one representative each from the three Governments (possibly an OKACOM Commissioner), UNDP and FAO.  The interviews should be held in Johannesburg/Pretoria as a neutral centre if the applicants to be interviewed are from Southern Africa, and in Rome if the applicants are from Europe or North America.  However, what is more important is that the decision of the interviewing panel should be final and the record of the  process, including the interview and the basis for selection, should be available for disclosure at least to the PSC, even though the decision cannot be re-litigated.

The evaluation team also suggests that consideration should be given to the recruitment being made at D1 level and that the position should not be referred to as CTA since this is a misnomer and could lead to misunderstandings especially in translation.

Finally, the evaluation team notes the need to review the Terms of Reference for the Project Manager.  In particular the reporting functions of the PM need to be tightened.  He/she is required to do more than simply “consult with, and co-ordinate closely with” the Project Steering Committee.  The Project Manager is required to report to the PSC on project progress and performance, and take directions and guidance from the PSC on project implementation.  He/she must also report to FAO on personal performance and administrative matters.

4.3.3	Special relationship with OKACOM

It has been suggested to the evaluation team that it will be beneficial for the project if the PMU, and especially the Project Manager, had to have a special relationship with OKACOM, in addition to the one through its membership of the PSC.  The team favours such a development and can see benefits accruing, as long as the objectives of the relationship are clearly understood by both sides.

The team sees this taking the shape of an OKACOM member being nominated by OKACOM to serve as the contact point for the PM with the Commission.  We stress that this must not be a supervisory relationship, neither is it one which monitors performance.  On the contrary, it must be more in the form of a mentoring arrangement and a gateway to OKACOM for the PM.  It is primarily for the PM’s benefit and it is expected that the initiative for most contact will lie with the PM.

4.3.4	Project performance monitoring

According to GEF guidance, “All projects will include a concrete and fully budgeted monitoring and evaluation plan” and the ProDoc does provide a schedule of various meetings and reports.  It also recognizes the need for a monitoring and evaluation plan which will include critical indicators.  These indicators are expected to track the short and long-term impacts of this and other related projects in the Basin and are expected to include process (e.g. policy, legal, institutional and other reforms), stress reduction (e.g. reduced pollutant loads or per capita water demands, etc), and environmental status (e.g. cleaner waters, restored habitats, etc).  The ProDoc also identifies the “updated TDA that will be created by the end of year two of the project” as a particularly useful indicator mechanism.

No indicators are provided to measure the outcomes or the long-term impact of the project.  On the other hand, indicators have been identified for the overall objectives, purpose and outputs In the LogFrame Matrix.  However, there are no process indicators and this should be rectified during the preparation of the Annual Work Plans when the activities will be more accurately defined.  At that stage the responsibility for carrying out the activities should also be specified.

The indicators used, refer only to the end of the project and it is necessary to specify in addition the values at other milestones, such as at the beginning (the baseline) and the mid-term of the project. This is particularly necessary since the formulation makes provision for a mid-term evaluation as well as a terminal evaluation. Once again, this could be done during the preparation of the Annual Work Plans.  It would also help for the purposes of monitoring and evaluation to include the beneficiaries in the LogFrame Matrix.

Even though the output and input budgets provided are acceptable, monitoring and evaluation would be greatly facilitated if the input budgets are related to the output budgets.  This is to enable the PSC to assess any departures from the budgeted inputs for delivering the outputs.  This should be addressed during the preparation of the Annual Work Plans and budgets.  The present system of financial reporting will need to be adjusted to accommodate this.

The evaluation team was advised that the PMU had started to follow the LogFrame Matrix according to its defined objectives, outcomes and respective indicators for the formulation of the Annual Work Plan and budget with the participation of all project professional staff.  However, the ProDoc was of somewhat limited usefulness for project implementation and performance monitoring mainly because by the time the project got going, it was rather dated (it had been developed some 3-5 years earlier).  Some adjustments to the outputs/activities and indicators were made and these were reflected in the PIR-2005.  However, if the project is restarted, a more thorough review of the LogFrame Matrix is required at the outset to reflect changed circumstances.  It is also essential that an effective monitoring plan is developed and to obtain stakeholders’ commitment to the confirmed/revised targets and indicators through a fresh project inception workshop with the active participation of national/regional key stakeholders.

Finally, a very effective monitoring mechanism is the regular reporting by the PM to the PSC.  This did take place in this project as evidenced by the record of the PSC meetings.

4.3.5	Conclusions on project management

While the evaluation team accepts the fact that the PMU will remain in Luanda, there needs to be a clear understanding by all stakeholders that the professional independence of the PM and the PMU is not to be questioned except through the PSC – the PM and PMU must be independent of any one government in the execution of their duties.

While the new PM is to be appointed according to transparent UN procedures, the process must recognize the ProDoc commitment to provide a role for the PSC in the appointment process.  This is best achieved if the Panel is to comprise one representative from each government, one from UNDP and one from FAO.  However, it is also imperative that the decision of the panel must be final and all key stakeholders must undertake that they will support the appointee to their fullest possible extent.  The appointment of a good PM is seen by virtually all those spoken to by the team as the most crucial element in the success or failure of the project.

If the project is restarted, the new PM should lead efforts to review the LogFrame (including its milestones and indicators), formulate an effective monitoring plan and put in place a robust monitoring mechanism for the project, building on the indicators used in the PIR-2005.  The results of monitoring should be published on the project’s website or other recognized website as part of a serious outreach effort.  In the interest of accountability, the results of monitoring should include financial statements together with an indication of who will be acting in response to the results.

4.4	State of the budget and financial viability

This is not a financial audit of the project and the procedures used for disbursements and the financial control systems have already been discussed above under Section 4.2.  This section examines the state of the budget and draws conclusions on the financial viability of the project, should it be restarted.

The ProDoc provides a helpful tabulated summary of the calculated cost of each Output and the source of funding in each case.  This table is reproduced below :

Table 1.	Project Financing by Outputs (in US$) (from ProDoc)

| Project Components/Outputs | TOTAL | Co-financing | GEF |
| --- | --- | --- | --- |
| Component A: Joint Management |  |  |  |
| Output A1: Expertise | 731,700 | 35,000 | 696,700 |
| Output A2: Stakeholder Participation | 934,850 | 100,000 | 834,850 |
| Output A3: Policy initiatives | 360,800 | 315,000 | 45,800 |
| Output A4: Monitoring and Evaluation | 161,675 | 0 | 161,675 |
| Total: A. | 2,189,025 | 450,000 | 1,739,025 |
| Component B: Completed TDA |  |  |  |
| Output B1: Basin water resource analysis | 1,966,820 | 1,426,000 | 540,820 |
| Output B2: Socio-economic analysis | 720,200 | 200,000 | 520,200 |
| Output B3: Super-imposed frameworks | 94,069 | 0 | 94,069 |
| Output B4: Environmental assets | 117,630 | 0 | 117,630 |
| Output B5: Alternatives | 500,576 | 0 | 500,576 |
| Output B6: Water management models | 127,450 | 0 | 127,450 |
| Output B7: Criteria | 90,140 | 0 | 90,140 |
| Total B. | 3,616,885 | 1,626,000 | 1,990,885 |
| Component C: SAP Formulation |  |  |  |
| Output C1: Technical & policy implications of options | 111,660 | 0 | 111,660 |
| Output C2: Joint management plan negotiated | 417,040 | 0 | 417,040 |
| Output C3: Commitments defined | 137,190 | 0 | 137,190 |
| Output C4: SAP document produced | 245,210 | 0 | 245,210 |
| Output C5: SAP finance mobilised | 259,900 | 0 | 259,900 |
| Total C. | 1,171,000 | 0 | 1,171,000 |
| Project Support Services | 490,091 |  | 490,091 |
| TOTALS | 7,467,000 | 2,076,000 | 5,391,000 |
| PDF (Block A and B) | 374,000 |  | 374,000 |
| Total Project Financing | 7,841,000 |  | 5,765,000 |

From this table it can be seen that the project was depending almost completely on co-funding for Output A3 - Policy Initiatives and Output B1 - Basin Water Resource Analysis.  Less so, but still significant is its dependence on co-funding for Output B2 – Socio-economic Analysis.  The team was advised that these co-financing figures were rough estimates at the time the ProDoc was finalized, which was 3-5 years prior to project initiation.  By the time the project started, the situation was completely different and the co-financing figures no longer applied.  The main co-financing source during the first year of project operation was the USAID-funded IRBM Project and the main activity conducted on a shared expense basis between EPSMO and IRBM was the rehabilitation of hydrometric stations in the Angolan part of the Basin.

The evaluation team was advised that the establishment and running costs of the PMU and its personnel and overall project expenses, had been distributed proportionally across all outputs in the original budget.  This is not considered adequately transparent.

The PM proposed a revision of the budget at the Inception Report stage (April 2005) “in the light of current needs, realities and time frames and on the basis of the revised work plan”.  While the total amount from GEF remained the same, some significant switches among the Components and particular Outputs were proposed and these can be followed in Table 2 below.  At the component level, Component A is increased significantly and so is Component B but to a lesser extent.  But this is done at the expense of Component C which has been halved.

The costs of the PMU and “central” project personnel were now lumped together under Output A1: Expertise, and this, which in the opinion of the evaluation team is no more transparent than before, has led to the more than 100% increase in this item.  Other salient changes are the increases for Output A3 : Policy Initiatives, and Output B1: Basin Water Resource Analysis (which have been more than doubled), and the drastic decreases in Output A4: Monitoring and Evaluation, and in all but one of the Outputs under Component C: SAP Formulation.

However, this outputs-based budget revision was not implemented.  Instead, FAO effected an adjustment to the budget according to the inputs-based Oracle system and this was presented to the PSC meeting in November 2005.  In his report to the meeting the Project Manager explained the reasons for re-allocations between budget categories and these were :  major reductions in allocations to ‘travel’ (mainly consultants), ‘consultants’ (fees), and ‘non-expendable equipment’ resulted from more realistic assumptions about travel costs and consultancy requirements, as well as price reductions in or improved co-funding prospects for different types of equipment, respectively;  major increases in allocations to ‘contracts’, ‘professional salaries’, ‘technical support services’, ‘general operating expenses’, and ‘training’, in turn, were motivated by more informed assumptions about the need for contracts, salaries, support services, operating expenses and training requirements.  These budget revisions could be considered as examples of adaptive management.

The latest budgetary information available to the evaluation team was provided by the FAO Budget Holder in a series of Inputs-based tables in the Oracle format.  Subsequently, a table was provided showing budget changes and estimated remaining funds by Output.  This was requested specifically by the team because we found the inputs-based budget statement as unhelpful for project analysis and planning purposes.  FAO has advised the team that it is ready to implement output-based financial reporting if this is what is required.

The tables provided by FAO are carried in Annex 6, and the information from the Outputs-based table has been entered in the following table which traces the changes in the budget for the GEF contribution, per Output, and finishes with an indication of the remaining funds as on 15 October 2006.

Table 2.	Changes in the GEF component of the project budget and remaining funds

| PROJECT COMPONENTS/OUTPUTS | ORIGINAL (as in ProDoc) | PROPOSED REVISION (as in Inception Report) | APPROVED BUDGET REVISION “B” | SPENT (as on 15 October) | REMAINING FUNDS (as on 15 October) |
| --- | --- | --- | --- | --- | --- |
| Component A: Joint Management |  |  |  |  |  |
| Output A1: Expertise | 696,700 | 1,309,043 | 1,875,898 | 789,000 | 1,086,898 |
| Output A2: Stakeholder Participation | 834,850 | 577,322 | 386,050 | 0 | 386,050 |
| Output A3: Policy initiatives | 45,800 | 160,142 | 291,571 | 0 | 291,571 |
| Output A4: Monitoring and Evaluation | 161,675 | 47,572 | 90,583 | 48,000 | 42,583 |
| Total A | 1,739,025 | 2,094,079 | 2,644,102 | 837,000 | 1,807,102 |
| Component B: Completed TDA |  |  |  |  |  |
| Output B1: Basin water resource analysis | 540,820 | 1,138,390 | 603,428 | 130,000 | 473,428 |
| Output B2: Socio-economic analysis | 520,200 | 437,070 | 464,418 | 0 | 464,418 |
| Output B3: Super-imposed frameworks | 94,069 | 103,071 | 103,000 | 59,000 | 44,000 |
| Output B4: Environmental assets | 117,630 | 95,142 | 125,000 | 0 | 125,000 |
| Output B5: Alternatives | 500,576 | 172,874 | 116,267 | 0 | 116,367 |
| Output B6: Water management models | 127,450 | 95,335 | 116,367 | 0 | 116,367 |
| Output B7: Criteria | 90,140 | 174,599 | 44,100 | 0 | 44,100 |
| Total B | 1,990,885 | 2,216,481 | 1,572,680 | 189,000 | 1,383,680 |
| Component C: SAP Formulation |  |  |  |  |  |
| Output C1: Technical & policy implications of options | 111,660 | 161,018 | 217,128 | 0 | 217,128 |
| Output C2: Joint management plan negotiated | 417,040 | 214,032 | 214,000 | 0 | 214,000 |
| Output C3: Commitments defined | 137,190 | 83,000 | 83,000 | 0 | 83,000 |
| Output C4: SAP document produced | 245,210 | 59,300 | 24,000 | 0 | 24,000 |
| Output C5: SAP finance mobilised | 259,900 | 73,000 | 146,000 | 0 | 146,000 |
| Total C | 1,171,000 | 590,350 | 684,128 | 0 | 684,128 |
| Project Support Services | 490,091 | 490,091 | 490,090 | 98,478 | 391,612 |
| OVERALL TOTALS | 5,391,000 | 5,391,001 | 5,391,000 | 1,124,478 | 4,266,522 |

As can be seen from above, Budget Revision “B” continued the trend set in the Inception Report by increasing the budget for Component A even further.  However, the budget for Component B has been pared back and is now less than the original budget.  Component C has been increased slightly but it is still almost half of what the ProDoc had allocated in the original budget.

The table also shows that the only significant expenditure has been for Output A1, presumably for salaries and other PMU expenses; and for Output B1 for the EPSMO share of the hydromet stations rehabilitation.

As on 15 October 2006, 31% of the budget for Component A had been spent, 12% of the budget for Component B had also been spent, but there has been no expenditure for Component C (as expected).  Component A expenditure reflects the duration of the project to date (approximately one year which is one third of the scheduled project duration).  If the project is restarted, the remaining budget for Component A is going to last for about two years.  However, from the lessons learnt to date, this may not be sufficient time to complete all project activities, and while the team is confident that sufficient funds remain overall to complete the project, the team does not support the continuing erosion of the budgets for Components B and C to cover the escalating costs of project management and administration unless it can be fully justified to the PSC.  An effective way of overcoming this potential constraint is to negotiate with sister/parallel projects in the Basin to collaborate on some activities which they have in common with EPSMO, and this is discussed further in the following section.  This should lead to savings on some activities and the funds could be deployed elsewhere within the budget.

4.5	Coordination with other initiatives

The relative vacuum created by the slow progress made by the EPSMO project, and the perceived need for early action on Okavango Basin conservation and management issues, motivated some national, regional and international stakeholders, with the support of donor agencies like SIDA, USAID and the EU, to initiate various projects in the Okavango Basin.  Of these, the two which have had the closest working relationship with the project are :

- Okavango Improved River Basin Management Project (IRBM), funded by USAID, US$5-6 million over 4 years (2004-2008).

- “Every River Has its People” (ERP)–Okavango, funded by SIDA, Phase 2, $2 million US over 3 years (2004–2006)

Both the above projects are considered as parallel projects and some of their activities have been considered as co-funding for the purpose of the EPSMO project.   While no formal agreement for collaboration was finalized, the three projects had agreed in principle to coordinate their efforts at a meeting in Johannesburg in February 2005.  A significant output from that meeting was a list of indicative follow-up actions which the three partners agreed each would carry out.  On the part of the EPSMO project, the commitment included :

- Confirm and document an institutional diagram for OKACOM and OBSC with functions and procedures for approvals and reporting.  Describe the roles and responsibilities, institutional arrangements and linkages for OKACOM and OBSC.  Describe relationships to riparian governments and projects.

- Revise project/activities matrix by Feb 28 and share with participants.

- Share responsibility for aerial survey.

- Take lead on:

  - Overall communication strategy (consultant to be hired)

  - Email distribution list for project coordination

  - Focal point for Luanda

  - Repatriation of data to Angola (e.g. water info from Portugal)

  - Environmental implications of HIV/AIDS

  - Biophysical indicators

  - Ecologically sensitive areas studies (IRBM will support)

If the project is restarted, it will need to reopen the productive dialogue with both these other initiatives, update its commitment and collaborate effectively for mutual benefit.

While the above are the projects with which the EPSMO Project should rekindle the most direct collaboration if restarted, there are other projects with whom collaboration may lead to mutual benefits.  These include a number of GEF projects (e.g. Namibia Protected Areas, Botswana  Biodiversity, Angola NBSAP); some in which FAO is involved (e.g. AfDB food security in Angola, National Irrigation Policy & Strategy in Botswana, Review of the Green Scheme in Namibia); and others such as the Okavango Delta Management Plan Project in Botswana.

The distinguishing feature of the EPSMO project has been described as its creation of the holistic Basin-wide context within which other initiatives in the Basin can nest.  However, it cannot, and must not, do this in isolation and collaboration with other relevant initiatives in the Basin is an essential element in its implementation approach.  This is best achieved with the assistance of the OKACOM Secretariat which might be moving from its administrative phase to a more technical second phase during the remaining life of the EPSMO project.

4.6	Lessons learnt

There are a number of lessons that can be drawn from the negative experience of the project to date.  In view of the project’s circumstances, these are not the usual lessons dealing with stakeholder engagement, application of adaptive management strategies, efforts to secure sustainability, knowledge transfer, and the role of M&E in project implementation.   Instead they arise out of roles and responsibilities, processes and procedures, and governance structures.  While most of these are applicable primarily to this project, some may be of broader value.

- The strong expressions of ownership on the part of in-country organizations and individuals need to be actively harnessed and channelled towards the success of the project.  If not, they will become a barrier to project success.

- If misunderstandings are not cleared up as soon as they are noted and agreement obtained, things can escalate and problems become insurmountable.

- The time that it often takes to get a GEF project operational is lengthy and in this case it led to the loss of momentum.  Maybe there needs to be a time beyond which a project’s approval lapses unless it becomes operational.

- A project that has had repeated delays such that its Project Document becomes stale and out of date by the time it starts, can face serious barriers getting off the ground.

- If a project that is fully justified by the need that has been identified falters, others often arise to fill the gap, and the original project needs to ensure that the original justifications are still there before it gets started again.

- Loose terminology can create problems especially if translations into other languages are involved.  For example, the difference between lead country and host country; and the use of CTA (Chief Technical Advisor) when what is meant is in fact Project Manager.

5	FINDINGS : RESULTS AND IMPACTS

5.1	Progress to date

The project commenced operations in November 2004 with the arrival of the Project Manager in Luanda.  As has been mentioned repeatedly elsewhere in this report, this project has achieved little tangible progress.  In an effort to obtain the most up-to-date record of the results achieved to date, the evaluation team examined critical documents such as the minutes of the second PSC meeting in November 2005 and the latest PIR of April 2006; and requested a report on progress from the a.i. Project Manager in the PMU.

According to the report of the Project Manager to the November 2005 PSC meeting, the following Activities had been undertaken by the project –

Under Output A1

- PMU office space has been identified in Luanda and rented since June 2005;

- PMU support staff (an administrative assistant and a secretary) has been recruited and has initiated work;

- An Angolan Field Office has been identified in Menongue, Kuando Kubango Province and rented since July, to serve as a logistical base for EPSMO field operations in the Angolan part of the ORB;

- A National Project Coordinator (NPC) for Angola has been recruited and has initiated work, thus making the National Coordination Unit (NCU) for Angola operational;

- The NCU for Namibia has been constituted and is operational;

- A TDA/SAP Training Course has been held for GEF EPSMO staff, OBSC members and other ORB stakeholders;  and

- National Inter-Sectoral Committee for Namibia has been established and is operational.

Under Output B1, some progress has been achieved towards:

- the development of a consultant data base;

- the rehabilitation of hydrometric gauging stations in the Angolan part of the ORB;  and

- the development of a GIS system for EPSMO, covering the entire Okavango River Basin (ORB).

As can be seen from the above, by the end of October 2005, when the project had been operational for 12 months, only inception-type of activities and mobilization had been carried out and no substantive results had been achieved.

By about 16 months from its becoming operational (April 2006) when the second PIR was written, the project was rated as Unsatisfactory in terms of its progress towards the Objective and the targeted Outcomes.  The situation had changed little by the time the PMU reported (see Annex 7) on progress to the evaluation team in October 2006.

Many of those spoken to by the evaluation team recounted their experiences in operating regionally and Basin-wide, either at project level or on collaborative initiatives.  All reported that a clear lesson is that the time needed for mobilization, achieving consensus and gaining trust, is grossly underestimated.  The process takes time, a lot of time, and patience is of the essence.  This is especially so with regards to Angola which is only now emerging from a very difficult period and which has a lot of catching up to do before it gains the necessary self-assurance and starts participating as an equal partner in Basin-wide initiatives.  The evaluation team believes that the EPSMO project made the same mistake as other interventions and has paid the price.  Where some other initiatives had the flexibility to revise schedules, review plans and adapt to the circumstances, EPSMO could not.  If the project is restarted, the stakeholders will need to accept that progress will be slow.

5.2	Project impacts and sustainability

This project is nested in GEF Operational Programme #9 – Integrated Land and Water Multiple Focal Area Programme.  The goal of this Operational Programme is to help groups of countries utilize the full range of technical, economic, financial, regulatory, and institutional measures needed to operationalize sustainable development strategies for international waters and their drainage basins.

The first Component of the project aims to achieve strengthened mechanisms for joint management of the Okavango River Basin.  This target fits well within the outcomes expected by OP#9 which include the long-term commitment on the part of governments, IAs, donors, and the GEF to leverage the intended sectoral changes to address the root causes of complex environmental problems.  Because impacts which result in damage to the water resources in one nation often occur upstream in another nation, political commitments on the part of neighbouring countries to work together, establish factual priorities, and decide on joint commitments for action need to be nurtured.  Such collaborative processes will be fostered through the SAP formulation.

The project has created some momentum in this direction through its mobilisation activities, especially in Angola, less so in Namibia and much less in Botswana.  However, it has had no discernible impact to date.

The second Component targets the completed transboundary diagnostic analysis.  This work was started during the PDF’B’ phase and a draft TDA was produced which initiated a consultative process with some basin stakeholders, established the current status of the basin as a whole, identified causes of degradation and imminent threats, and indicated critical gaps in information, policy and institutional arrangements.  According to the ProDoc, the draft TDA will be expanded as gaps in the analysis are filled.

Some progress could be claimed in this direction through the installation of five hydromet stations in the upper catchments which was contributed to by the project.  However, this can hardly be considered an impact or an outcome for the project.

The third Component of the project is the formulation of the Strategic Action Programme which will arise out of the foundation set by the TDA.  Since the TDA has yet to happen, no work has taken place on the SAP as yet.

Sustainability depends on institutional strength and financial commitments and “strengthened multi-country institutional arrangements” are specifically targeted by GEF OP#9.  And, according to the ProDoc, “The TDA will include a thorough review of the competencies and comparative advantages of OKACOM as a basin organisation in preparation for SAP implementation. This analysis of the effectiveness of existing mechanisms and clear recommendations for improvement of both OKACOM and all the related policy, legal and institutional arrangements at national and regional level is an important test of the GEF intervention”.

In the event, a consultancy (or various consultancies) supported by SIDA examined the need and options for an OKACOM Secretariat having recorded OKACOM’s institutional capacities and priority needs.  This obviated the need for EPSMO to review OKACOM and after a decision (in principle) in favour of a Secretariat had been made in Oct 2004, IRBM offered to provide “interim secretariat services” (until such time as a Secretariat would be established, with SIDA core support and some USAID support).  While this is a very important outcome, it cannot be claimed by this project and the sustainability of its products may ultimately depend on the work of other projects.

5.3		Stakeholder involvement in implementation

Stakeholder involvement in project implementation has been patchy.  The evaluation team found that the involvement of key stakeholders has been too little by some (UNDP Country Offices) and too much by others (OKACOM).  As discussed elsewhere, the former is the result of inadequate resources, while the latter arose from a misunderstanding of roles and responsibilities.  The PMU was expected to develop a public participation plan but this did not materialise before project activities were halted and the involvement of communities and the public in project implementation has been non-existent.

The following table summarizes the evaluation team’s views on the extent of stakeholder participation in project implementation to date.

Table 3.	Summary of stakeholder involvement in project implementation

| STAKEHOLDER | RELATIONSHIP | EXTENT OF INVOLVEMENT |
| --- | --- | --- |
| Government of Angola | Owner | Not highly visible, dependent on reporting by OKACOM commissioners and this process is unknown. |
| Government of Botswana | Owner |  |
| Government of Namibia | Owner |  |
| UNDP CO in Luanda | I.A. Principal UNDP office | Not very active. Needs to be more proactive. Should assume UNDP lead but requires allocation of resources to do so. |
| UNDP CO in Gaborone | I.A. UNDP support office | Not very active. Support role requires better communication from Luanda. |
| UNDP CO in Windhoek | I.A. UNDP support office | Somewhat more active. Support role requires better communication from Luanda. |
| UNDP/GEF | Funding source | Very active. Maybe stand back a little in favour of UNDP Country Offices. |
| OKACOM | Prime beneficiaries | Very actively involved, but role misunderstood. High degree of ownership augurs well for project outcomes. |
| OBSC | Technical support | Very active but as intermediaries of OKACOM and at policy level. Need to engage directly with project at technical levels especially for TDA. |
| FAO HQ in Rome | Executing Agency | Very active and good technical support but from a distance. |
| FAO Regional Office in Accra | EA Budget Holder | Very active but weak administrative support system. Limited or no delegation to PM. |
| FAO CO in Luanda | EA support office | Active, but with limited capacity for administrative support. Some resources. |
| FAO CO in Windhoek | EA support office | Not very active, limited capacity and no resources to provide adequate support. |
| FAO CO in Gaborone | EA support office | Not active and no resources whatsoever for support. |
| NGOs | Implementation partners | Not very involved – collaboration necessary when project is underway. |
| Communities | Ultimate beneficiaries | Not involved at all yet. Must be fully involved when project is underway. |
| Technical/research institutions | Partners for data and info | Minimal involvement to date. Must be fully involved when project is underway. |
| Other related projects | Complementary partners | Partly involved to date – need to be engaged again in collaborative arrangements. |

5.4	Conclusions on results

As has been noted throughout this report, progress by the project towards the achievement of its Objective and the three components is unsatisfactory and no long term impacts or outcomes can be claimed as yet.

If the project is restarted, and if the various measures recommended in this report are implemented, there is no reason why the targeted outcomes cannot be achieved.

6	COLLECTED CONCLUSIONS

Conclusions have been drawn throughout this report.  They are gathered here and augmented as necessary to reflect the list of tasks outlined in the Terms of Reference for the evaluation.

6.1	Overall conclusion

If the Governments can demonstrate that there is still the political will to sustain the project and with a clearer understanding and acceptance of the various roles and responsibilities, the restructuring and acceptance of the PSC as the highest body for project governance, the enhancement of support and monitoring by the Implementing Agency, the streamlining of the administrative procedures of the Executing Agency, and the removal of other barriers that have hindered it to date, the evaluation team believes that the project is viable and that if restarted it has a good chance of attaining its objectives successfully.

However, in order for this to happen, these prerequisites must be accepted and implemented by all stakeholders as a rescue package and all elements need to be implemented.  Failure to implement some of the proposed changes or taking more than 4-5 months in deciding to do so, will jeopardise the success of the project.  In this case it will be better for UNDP to abandon the project now rather than wait for it to fail.

6.2	Project design

This is a simple model which has been successfully applied in many other projects and as such, the project design is basically sound and, in principle, the project should be viable.   Even though the project design could have been improved, it was not, per se, responsible for the under achievement.

The original Objectives (or components) of the project are still valid and in spite of the initiatives that have been implemented in the meantime, the GEF project is still relevant since none have created the overarching and holistic context for management from a basin-wide perspective, that the GEF project is targeting in the Strategic Action Programme (SAP).

The only possible design flaw of the project is the three-year timescale.  In the circumstances faced by the project, it seems that this timescale was unrealistic.  In a region such as this, with the disparities that exist, it takes time to build relationships and trust.

6.3	Project Steering Committee

The Project Steering Committee must be recognized and supported by all stakeholders as the highest governance body for the project.  As such, it must have both the authority and the power to set policy for the project and to monitor its performance.  By confirming and accepting that the PSC is the highest body for governance of the project, and that issues and disagreements are brought to the PSC for resolution, the stakeholders will avoid issues becoming personalized, which is what caused the downfall of the project.

The membership of the PSC must include all the key stakeholders, in particular the Governments of Angola, Botswana and Namibia represented by their OKACOM Co-Chairs or as the Governments may decide; UNDP/GEF as the funding source; UNDP as the organization that is accountable for the GEF funds; and FAO which is the organization entrusted with the execution of the project.  The PSC will be co-chaired by the UNDP and OKACOM and will conduct its business by consensus. The Project Manager supported by the Project Budget Holder will be required to attend PSC meetings and inform the PSC.  Other OKACOM Commissioners and OBSC members could also attend to assist with technical and other matters.  Likewise, NCU Coordinators (if available) and representatives from other related projects in the Basin would be welcome to attend and inform the PSC.

6.4	Progress towards attaining the project’s environmental objectives

Progress by the project towards the achievement of its Objective and the three components is unsatisfactory and no long term impacts or outcomes can be claimed as yet.  If the project is restarted, and if the various measures recommended in this report are implemented, there is no reason why the targeted outcomes cannot be achieved.  However, this is subject to the acceptance of the recommendations by all stakeholders.

6.5	Adequacy of remaining funds

On the basis of the financial resources estimated to be remaining according to Outputs, if the project is restarted, the remaining budgets for Components B and C are considered adequate to carry out the proposed activities.  In fact, since some parallel projects have stepped into the breach and carried out some of the activities, it is possible that funds from these two Components could be in excess of requirements.  On the other hand, funds for Component A would be expected to last for  about two years (which was the original duration of the project).

Experience in the Basin indicates that the time allowed for mobilization, achieving consensus and gaining trust, has been grossly underestimated.  Forging relationships and gaining trust takes time, a lot of time, and if the project is restarted, the stakeholders will need to accept that progress will be slow and that project financial resources may become stretched, even for Components B and C.  In this event, a project revision could move funds to where they are most needed although the team does not support the continuing erosion of the budgets for Components B and C to cover the escalating costs of project management and administration unless it can be fully justified to the PSC.  An alternative strategy would be to negotiate cooperation with sister projects in the Basin (see 6.17 below).

6.6	Roles and responsibilities

The role of OKACOM as the originator of the project concept, the role of the Governments as the signatories to the Project Document, the role of the Project Steering Committee as the highest governance body for the project, and the role of the Project Manager as the individual entrusted with the responsibility to obtain the project Outputs and achieve its Objectives, have been misunderstood and confused.  Likewise, there has been a lack of understanding of the procedures and processes employed by the Implementing Agency and the Executing Agency.

Added to all this was the genuine assumption of the responsibility for day-to-day project overseeing by Angola as the lead/host country which was not intended.

These misunderstandings and confusion permeated all aspects of the project to the extent that even something that is not very important in the greater scheme of the project, such as office premises for the PMU, escalated into a major area of contention and disagreement and in turn contributed to further strained relations.

6.7	Use of LogFrame and performance indicators

Since the project had not really taken off, there was not much opportunity to use the LogFrame to good effect and measure up progress against the set indicators.  The PMU had started to follow the LogFrame Matrix according to its defined objectives, outcomes and respective indicators for the formulation of the Annual Work Plan and budget.  However, the ProDoc was of somewhat limited usefulness for project implementation and performance monitoring mainly because by the time the project got going, it was rather dated (it had been developed some 3-5 years earlier).  If the project is restarted, a more thorough review of the LogFrame Matrix will be required at the outset to reflect changed circumstances.  The indicators given in PIR-2005 may be helpful in this respect.  It is also essential that an effective monitoring plan is developed and stakeholders’ commitment to the confirmed/revised targets and indicators needs to be obtained through a fresh project inception workshop with the active participation of national/regional key stakeholders.

6.8	Partnership arrangements

Two projects which had the closest working relationship with the EPSMO project were the Okavango Improved River Basin Management Project (IRBM) funded by USAID, and “Every River Has its People” (ERP) funded by SIDA.  While no formal agreement for collaboration was finalized, the three projects agreed in principle to coordinate their efforts and a list of indicative follow-up actions was drawn up.  If the project is restarted, it will need to reopen the productive dialogue with both these initiatives, update its commitment and collaborate effectively for mutual benefit.  There may even be merit in attempting to blend the three LogFrames of IRBM, ERP and EPSMO.

The distinguishing feature of the EPSMO project has been described as its creation of the holistic Basin-wide context within which other initiatives in the Basin can nest, and this justification is still valid.  However, EPSMO cannot, and must not, do this in isolation and collaboration with these and other relevant initiatives in the Basin is an essential element in its implementation approach.

6.9	Technical and administrative support by UNDP

As implementing agency, UNDP must be more proactive, and in particular the country offices need to be more engaged.  Of these, the Principal Country Office in Angola must assume the lead role in supporting and monitoring the project through the PMU.

UNDP needs to take a more assertive stance in its requirements of FAO in the delivery of its contractual obligations.  It is also necessary to have a formal Memorandum of Understanding between UNDP and FAO.

6.10	Technical and administrative support by FAO

The comparative advantage that FAO was meant to bring to this project is not significant, in that the most unique component is the technical element and this could have been obtained on contract, separately from the administrative element which would have been more efficiently carried out by an organization with support systems attuned to those of UNDP.

FAO procedures for disbursements, recruitment and travel need to change to reflect the needs of a project such as this one, because the alternative is project failure.  In particular, the PM must be given the utmost level of delegation and flexibility and then supported to get on with the job he/she has been engaged to perform.   FAO has indicated that it is prepared to move in these positive directions

With the procedural reforms within FAO currently underway in search of greater efficiency, FAO should use this project as a pilot to test a more devolved, delegated and less controlled system.  Existing procedural constraints could be set aside and a more devolved approach to project management could be adopted with streamlined procedures, higher degree of delegation (with accountability), higher levels of financial discretion, broader powers of recruitment and generally allowing greater flexibility to the Project Manager in a climate of mutual trust.

While the new PM is to be appointed according to transparent UN procedures, the process must recognize the ProDoc commitment to provide a role for the PSC.  This is best achieved if the Panel is to comprise one rep from each government, one from UNDP and one from FAO.  However, it is also imperative that the decision of the panel must be final and all key stakeholders must undertake that they will support the appointee to their fullest possible extent.  The appointment of a good PM is seen by virtually all those spoken to by the team as the most crucial element in the success or failure of the project.

6.11	Level of delivery

The project has under performed and failed to deliver the outputs expected in the one year it operated.  The level of delivery of the project has been unsatisfactory and many influences have contributed to this.  Of these, the most crucial influence has been the weak project governance which, in turn, was brought about by the confusion that existed on the roles and responsibilities of the various stakeholders, and the lack of appreciation of the procedures and processes of the implementing agency and the executing agency.

6.12	Ownership

The evaluation team concludes that the high level of ownership of the project by OKACOM and OBSC (particularly on the Angolan side), together with the positive views of those working on parallel projects in the Basin, augur well for the success of the project if it were to be restarted.  Virtually all those consulted by the team said that the project must continue.  Many, especially those representing community level stakeholders and potential beneficiaries, have great expectations for the project.  The team detected some sadness and anguish that the project got to the point where its activities had to be halted, but we also felt that maybe stakeholders are now prepared to move on.  The team was told that the project “is vitally important” and that “the project must not close – the people of the Okavango Basin need the project”.

6.13	Government involvement and commitment

The three Governments agreed, contractually, to receive GEF funds and to abide by the procedures of the implementing agency, namely UNDP, according to their respective Standard Basic Assistance Agreements (SBAA) with UNDP.  These procedures comprise the legal basis for the project.

Country level involvement in project implementation has been effected almost exclusively by the OKACOM Commissioners and the OBSC members acting upon the mandate given them by their respective Governments and the special relationship that OKACOM has with this project, must be recognized.

While the evaluation team accepts the fact that the PMU will remain in Luanda, there needs to be a clear understanding by all stakeholders that the professional independence of the PM and the PMU is not to be questioned except through the PSC.  The PM and PMU must be independent of any one government in the execution of their duties.

6.14	Stakeholder Participation and benefits accrued

Stakeholder involvement in project implementation has been patchy.  The evaluation team found that the involvement of key stakeholders has been too little by some (UNDP Country Offices) and too much by others (OKACOM).  As discussed elsewhere, the former is the result of inadequate resources, while the latter arose from a misunderstanding of roles and responsibilities.  The PMU was expected to develop a public participation plan but this did not materialise before project activities were halted and the involvement of communities and the public in project implementation has been non-existent.

6.15	Financial Management

The segregation of duties operated by FAO for its disbursement process may have evolved out of a need for strict checks and balances, but it creates a maze of authorities, responsibilities, reviews and approvals and it is no wonder that the system is being reviewed and streamlined.  It was alleged to the evaluation team that the FAO process is too cumbersome for the expeditious implementation of projects.  It is also very rigid and tends to stifle the performance of a Project Manager.  Perhaps if the system had to focus less on procedural minutiae and place more emphasis on the objective of the procedures, projects would be better served, delivery rates would go up and cost-effectiveness would rise.

6.16	Lessons Learnt

There are a number of lessons that can be drawn from the negative experience of the project to date.  In view of the project’s circumstances, these are not the usual lessons dealing with stakeholder engagement, application of adaptive management strategies, efforts to secure sustainability, knowledge transfer, and the role of M&E in project implementation.   Instead they arise out of roles and responsibilities, processes and procedures, and governance structures.  While most of these are applicable primarily to this project, some may be of broader value.

6.17	Project implementation

If the project is restarted, the opportunity should be taken to rephase and rebudget the project, but not necessarily redesign it.   The team also feel that to the extent possible, the focus of the project should be shifted from the capital cities to the Basin which is where the natural resources are and where those that rely on them, live.

The emphasis should be shifted away from the TDA and more to the SAP component.  The TDA must be completed in the shortest possible time and while it must be able to provide a solid foundation for the SAP, if gaps are identified, it is not essential to wait until they are filled.  Gaps can be recorded and the SAP can provide the activities that will fill the gaps at the operational phase.

The work on the SAP should focus on the national level in the first instance and if it appears that the project will run out of time and/or financial resources to complete the Basin-wide SAP, the task can be shared with the OKACOM Secretariat following appropriate negotiations.  The OKACOM Secretariat could provide logistical coordination and administrative support while OBSC will provide the necessary technical input to consolidate the final Basin-wide SAP.  This will also be a good opportunity to involve fully the three staff, one from each country who, we understand, will be seconded to the Secretariat according to the procedures to be adopted by OKACOM for the Secretariat.

7	RECOMMENDATIONS : WHERE TO FROM HERE?

7.1	Removal of obstacles hindering project success

7.1.1	Project Ownership and Governance

For the purpose of clarifying project ownership and ensuring strong and effective governance …

We recommend to UNDP that, in consultation with the three Governments, it should restructure the Project Steering Committee to signal its position as the highest governance body for the project with the following characteristics :

- Members to comprise – a representative of each of the three Governments namely, their OKACOM Co-Chairs or whoever the Governments decide, a representative of UNDP/GEF, a representative of the UNDP Country Offices and a representative of FAO at Headquarters level.  The UNDP Principal Resident Representative is to co-chair meetings with the relevant OKACOM Commissioner on rotation.

- The Project Manager will be required to attend and present a report on progress and respond to policy directives and guidance issued previously.

- The FAO Budget Holder will be required to attend to assist the Project Manager and present a financial report.

- Other OKACOM commissioners and members of OBSC will participate as available and provide technical and other advice.

- The Terms of Reference of the PSC should be redrawn by UNDP along the lines suggested in Annex 5 and should be endorsed formally by all members.

- The PSC should meet at least every 6 months, more frequently if necessary, in each of the countries on rotation, if possible in one of the towns or main settlements in the Okavango Basin.

- Meetings are to be hosted by the relevant Ministry as part of the Government in-kind contribution.

7.1.2	Project Administration and Execution

In order to overcome the administrative and execution barriers that have plagued the project …

7.1.2.1	We recommend to UNDP and FAO that they should reach agreement on the format to be used for financial reporting and that this should be acceptable to the PSC;  that the quarterly and annual financial monitoring system should be able to provide information about both the outputs-based and the inputs-based budgets; and that this be one of the items in a formal MoU to be signed between UNDP and FAO.

7.1.2.2	We recommend to FAO that technical support should be retained in Rome and that arrangements must be made for scheduled, regular visits by the Technical Advisor to the PMU and each of the NCUs.

7.1.2.3	We recommend to FAO that the existing ability of the Project Manager to approve travel without formal Travel Authorization if travelling within Angola, should be extended to encompass all travel to and from each of the three countries and including Johannesburg.

7.1.2.4	We recommend to FAO that the Budget Holder should be co-located with the technical support unit in Rome.  However, regardless of where the Budget Holder is located, he/she should use his/her authority of delegation to enable the PM to have the maximum authority and the greatest freedom to manage project resources, based on the approved Annual Work Plan and Budget.  Under this arrangement, funds would be transferred to the FAO Luanda Office, the PM would authorize disbursements, and the FAO Luanda Office will make the disbursement in accordance with the FAO’s rules and procedures.  Funds would be replenished when the PM has accounted for what had earlier been released to him/her.

7.1.2.5	We recommend to FAO that in recognition of its ongoing procedural reforms in search of greater efficiency, it considers the administration and execution of this project as a pilot which can then be evaluated before being emulated throughout the system.  Under such an approach, existing procedural constraints can be set aside to allow a higher degree of delegation (with accountability), higher levels of financial discretion, broader powers of recruitment and generally allowing greater flexibility to the Project Manager in a climate of mutual trust.

7.1.2.6	We recommend to UNDP COs that they must take a more proactive role in this and other GEF projects with their Environment Units adequately resourced and empowered to backstop, monitor and support projects.  This is absolutely essential in respect of the UNDP Angola Country Office which is the Principal UNDP Office for the project.

7.1.2.7	We recommend to the UNDP Angola Country Office that it undertake to assist the new PM with diplomatic support in his/her relationship with the Governments of the three countries.

7.1.3	Project Management

On the issue of project hosting, office location, PM responsibilities and recruitment …

7.1.3.1	We recommend to UNDP, FAO and the Government of Angola as host government, that the Project Management Unit be retained in Luanda and that the current premises for the PMU should be retained.  If for any reason (such as landlord’s requirements) the PMU needs to relocate, consideration should be given to locating it in Lubango or Huambo with the latter being in the Okavango Basin and neither of which is understood to be as difficult as Luanda.

7.1.3.2	We recommend to the Project Manager to use every opportunity to shift the centre of gravity of the project to the Basin, by basing the NCUs in Menongue, Rundu and Maun, and by providing more equitable support through project funds to Namibia and Botswana to cover the actual expenses of their NCUs.

7.1.3.3	We recommend to UNDP and FAO that the ToRs of the Project Manager should be revised to identify clearly to whom he/she is responsible, to whom he/she reports, and to whom he/she is accountable, and that the concurrence of the PSC should be sought on the new ToRs

7.1.3.4	We recommend to UNDP, FAO and the three Governments that the recruitment of a new Project Manager should be according to the UN rules and procedures, should start with an international search, the process should be expedited to the extent possible, interviews should be held in Johannesburg or Rome, the interviewing panel should comprise a representative each of the three Governments, UNDP and FAO, and the decision of the panel will be final.

7.1.3.5	We recommend to UNDP, FAO and the three Governments that in screening candidates for the position of PM, the qualities to be looked for are : leadership and proven track record in managing people and resources;  interpersonal, negotiating and diplomatic skills;  sensitivity to the socio-cultural and socio-economic differences among the countries;  and the ability to inspire confidence and trust.  These qualities are to be given precedence over technical qualifications.

7.2	Project Implementation

7.2.1	Project Viability

7.2.1.1	We recommend to all stakeholders that in order for the project to be viable, these recommendations need to be accepted by all and implemented fully, as a package.  If any of the salient recommendations are not accepted by all stakeholders, the viability of the project may be placed in jeopardy.

7.2.1.2	We recommend to UNDP that unless decisions on the recommendations are made by the end of January 2007, and unless there is a clear indication that a new Project Manager will be in place by the end of April 2007, the project should be abandoned.

7.2.1.3	We recommend to UNDP that if the project is restarted, a thorough review (not necessarily independent, but more thorough than the PIR, and involving stakeholders and beneficiaries), should be conducted after six months to assess the extent to which the project has overcome previous obstacles and made progress towards its targets.

7.2.2	Project design

To ensure that the project benefits from the results achieved by other initiatives in the Basin and to strengthen the project design …

7.2.2.1	We recommend to the Project Manager, under the guidance of the PSC, that the project scope should be reviewed and changed/confirmed in view of the work of other projects;  that meaningful collaboration with these other projects should be established since some of their results can be considered as co-funded activities;  and that their representatives should be invited as observers to the PSC meetings.

7.2.2.2	We recommend to the Project Manager that he/she reviews the LogFrame Matrix for approval by the PSC, that the review should take into account changed circumstances and it should extend to confirmed/revised targets and indicators.  The review should lead to an effective monitoring plan which should be adopted through a fresh project inception workshop with the active participation of national/regional key stakeholders.

7.2.2.3	We recommend to the Project Manager that the PMU should retain lead responsibility for Component A and a coordinating role for each of Component B and Component C with the coordination being provided through the services of one or more expert consultants.

7.2.2.4	We recommend to the Project Manager that a Public Information and Participation Plan/Strategy should be formulated as soon as possible for approval by the PSC and that in addition to the meaningful provision of opportunities for participation by communities and the public in the project implementation, the Plan/Strategy should also provide for outreach, communication and knowledge management.

7.2.2.5	We recommend to GEF and UNDP that in order to clarify objectives, constraints, procedures and processes of the GEF for all stakeholders, a regional GEF workshop/seminar be organized, to which all key stakeholders of this project as well as participants from other GEF projects in the region will be invited to participate.

7.2.3	Component ‘A’ : Mechanisms for Joint Management

As a mechanism for joint management …

7.2.3.1	We recommend to the Project Manager that as a follow-up to the recommendation above on project design, the PMU assume lead responsibility for the active implementation of this Component, led by the PM himself/herself.

7.2.3.2	We recommend to the Project Manager and the PSC that if the project is restarted there should be a start-up workshop organized by UNDP with the participation of the members of the PSC, PMU, NCUs, OKACOM, OBSC, and partner NGOs. This is to explain what the project is about, how it is organized and governed, and what the roles and responsibilities are of the various stakeholders and actors.

7.2.3.3	We recommend to the Project Manager and the Government of Botswana that as soon as feasible after the restarting of the project, all efforts are taken to appoint a National Project Coordinator for Botswana to head the Botswana NCU along the same lines as in as Angola and Namibia.

7.2.3.4	We recommend to the Governments of Angola, Botswana and Namibia that in the National Intersectoral Committees (NISC), which have already been established in Angola and Namibia, there should be representatives of the relevant line Ministries with an interest in the Basin as well as the Ministry of Foreign Affairs and the Attorney General’s Office in recognition of the international and legal nature of the subject.

7.2.3.5	We recommend to the Project Manager to take cognizance of the work carried out by ERP/SIDA and IRBM/USAID  :

- To establish the Basin-wide forum through the Association for Environment Conservation and Rural Development (ACADIR) in Angola, the Kalahari Conservation Society (KCS) in Botswana and the Namibia Nature Foundation (NNF) in Namibia;

- To set up, support, house and fund the OKACOM Interim Secretariat;

- To review the mandate and functions of OKACOM and its organs.

and report to the PSC on how this work has influenced EPSMO activities.

7.2.4	Component ‘B’ : Transboundary Diagnostic Analysis (TDA)

For the early completion of the TDA …

7.2.4.1	We recommend to the PSC and the Project Manager that this Component should be entrusted to the extent possible to the NCUs with the full collaboration of the OBSC, to compile the TDA at national level.  Following this, the PMU should appoint an expert consultant to work with the OBSC to blend the national TDA elements into a truly Basin-wide TDA.  We recommend that in view of the need to accommodate seasonal elements, the investigation should commence as soon as possible and be carried out over a 12-month period, but no more.

7.2.4.2	We recommend to the Project Manager that the regional group/s of experts especially for climate, hydrology and water resources, socio-economic development, and land cover/land use should be established immediately with nominations from the three countries.  The climate, hydrology and water resources group should include experts from the meteorological services and those responsible for ground water, water quality and sediment transport.

7.2.4.3	We recommend to the Project Manager, the NCUs and the OBSC that in the compilation of the TDA (both national elements and Basin-wide) it is not essential to fill all the gaps in data and information;  it is sufficient to note and highlight any occurring gaps in knowledge and signal them to be rectified as part of the SAP implementation.

7.2.4.4	We recommend to the NCUs and the OBSC that in compiling the national and Basin-wide TDAs, use should be made of simpler methodologies, for example for water resources availability analysis.  Use should also be made of new data which have become available since the draft TDA was completed, for example, through the work of the Harry Oppenheimer Okavango Research Centre, the Okavango Delta Management Plan Project, the various hydrological models which have been developed, etc.  In addition, use should be made of the institutional models for managing international shared river basins available in the Toolbox for Integrated Water Resources Management of the Global Water Partnership.

7.2.5	Component ‘C’ : Strategic Action Programme (SAP)

In order not to delay the formulation of the SAP …

7.2.5.1	We recommend to the PSC and the Project Manager that work on the formulation of the SAP under this Component should be entrusted initially to national working groups established for the purpose to approach the task from a national perspective in the first instance with the assistance of an expert consultant engaged by the PMU.  The national-level outcomes are then to be coordinated and facilitated by the OKACOM Interim Secretariat with the assistance of consultant expertise to blend them into a Basin-wide SAP.  The work can start immediately with some of the recommendations from the preliminary TDA.

7.2.5.2	We recommend to UNDP/GEF and OKACOM that if it appears that the project will run out of time and/or financial resources to complete the Basin-wide SAP, negotiations be entered into with the SIDA Project to enable the task to be shared with the OKACOM Secretariat.

ANNEX 1		EVALUATION TERMS OF REFERENCE

Terms of Reference

Project Independent Interim Evaluation

Project: Environmental Protection and Sustainable Management

of the Okavango River Basin

RAF/00/G33/A/1G/12

1. Introduction:

1.A: 	Standard UNDP-GEF Monitoring and Evaluation Requirements

The Monitoring and Evaluation (M&E) policy applied by UNDP-GEF at the project level has four objectives: i) to monitor and evaluate results and impacts; ii) to provide a basis for decision making; iii) to promote accountability for resource use; and iv) to document, provide feedback on, and disseminate lessons learned. Independent interim evaluations are commissioned to examine progress in achieving project objectives and make recommendations as to how to improve project performance.

1.B.	Background/Rationale for Project

The Okavango River Basin (ORB) remains one of the least human impacted basins on the African continent. Mounting socio-economic pressures on the basin in the riparian countries, Angola, Botswana and Namibia, threaten to change its present character.  It is anticipated that in the long term this may result in irretrievable environmental breakdown and consequent loss of domestic and global benefits. Maintaining these benefits requires agreement over the sharing of both the benefits and associated liabilities (to include those of an environmental nature) through joint management of the basin’s water resources. The 1994 Permanent Okavango River Basin Commission (OKACOM) Agreement, 1995 SADC Protocol on Shared Watercourse Systems and the 1997 UN Convention on the law of the non-navigational uses of international watercourses provides a framework for such management. Under the OKACOM Agreement, the riparian countries are working toward the implementation of an Integrated Management Plan (IMP) for the basin on the basis of an Environmental Assessment (EA).

The project objective is to alleviate imminent and long-term threats to the linked land and water systems of the ORB through the joint management of the ORB water resources and the protection of its linked aquatic ecosystems, comprising all wetlands, fluvial and lacustrine systems, and their biological diversity. A two-stage approach has been adopted.  Stage 1, the subject of this intervention, will involve the preparation of the Strategic Action Program (SAP).  Stage 2, the subject of a subsequent intervention, will involve implementation of the SAP.

The Project is executed by the Food and Agriculture Organization of the United Nations (FAO). The Project Management Unit is located in Luanda, hosted by the Angolan Ministry of Energy and Water.

There is a need to assess progress towards meeting the planned outcomes of the project. A number of new projects have also been initiated in the area, with funding, inter alia from USAID and SIDA.  The scope and activities of the project, as well as governance and administrative arrangements need to be reviewed to ensure that the planned objectives can be realised both timeously and cost effectively.

2.	Objective of the Evaluation

The Evaluation has been commissioned by UNDP and will be conducted according to guidance, rules and procedures for such evaluations established by UNDP and the Global Environment Facility. The overall objective of the Independent Interim Evaluation is to review the achievements made by the project after one year of operation, examine delivery and recommend measures to enhance performance. It will establish the relevance of the project in light of the initiation of other activities, the level of commitment to outcomes by all parties, and the performance of the project’s governance arrangements. The evaluation team should identify specific lessons pertaining to the strategies employed and implementation arrangements, which will be of relevance to similar International Waters projects.

3.	Scope of the Evaluation

The Evaluation will assess the project’s achievements according to the following Project Review criteria (an explanation of the terminology employed is provided in annex 2):

- Outcomes

- Assess progress towards attaining the project’s environmental objectives and accrual of environmental benefits at all levels – global, regional and national.  This should include the extent to which the project contributed to: (a) strengthened mechanisms for the joint management of the Okavango River Basin (ORB); (b) a completed transboundary analysis; and (c) a formulated SAP.

- Establish whether the project outcomes, agreed by the GEF Council can be attained with the remaining funds.

- Implementation approach

- Review the clarity of roles and responsibilities of the various individuals, agencies and institutions and the level of coordination between relevant players.

- Assess the level to which the Logical Framework Approach (LFA) and performance indicators were used as project management tools.

- Evaluate any partnership arrangements established for implementation of the project with relevant stakeholders involved in the country/region.

- Describe and assess efforts of UNDP and FAO in support of the implementing agencies and national institutions, notably in terms of technical and administrative backstopping.

- Based on a thorough examination of the level of delivery and reasons behind this, make recommendations with regard to the project objectives, project performance, and solving of existent differences.

- Country Ownership/drivenness

- Assess the extent to which country representatives (including governmental officials, civil society, etc.) were actively involved in project implementation.

- Assess whether the Governments of Angola, Botswana and Namibia have maintained technical and financial commitment to the project

- Stakeholder Participation and benefits accrued

- Assess the level of public involvement in the project and comment as to whether the scope of public involvement has been appropriate given the broader goals and objectives of the project.

- Review and evaluate the extent to which project benefits have reached the intended beneficiaries.

- Financial Management

- Assess the financial control systems, including reporting and planning, that allowed the project management to make informed decisions regarding the budget.

- Assess the extent to which the flow of funds had been proper and timely both from UNDP and from the Project Management Unit to the field.

- Evaluate the extent of due diligence in the management of funds and financial audits.

- Cost effectiveness

- Assess the extent to which the project has completed the planned activities and met or exceeded the expected outcomes according to schedule and as cost effective as initially planned.

- Monitoring and Evaluation

- Review the project’s reporting systems and their efficiency.

- Review the implementation of the project’s monitoring and evaluation plans including any adaptation to changing conditions (adaptive management).

- Lessons Learned

- Describe the main lessons that have emerged in terms of: strengthening country ownership/drivenness; strengthening stakeholder participation; application of adaptive management strategies; efforts to secure sustainability; knowledge transfer; and the role of M&E in project implementation.  In describing all lessons learned, an explicit distinction needs to be made between those lessons applicable only to this project, and lessons that may be of value more broadly.

4.  	Products Expected from the Evaluation

The Evaluation team will present a final report to UNDP, GEF, FAO and the concerned Governments following the format appended as Annex 1. The Report will include an Executive Summary summarising the main findings, lessons and recommendations.  The evaluation will include ratings on the following aspects (1) sustainability, (2) Outcome/ achievement of the objectives, (3) implementation approach.

5.	Evaluation Team

The evaluation will be performed by a two-person team. The team will comprise 2 international consultants, both wholly conversant with the development context of Africa, and International Waters management. One of the consultants will have had previous experience evaluating GEF funded projects, while one will have experience with managing inland water bodies in Africa. The team will have a wide range of skills, including prior evaluation experience, expertise in water management, and related activities, and experience with economic and social development issues.

6.	Methodology

The evaluation team will specify the methods used in compiling the evaluation in the final report. These will include the following:

The Evaluation team will liaise with all key stakeholders, including OKACOM members, Government Ministries at national and district level, NGOs and academic institutions, and civil society representatives. Structured and semi structured interviews will be organised with key stakeholders to collect information.

Introductory and exit briefing meetings will be organised with OKACOM, UNDP and FAO to discuss the evaluation. Copies of the final report will be circulated to Basin States and OKACOM, which will  be afforded an opportunity to provide an opinion on the findings of the report before it is finalised.

The evaluation team will undertake a review of documentation, including the Project Document and technical reports, as listed in section 8. Field visits to the project sites in ORB, to verify information collected at the national level should also be undertaken.

7.	Implementation Arrangements

The evaluation should take about 1 month starting in July 2006. The UNDP Country Office in Angola will assume responsibility for coordinating the in country programme of the evaluation team, including stakeholder meetings and field visits in consultation with the Government. Briefing sessions and bilateral meetings will be organised with UNDP, FAO, OKACOM/ OBSC.

8.	Reference Documents

The Evaluation team will review all relevant background documents, to be supplied by UNDP, FAO and OKACOM, including, amongst others:

- Project Document

- Rules and Procedures of the UN System for Project Execution

- Project Implementation Reviews (PIRs/ APRs)

- Project Plans

- Project Quarterly Reports

- Minutes of OKACOM Meetings, documenting OKACOM Policies

-- Other OKACOM documents as relevant to be made available by the Interim Secretariat

Annex 1: Evaluation Report: Outline

Executive summary

- Brief description of project

- Context and purpose of the evaluation

- Main conclusions, recommendations and lessons learned

Introduction

- Purpose of the evaluation

- Key issues addressed

- Methodology of the evaluation

- Structure of the evaluation

The project(s) and its development context

- Project start and its duration

- Problems that the project seek to address

- Immediate and development objectives of the project

- Main stakeholders

- Results expected

Findings and Conclusions

- Project formulation

- Implementation approach

Country ownership/Driveness

- Stakeholder participation

- Replication approach

- Cost-effectiveness

- Linkages between project and other interventions within the sector

- Indicators

- Management arrangements

- Implementation

- Financial Planning

- Monitoring and evaluation

- Execution and implementation modalities

- Management by the UNDP country office

- Coordination and operational issues

- Results

- Attainment of objectives

- Sustainability

- Contribution to upgrading skills of the national staff

Recommendations

Annex 2.  Explanation on Terminology

Implementation Approach includes an analysis of the project’s logical framework, adaptation to changing conditions (adaptive management), partnerships in implementation arrangements, changes in project design, and overall project management.

Some elements of an effective implementation approach may include:

- The logical framework used during implementation as a management and M&E tool

- Effective partnerships arrangements established for implementation of the project with relevant stakeholders involved in the country/region

- Lessons from other relevant projects (e.g., same focal area) incorporated into project implementation

- Feedback from M&E activities used for adaptive management.

Country Ownership/Driveness is the relevance of the project to national development and environmental agendas, recipient country commitment, and regional and international agreements where applicable.

Some elements of effective country ownership/driveness may include:

- Project Concept has its origin within the national sectoral and development plans

- Outcomes (or potential outcomes) from the project have been incorporated into the national sectoral and development plans

- Relevant country representatives (e.g., governmental official, civil society, etc.) are actively involved in project identification, planning and/or implementation

- The recipient government has maintained financial commitment to the project

- The government has approved policies and/or modified regulatory frameworks in line with the project’s objectives

For projects whose main focus and actors are in the private-sector rather than public-sector (e.g., IFC projects), elements of effective country ownership/driveness that demonstrate the interest and commitment of the local private sector to the project may include:

- The number of companies that participated in the project by: receiving technical assistance, applying for financing, attending dissemination events, adopting environmental standards promoted by the project, etc.

- Amount contributed by participating companies to achieve the environmental benefits promoted by the project, including: equity invested, guarantees provided, co-funding of project activities, in-kind contributions, etc.

- Project’s collaboration with industry associations

### Stakeholder Participation/Public Involvement consist of three related, and often overlapping processes: information dissemination, consultation, and “stakeholder” participation. Stakeholders are the individuals, groups, institutions, or other bodies that have an interest or stake in the outcome of the GEF-financed project. The term also applies to those potentially adversely affected by a project.

Examples of effective public involvement include:

Information dissemination

- Implementation of appropriate outreach/public awareness campaigns

Consultation and stakeholder participation

- Consulting and making use of the skills, experiences and knowledge of NGOs, community and local groups, the private and public sectors, and academic institutions in the design, implementation, and evaluation of project activities

Stakeholder participation

- Project institutional networks well placed within the overall national or community organizational structures, for example, by building on the local decision making structures, incorporating local knowledge, and devolving project management responsibilities to the local organizations or communities as the project approaches closure

- Building partnerships among different project stakeholders

- Fulfillment of commitments to local stakeholders and stakeholders considered to be adequately involved.

Sustainability measures the extent to which benefits continue, within or outside the project domain, from a particular project or program after GEF assistance/external assistance has come to an end.  Relevant factors to improve the sustainability of project outcomes include:

- Development and implementation of a sustainability strategy

- Establishment of the financial and economic instruments and mechanisms to ensure the ongoing flow of benefits once the GEF assistance ends (from the public and private sectors, income generating activities, and market transformations to promote the project’s objectives).

- Development of suitable organizational arrangements by public and/or private sector

- Development of policy and regulatory frameworks that further the project objectives

- Incorporation of environmental and ecological factors affecting future flow of benefits.

- Development of appropriate institutional capacity (systems, structures, staff, expertise, etc.)

- Identification and involvement of champions (i.e. individuals in government and civil society who can promote sustainability of project outcomes)

- Achieving social sustainability, for example, by mainstreaming project activities into the economy or community production activities

- Achieving stakeholders consensus regarding courses of action on project activities.

Replication approach, in the context of GEF projects, is defined as lessons and experiences coming out of the project that are replicated or scaled up in the design and implementation of other projects. Replication can have two aspects, replication proper (lessons and experiences are replicated in different geographic area) or scaling up (lessons and experiences are replicated within the same geographic area but funded by other sources). Examples of replication approaches include:

- Knowledge transfer (i.e., dissemination of lessons through project result documents, training workshops, information exchange, a national and regional forum, etc).

- Expansion of demonstration projects.

- Capacity building and training of individuals, and institutions to expand the project’s achievements in the country or other regions.

- Use of project-trained individuals, institutions or companies to replicate the project’s outcomes in other regions.

Financial Planning includes actual project cost by activity, financial management (including disbursement issues), and co-financing. If a financial audit has been conducted the major findings should be presented in the TE.

Effective financial plans include:

- Strong financial controls, including reporting, and planning that allow the project management to make informed decisions regarding the budget at any time, allows for a proper and timely flow of funds, and for the payment of satisfactory project deliverables

- Due diligence due diligence in the management of funds and financial audits.

Cost-effectiveness assesses the achievement of the environmental and developmental objectives as well as the project’s outputs in relation to the inputs, costs, and implementing time. It also examines the project’s compliance with the application of the incremental cost concept. Cost-effective factors include:

- Compliance with the incremental cost criteria (e.g. GEF funds are used to finance a component of a project that would not have taken place without GEF funding.) and securing co-funding and associated funding.

- The project completed the planned activities and met or exceeded the expected outcomes in terms of achievement of Global Environmental and Development Objectives according to schedule, and as cost-effective as initially planned.

- The project used either a benchmark approach or a comparison approach (did not exceed the costs levels of similar projects in similar contexts). A benchmark approach in climate change and ozone projects measures cost-effectiveness using internationally accepted threshold such as 10$/ton of carbon equivalent reduced, and thresholds for the phase out of specific ozone depleting substances measured in terms of dollars spent per kg ($/kg) of each type of ODS reduced.

Monitoring & Evaluation.  Monitoring is the periodic oversight of a process, or the implementation of an activity, which seeks to establish the extent to which inputs, work schedules, other required actions and outputs are proceeding according to plan, so that timely action can be taken to correct the deficiencies detected. Evaluation is a process by which program inputs, activities and results are analyzed and judged explicitly against benchmarks or baseline conditions using performance indicators. This will allow project managers and planners to make decisions based on the evidence of information on the project implementation stage, performance indicators, level of funding still available, etc, building on the project’s logical framework.

Monitoring and Evaluation includes activities to measure the project’s achievements such as identification of performance indicators, measurement procedures, and determination of baseline conditions.  Projects are required to implement plans for monitoring and evaluation with adequate funding and appropriate staff and include activities such as description of data sources and methods for data collection, collection of baseline data, and stakeholder participation.  Given the long-term nature of many GEF projects, projects are also encouraged to include long-term monitoring plans that are sustainable after project completion.

Any issues related to the quality of backstopping and quality assurance and control of project deliverables listed in the project document should be addressed in this section.

ANNEX 2		MISSION SCHEDULE

| OKAVANGO EVALUATION MISSION |
| --- |
| MISSION ONE |
| SEPTEMBER |
| Thu 14 |  | Start work at homebase; documents review |
| Fri 15 |  | Documents review, mission planning |
| Sat 16 |  | Documents review, mission planning |
| Sun17 |  | PT departs Wellington for Singapore, via Auckland |
| Mon 18 |  | PT departs Singapore and arrives Johannesburg Mission planning; scope of work; documents review NBA departs Accra |
| Tue 19 | 0930 | NBA arrives Johannesburg PT apply for Angola Visa Team assembles; Mission planning; scope of work; documents review Briefing with Nik Sekhran Telecon with Andy Hudson, UNDP/GEF, NY |
| Wed 20 |  | Telecon with Jake Burke, FAO, Rome Mission planning; scope of work; documents review PT collect Angola visa |
| Thu 21 |  | Team travels Johannesburg to Luanda via Windhoek |
| Fri 22 | 0830 1100 1400 1500 1600 | FAO - Dr Anatolio Ndong Mba, ResRep; Ms Baktha Boulam, Admin Officer; Mr Paulo Vicente, ARR PMU - Manuel Quintino, PM OKACOM – Eng Armindo Gomez da Silva, Co-Chair OKACOM – Mr Isidro Pinheiro, Commissioner OBSC – Mr Carlos Andrade, Mr Paulo Emilio |
| Sat 23 |  | Consolidation of information from consultations, drafting |
| Sun 24 |  | Consolidation of information from consultations, drafting |
| Mon 25 | 0900 1000 | UNDP - Mr Pierre Francoise Pirlot, ResRep UNDP – Dr Gita Welch, Country Director; Ms Gabriela do Nascimento, Prog Assoc, Focal Point. |
| Tue 26 | 1000 | ACADIR NGO – Mr Jose Neto, President Telecon with Dieudonne Koguiyagda, Project Budget Holder, Accra Further discussions with PM |
| Wed 27 |  | Consolidation of information, documents review and drafting |
| Thu 28 |  | Team travels Luanda to Windhoek |
| Fri 29 | 0900 1000 1100 1200 1400 | RAISON – Mr John Mendelsohn, Director UNDP – Mr Lebogang Motlana, DRR FAO – Mr Moketsi Mokati, ResRep UNDP – Ms Akiko Yamamoto, Prog Analyst Fisheries, DWA – Dr Clinton Hay |
| Sat 30 |  | Consolidation of information from consultations, drafting |
| OCTOBER |
| Sun 01 |  | Consolidation of information from consultations, drafting |
| Mon 02 | 0830 0930 1100 1230 1400 1500 | NNF – Dr Chris Brown, Exec Director, Mr Mwazi Mwazi Project Coordinator (Every River Project) IRBM – Shirley Bethune, Project Coordinator Mr Piet Heyns, OKACOM Commissioner Dr Stefan de Wet, OBSC Member Hydrology – Mr Van Langenhove Guido, Deputy Director SSDC – Dr Hartmut Krugmann, former Project Manager |
| Tue 03 | 0830 1430 | Ms Laura Namene, OBSC Member Ms Patricia Skyer, USAID-Namibia Drafting of preliminary draft |
| Wed 04 | 0900 1430 1500 | OKACOM - Amagulu Ndeutuapo, Commissioner UNDP - Simon Nhongo, Res Rep Debrief at UNDP Drafting of preliminary draft |
| Thu 05 |  | Team travels Windhoek to Gaborone via Johannesburg Drafting of preliminary draft |
| Fri 06 | 0730 0900 1100 1400 1500 1530 | OKACOM Interim Secretariat - Mr Chaminda Rajapaksi; IRBM Project - Mr Scott McCormack OKACOM – Mr Stevie Monna, Commissioner OKACOM – Mr Gabaake Gabaake, Commissioner UNDP – Mr Leonard Dikobe UNDP – Resident Representative FAO |
| Sat 07 | 0900 | Every River Project – Mr Monty Montshiwa Final drafting effort for preliminary draft Share preliminary draft with UNDP, OKACOM Secretariat, PM and FAO |
| Sun 08 | 0900 | Team travels Gaborone to Maun |
| Mon 09 | 0900 1100 1400 | Ms Portia Segomelo, Coordinator Okavango Delta Management Plan Dr Naidu Kurugundla, Head Aquatic Vegetation Control, Department of Water Affairs Dr Nkobi Moleele, Nat Coordinator GEF Biokavango Project, HOORC |
| Tue 10 | 0900 1100 1400 | Mr Mafila Malesu, District Tourism Officer, Department of Tourism Mr K Baeti, Head Water Resources Section, Dept Water Affairs Mr Sibangani Mosojane, Distriuct Wildlife Coordinator, Department of Wildlife and National parks |
| Wed 11 | 1400 1700 | Team travels Maun to Gaborone OKACOM - Dr Akolang Tombale, Commissioner |
| Thu 12 | 1600 | Follow-up meetings with stakeholders USAID – Mr Wayne McDonald, Director Regional Project Implementation; Mr Chris Schaan, IRBM Project CTO |
| Fri 13 |  | Drafting |
| Sat 14 |  | Drafting |
| Sun 15 |  | Drafting |
| Mon 16 |  | Drafting |
| Tue 17 |  | Final drafting |
| Wed 18 |  | NBA departs Gaborone, transit Johannesburg and arrives Accra Continue final drafting |
| Thu 19 |  | PT departs Gaborone, transits Johannesburg |
| Fri 20 |  | PT transit in Singapore Dispatch draft Evaluation Report to UNDP and FAO UNDP to distribute Draft Evaluation Report to all stakeholders and all those we consulted |
| Sat 21 |  | PT arrives Auckland in transit and on to Wellington |

| MISSION TWO |
| --- |
| NOVEMBER/DECEMBER |
| Tue 28 |  | Re-drafting, taking into account comments received Follow-up consultations as required, phone/email, etc |
| Wed 29 |  | Re-drafting, taking into account comments received Follow-up consultations as required, phone/email, etc |
| Thu 30 |  | PT departs Wellington, transits Auckland and on to Singapore |
| Fri 01 |  | PT departs Singapore and arrives Johannesburg Mission planning and logistics NBA departs Accra |
| Sat 02 |  | NBA arrives Johannesburg Evaluation team reassembles and collates comments received Re-drafting, taking into account comments received Follow-up consultations as required, phone/email, etc |
| Sun 03 |  | Re-drafting, taking into account comments received |
| Mon 04 |  | Re-drafting, taking into account comments received |
| Tue 05 |  | Re-drafting, taking into account comments received; preparation of presentation |
| Wed 06 |  | Re-drafting, taking into account comments received; preparation of presentation |
| Thu 07 | 0900 | Final presentation to UNDP, PSC, OKACOM, and other stakeholders |
| Fri 08 |  | PT and NBA depart Johannesburg |
| Sat 09 |  | NBA arrives Accra PT arrives and transits Singapore |
| Sun 10 |  | PT arrives Auckland, in transit and on to Wellington |

ANNEX 3		DOCUMENTS REVIEWED AND CONSULTED

Mendelsohn, John and Selma el Obeid (2004)  Okavango River, The Flow of a Lifeline.  Struik Publishers, Cape Town.

Okavango Delta Management Plan Project (2006)  Draft Management Plan – Executive Summary.  Okavango Delta Management Plan Project Secretariat, Maun.

Turton, Anthony (Ed) (2002)  Transboundary Rivers, Sovereignty and Development : Hydropolitical drivers in the Okavango Basin.  African Waters Issues Research Unit, Pretoria.

Robinson, Peter  (2003)  Angola Water Policy Review.  SADC, Water Sector.  GTZ.

Angola, Republic of  (2003)  Strategy for the development of the water sector.  Ministry of Energy and Water.  Luanda

Angola, Republic of  (2004)  National Water Sector Management Project – Mid-Term Review.  Ministry of Energy and Water.  Luanda.

Agreement between the Governments of the Republic of Angola, the Republic of Botswana and the Republic of Namibia on the Establishment of a Permanent Okavango River Basin Water Commission. 1994

Krugmann, Hartmut – CTA/Project Manager  (2005) Environmental Protection and Sustainable Management of the Okavango River Basin (EPSMO).  UNTS/RAF/010/GEF.  Inception Report, 04 April 2005

Namibia, Government of  (2000)  National Water Policy – Framework for Equitable, Efficient and Sustainable Water Resources Management and Water Services.  Ministry of Agriculture, Water and Rural Development, Windhoek.

Holtz, Uwe  (2003) Namibia – in Poverty Reduction Strategy Papers and their Relationship to the Combating of Desertification – The Role of Parliaments.  Bonn University.

Namibia, Government of  (1995)  Namibia’a Environmental Assessment policy for Sustainable Development and Environmental Conservation.

Namibia, Government of  (2004)  Water Act.

DHI Water & Environment (2005)  Hydrology and Water Resources : Okavango Delta Management plan.  Department of Water Affairs and Department of Environmental Affairs, Gaborone.

OKACOM Interim Secretariat  (undated)  OKACOM Brochure, Gaborone.

University of Botswana (undated)  Harry Oppenheimer Okavango Research Centre Booklet.  Maun

SIDA  (undated)  Every River Has its People Project.  Brochure.  Windhoek.

Other documents

- Project Document

- Rules and Procedures of the UN System for Project Execution

- Project Implementation Reviews (PIRs/ APRs)

- Project Quarterly Reports

- Minutes of PSC meeting

- Minutes of OKACOM Meetings, documenting OKACOM Policies

- Other OKACOM documents made available by the Interim Secretariat

WEBSITES VISITED AND CONSULTED

Every River Has its People Project  http://www.everyriver.net/PrjBakgr.html

OKACOM Home Page  http://www.okacom.org/English/pages/home.htm

International Rivers Network  http://www.irn.org/programs/okavango/

Okavango Delta Peoples of Botswana  http://www.mindspring.com/~okavango/

Global International waters Assessment (GIWA)  http://www.giwa.net/publications/r44.phtml

UNDP Office in Angola  http://mirror.undp.org/angola/

UNDP Office in Namibia  http://www.undp.un.na/env/undp-env-home.htm

UNDP Office in Botswana  http://www.unbotswana.org.bw/undp/environment.html

IW Southeast Asia Regional Learning Centre  http://www.iwsea.org/information/TDA_SAP

Food and Agriculture Organization of the UN  http://www.fao.org/dcrep/W741B/w7414b

ANNEX 4		PERSONS AND ORGANIZATIONS MET AND/OR

CONSULTED

Permanent Okavango River Basin Water Commission (OKACOM)

Mr Armindo Mario Gomez da Silva, Co-Chair, Angola

Mr Isidro Pinheiro, Commissioner, Angola

Mr Piet Heyns, Commissioner, Namibia

Mr WM Ndeutapo Amagulu, Commissioner, Namibia

Mr Akolang Tombale, Co-Chair, Botswana

Mr Gabaake Gabaake, Commissioner, Botswana

Mr Stevie Monna, Commissioner, Botswana

Okavango Basin Steering Committee (OBSC)

Mr Carlos Andrade, Member, Angola

Mr Paolo Emilio, Member, Angola

Mr Stefen de Wet, Member, Namibia

Ms Laura Namene, Member, Namibia

Ms Portia Segomelo, Member, Botswana

Mr Kalaote Kalaote, Member, Botswana

United Nations Development Programme (UNDP)

Mr Andy Hudson, GEF/UNDP Principal Technical Advisor

Mr Nik Sekhran, Regional Coordinator Biodiversity/ International Waters, GEF/UNDP

Mr Pierre-Francois Pirlot, UNDP Resident Representative, UN Resident Coordinator, Angola

Ms Gita Welch, Country Director, Angola

Ms Gabriela do Nascimento, Programme Associate, Angola

Mr Simon R Nhongo, Resident Representative, Namibia

Mr Lebogang Motlana, Deputy Resident Representative, Namibia

Ms Akiko Yamamoto, Programme Officer, Environment Unit, Namibia

Ms Viola Morgan, Deputy Resident Representative, Botswana

Mr Leonard Dikobe, Programme Specialist – Energy & Environment, Botswana

Mr Hiro Okuda, Programme Officer – Environment, Botswana

Food and Agriculture Organization of the United Nations (FAO)

Mr Jacob Burke, Senior Water Policy Officer, AGLW, Rome

Mr Anatolio Ndong Mba, Representative in Angola

Mr Paolo Vicente, Assistant Representative in Angola

Ms Bakhta Boulam, Administrative Officer in Angola

Mr Fernandez, Programme Officer, Angola

Mr Dieudonné Koguiyagda, Project Budget Holder, FAO Regional Office for Africa, Accra

Mr Moeketsi Mokati, Representative in Namibia

Mr David Tibe, Assistant Representative (Programme), Botswana

Environment Protection & Sustainable Management of the Okavango River Basin Project

Mr Manuel Quintino, Angola NCU Coordinator and Project Manager a.i.

Ms Eva Kulenga, Administration Assistant

ACADIR-Angola

Mr José Neto, President and CEO

Research and Information Services of Namibia (RAISON)

Mr John Mendelsohn

Ms Selma el-Obeid

Ministry of Fisheries and Marine Resources, Namibia

Mr Clinton Hay, Chief Fisheries Biologist

Ministry of Agriculture, Water and Forestry, Namibia

Mr Guido van Langenhove, Deputy Director Hydrology, Department of Water Affairs

Meteorological Services, Ministry of Works Transport and Communications, Namibia

Mr Sepiso Mwangala, Climate and data Bank Manager

Mr B Ngonyi Mwalwa, Inspector, Instrumentation and Communications

Namibia Nature Foundation

Mr Chris Brown, Executive Director

Integrated River Basin Management Project (IRBM)

Mr Scott McCormick, Chief of Party for Okavango IRBM Project, Botswana

Ms Shirley Bethune, National Coordinator, Namibia

Mr Chaminda Rajapaksi, Coordinator, OKACOM Interim Secretariat, Botswana

Mr Chris Schaan, NRM Specialist

Southern Sustainable Development Corporation, Namibia

Mr Hartmut Krugmann, previous Project Manager

US Agency for International Development (USAID)

Mr Wayne McDonald, Office Director, Regional Programme Implementation Office

Ms Patricia Skyer, Senior CBNRM Advisor, Namibia

Ministry of Environment and Tourism, Namibia

Mr IM Muhinda, Director of Administration and Support Services

Every River has its People Project

Mr Montshiwa M Montshiwa, Regional Project Manager, Botswana

Mr Mwazi Mwazi, Project Coordinator, Namibia

Ministry of Minerals, Energy and Water Affairs, Botswana

Mr Naidu Kurungundla, Senior Botanist, Department of Water Affairs

Mr Koketso Baeti, Head Hydrology & Water Affairs, Department of Water Affairs

University of Botswana, Harry Oppenheimer Okavango Research Centre

Mr Lars Ramberg, Director

Mr Nkobi Moleele, Coordinator, UNDP/GEF Okavango Wetland Biodiversity Conservation Project

Mr Cornelius Van der Post, Snr Research Fellow – Social Systems

Mr Piotr Wolski, Research Fellow, Groundwater Hydrology

Northwest District Council, Botswana

Mr Mafila Malesu, Tourism Officer

Ministry of Environment , Wildlife and Tourism, Botswana

Ms Felicity Rabolo, Tourism Officer, Department of Tourism

Mr Sibangani Mosojane, District Wildlife Coordinator, Dept of Wildlife & National Parks

UNEP/GEF/UNOPS Indigenous Vegetation Regional Project

Mr Gerrit B Bartels, Regional Coordinator, Botswana

Department of Environmental Affairs, Botswana

Mr Ruud Jansen, Chief Technical Advisor, Environment Support Programme

ANNEX 5		PROPOSED TERMS OF REFERENCE FOR

PROJECT STEERING COMMITTEE (PSC)

The Project Steering Committee sets the policy for the project and provides guidance and directions to the Project Manager and other project stakeholders.  It also supports UNDP which maintains ultimate accountability to the GEF for the delivery of project products and the administration of project funds.  Project funds will be administered as per the Standard Basic Assistance Agreements between UNDP and the Programme countries, which govern the use of UNDP funds.  UNDP will form part of and respect PSC decisions and agreements.  If a situation arises where UNDP feels that its mandate or its accountability could be compromised by a decision of the PSC, it will attempt to resolve the matter by negotiation taking into account the signed ProDoc and the SBAA.  If this fails, it may decide to refer the matter to the GEF Secretariat, or withdraw the project.

Tasks of the Project Steering Committee

- To set policy and provide strategic guidance to ensure the timely and cost-effective realisation of project objectives

- To review and recommend approval of Annual Work Plans

- To monitor progress in project implementation against agreed Outcomes and Outputs

- To validate Project Outputs, including the Transboundary Diagnostic Analysis Study, the Strategic Action Programme and other documents

- To resolve conflicts and problem areas as needed to facilitate project delivery

- To ensure that country commitments, including of co-financing, technical and operational support, are met

# Membership

The Project Steering Committee will comprise :

- One representative from each of the participating Governments : Angola, Botswana and Namibia (OKACOM Co-chairs or as the Governments so decide)

- One representative for UNDP at Country Office level (suggested Resident Representative or Country Director from Angola Country Office as the lead UNDP CO)

- One representative from UNDP/GEF Regional Coordination Unit

- One representative from FAO as Executing Agency

The following are also invited / expected to attend meetings :

- Other members of OKACOM

- Project Manager – required to attend and report on progress

- Project Budget Holder – required to attend and present  financial account

- Members of OBSC to advise on technical issues that may arise

- Relevant representatives of related projects in the Okavango Basin to advise on cooperative and complementary activities

Rules of Procedure

The Project Steering Committee will be co-chaired by UNDP and OKACOM.  UNDP will be represented by the UNDP Angola Resident Representative or Country Director to provide continuity.  OKACOM will be represented by the relevant Commissioner of the country where the meeting is being held.

- The PSC will meet at least every six months and more frequently if considered necessary.

- Meetings of the PSC will rotate between the participating countries, taking into account logistical and resource considerations.

- An agenda will be prepared by the PM in consultation with the co-chairs and taking into account any issues raised by members, and circulated in good time to allow OKACOM and others to consult

- The PSC will make all its decisions through consensus.

- The PSC will delegate representatives to sit on selection panels for consultants and service vendors, if requested by UNDP.

- The minimum number of members necessary to comprise a quorum will be determined by the first meeting.

- Members of the PSC may nominate an alternate to attend PSC meetings, in the event that the designated representative is unable to attend.  Alternates will be expected to be fully briefed and able to make decisions on behalf of the permanent member.

- An Annual Tripartite Review of the project will be chaired by UNDP, as part of a regular PSC meeting.  The TPR will approve the Annual Project Review (APR) and Annual Work Plan.

- Decisions made at the PSC will be considered collective decisions of the Committee as a whole and members undertake to stand by them following the meetings.

ANNEX 6	FINANCIAL MANAGEMENT DOCUMENTS SUPPLIED BY FAO

b

Printed on: 02-OCT-06 11.21.42 (via FPMIS)

Financial Statement (Trust Funds)

Activity: TF2A24AS03216 (TF Project)

From: 1997-01 To: 2015-13

TF_Activity: TF2A24AS03216 121614 UNTS/RAF/010/GEF (Project) ¦ Organization: N/A

|  | Budget | Soft Commitment | Hard Commitments | Total Commitments | Actuals | Commitments and Actuals | Available Budget | Forecast | Projected Balance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 5011 Salaries Professional (Parent account) | 624,336 | 0 | 0 | 0 | 286,525 | 286,525 | 337,811 | 0 | 337,811 |
| 5012 Salaries General Service (Parent account) | 67,000 | 0 | 0 | 0 | 41,234 | 41,234 | 25,766 | 0 | 25,766 |
| 5013 Consultants (Parent account) | 1,385,230 | 0 | 21,102 | 21,102 | 100,923 | 122,024 | 1,263,206 | 0 | 1,263,206 |
| 5014 Contracts (Parent account) | 500,000 | 0 | 0 | 0 | 59,351 | 59,351 | 440,649 | 0 | 440,649 |
| 5020 Locally Contracted Labour (Parent account) | 42,906 |  |  | 0 | 41,104 | 41,104 | 1,802 | 0 | 1,802 |
| 5021 Travel (Parent account) | 943,187 | 0 | 0 | 0 | 152,917 | 152,917 | 790,270 | 0 | 790,270 |
| 5023 Training (Parent account) | 485,991 | 0 | 0 | 0 | 475 | 475 | 485,516 | 0 | 485,516 |
| 5024 Expendable Procurement (Parent account) | 155,687 | 0 | 0 | 0 | 8,087 | 8,087 | 147,600 | 0 | 147,600 |
| 5025 Non Expendable Procurement (Parent account) | 346,431 | 0 | 0 | 0 | 131,767 | 131,767 | 214,664 | 0 | 214,664 |
| 5027 Technical Support Services (Parent account) | 78,845 |  |  | 0 | 30,340 | 30,340 | 48,505 | 0 | 48,505 |
| 5028 General Operating Expenses (Parent account) | 271,252 | 0 | 0 | 0 | 131,832 | 131,832 | 139,419 | 0 | 139,419 |
| 5029 Support Costs (Parent account) | 490,090 | 0 | 0 | 0 | 93,635 | 93,635 | 396,455 | 0 | 396,455 |
| 5040 General Overhead Expenses (Parent account) | 44 |  |  | 0 | 118 | 118 | <75> | 0 | <75> |
| Total Expenses | 5,390,998 | 0 | 21,102 | 21,102 | 1,078,307 | 1,099,409 | 4,291,590 | 0 | 4,291,590 |

Printed on: 02-OCT-06 11.22.27 (via FPMIS)

Financial Statement (Trust Funds)

Activity: TF2A24AS03216 (TF Project)

From: 1997-11 To: 2015-13

TF_Activity: TF2A24AS03216 121614 UNTS/RAF/010/GEF (Project) ¦ Organization: N/A

|  | Budget | Soft Commitment | Hard Commitments | Total Commitments | Actuals | Commitments and Actuals | Available Budget | Forecast | Projected Balance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 5101 Base Salary At Actual - Professional (Child account) |  |  |  | 0 | 111,812 | 111,812 | <111,812> | 0 | <111,812> |
| 5102 Assignment/Mobility/Transitional Allowances (Child account) |  |  |  | 0 | 19,822 | 19,822 | <19,822> | 0 | <19,822> |
| 5103 Post Adjustment (Child account) |  |  |  | 0 | 65,902 | 65,902 | <65,902> | 0 | <65,902> |
| 5104 Basic Medical Insurance Plan - Professional (Child account) |  |  |  | 0 | 5,114 | 5,114 | <5,114> | 0 | <5,114> |
| 5105 Pension Plan - Professional (Child account) |  |  |  | 0 | 34,052 | 34,052 | <34,052> | 0 | <34,052> |
| 5116 Medical Costs - Professional (Child account) |  | 0 | 0 | 0 | 222 | 222 | <222> | 0 | <222> |
| 5125 Termination Indemnity - Professional (Child account) |  |  |  | 0 | <269> | <269> | 269 | 0 | 269 |
| 5128 Benefits At Standard - Professional (Child account) |  |  |  | 0 | 52,161 | 52,161 | <52,161> | 0 | <52,161> |
| 5150 Professional Staff cost variance (Child account) |  |  |  | 0 | <2,291> | <2,291> | 2,291 | 0 | 2,291 |
| 5299 Salaries Professional Conversion (Child account) |  |  |  | 0 |  | 0 | 0 | 0 | 0 |
| 5300 Salaries Professional Budget (Child account) | 624,336 | 0 | 0 | 0 | 0 | 0 | 624,336 | 0 | 624,336 |
| 5301 Base Salary At Actual - General Service (Child account) |  |  |  | 0 | 18,484 | 18,484 | <18,484> | 0 | <18,484> |
| 5303 Basic Medical Insurance Plan - General Service (Child account) |  |  |  | 0 | 11,301 | 11,301 | <11,301> | 0 | <11,301> |
| 5304 Pension Plan - General Service (Child account) |  |  |  | 0 | 3,562 | 3,562 | <3,562> | 0 | <3,562> |
| 5315 Medical Costs - General Service (Child account) |  |  |  | 0 | 664 | 664 | <664> | 0 | <664> |
| 5338 Benefits At Standard - General Service (Child account) |  |  |  | 0 | 6,878 | 6,878 | <6,878> | 0 | <6,878> |
| 5350 General Service Staff cost variance (Child account) |  |  |  | 0 | 344 | 344 | <344> | 0 | <344> |
| 5499 Salaries General Service Conversion (Child account) |  |  |  | 0 |  | 0 | 0 | 0 | 0 |
| 5500 Salaries General Service Budget (Child account) | 67,000 | 0 | 0 | 0 | 0 | 0 | 67,000 | 0 | 67,000 |
| 5542 Consultants - Internationally-recruited (Child account) | 0 | 0 | 76 | 76 | 45,903 | 45,980 | <45,980> | 0 | <45,980> |
| 5543 Consultants - Locally-recruited (Child account) | 0 |  |  | 0 | 44,507 | 44,507 | <44,507> | 0 | <44,507> |
| 5551 Consultants - National Projects Personnel (Child account) |  | 0 | 21,025 | 21,025 | 10,513 | 31,538 | <31,538> | 0 | <31,538> |
| 5570 Consultants Budget (Child account) | 1,385,230 | 0 | 0 | 0 | 0 | 0 | 1,385,230 | 0 | 1,385,230 |
| 5571 Contracts - Services (Child account) | 0 | 0 | 0 | 0 | 38,902 | 38,902 | <38,902> | 0 | <38,902> |
| 5572 Contracts - Construction (Child account) | 0 |  |  | 0 | 20,449 | 20,449 | <20,449> | 0 | <20,449> |
| 5650 Contracts Budget (Child account) | 500,000 |  |  | 0 |  | 0 | 500,000 | 0 | 500,000 |
| 5651 Overtime (Child account) |  |  |  | 0 | 206 | 206 | <206> | 0 | <206> |
| 5652 Casual labour / Temporary assistance (Child account) | 0 |  |  | 0 | 40,898 | 40,898 | <40,898> | 0 | <40,898> |
| 5660 Overtime Budget (Child account) | 42,906 |  |  | 0 |  | 0 | 42,906 | 0 | 42,906 |
| 5661 Duty Travel (Child account) | 0 | 0 | 0 | 0 | 37,865 | 37,865 | <37,865> | 0 | <37,865> |
| 5672 Rest and Recuperation Travel (Child account) | 0 | 0 | 0 | 0 | 1,528 | 1,528 | <1,528> | 0 | <1,528> |
| 5684 Travel - Consultants - International (Child account) | 0 | 0 | 0 | 0 | 79,387 | 79,387 | <79,387> | 0 | <79,387> |
| 5685 Travel - Consultants - National (Child account) | 0 |  |  | 0 | 2,134 | 2,134 | <2,134> | 0 | <2,134> |
| 5692 Travel - ATS/STS/TSS (Child account) | 0 | 0 | 0 | 0 | 10,729 | 10,729 | <10,729> | 0 | <10,729> |
| 5694 Travel - Training (Child account) | 0 |  |  | 0 | 2,094 | 2,094 | <2,094> | 0 | <2,094> |
| 5698 Travel - Non Staff (Child account) | 0 | 0 | 0 | 0 | 19,180 | 19,180 | <19,180> | 0 | <19,180> |
| 5900 Travel - Duty Budget (Child account) | 943,187 | 0 | 0 | 0 | 0 | 0 | 943,187 | 0 | 943,187 |
| 5905 Group Training Costs (Child account) | 0 |  |  | 0 | 475 | 475 | <475> | 0 | <475> |
| 5920 Training Budget (Child account) | 485,991 | 0 | 0 | 0 | 0 | 0 | 485,991 | 0 | 485,991 |
| 5924 Other Expendable Equipment (Child account) | 0 |  |  | 0 | 7,970 | 7,970 | <7,970> | 0 | <7,970> |
| 5925 General Office Equipment - Contract For Purchase (Child account) |  |  |  | 0 | 83 | 83 | <83> | 0 | <83> |
| 5933 Other Office Supplies (Child account) | 0 |  |  | 0 | 34 | 34 | <34> | 0 | <34> |
| 6000 Expendable Procurement Budget (Child account) | 155,687 | 0 | 0 | 0 | 0 | 0 | 155,687 | 0 | 155,687 |
| 6002 Communications Equipment - Contract For Purchase (Child account) | 0 |  |  | 0 | 11,156 | 11,156 | <11,156> | 0 | <11,156> |
| 6004 Data Process Equip - Mini/Micro Comput - Contr For Purch (Child account) |  |  |  | 0 | 380 | 380 | <380> | 0 | <380> |
| 6005 Data Processing Equipment - Others - Contract For Purchase (Child account) | 0 | 0 | 0 | 0 | 38,913 | 38,913 | <38,913> | 0 | <38,913> |
| 6006 Furniture - Contract For Purchase (Child account) | 0 |  |  | 0 | 22,145 | 22,145 | <22,145> | 0 | <22,145> |
| 6007 Printing And Reproduction Equip - Contract For Purchase (Child account) | 0 |  |  | 0 | 145 | 145 | <145> | 0 | <145> |
| 6010 Improvements To Premises (Child account) |  |  |  | 0 | 10,950 | 10,950 | <10,950> | 0 | <10,950> |
| 6011 Vehicles - Contract For Purchase (Child account) | 0 |  |  | 0 | 24,033 | 24,033 | <24,033> | 0 | <24,033> |
| 6012 Other Non-Expendable Equipment - Contract For Purchase (Child account) | 0 |  |  | 0 | 15,618 | 15,618 | <15,618> | 0 | <15,618> |
| 6013 Security Equipment (Child account) |  |  |  | 0 | 8,428 | 8,428 | <8,428> | 0 | <8,428> |
| 6100 Non Expendable Procurement Budget (Child account) | 346,431 | 0 | 0 | 0 | 0 | 0 | 346,431 | 0 | 346,431 |
| 6112 Projects Servicing Costs (Child account) | 0 |  |  | 0 | 93,635 | 93,635 | <93,635> | 0 | <93,635> |
| 6120 Technical Assistance to Field Projects (Child account) | 0 |  |  | 0 | 30,340 | 30,340 | <30,340> | 0 | <30,340> |
| 6130 Support Costs Budget (Child account) | 490,090 | 0 | 0 | 0 | 0 | 0 | 490,090 | 0 | 490,090 |
| 6150 Technical Support Services Budget (Child account) | 78,845 |  |  | 0 |  | 0 | 78,845 | 0 | 78,845 |
| 6152 Miscellaneous (Child account) | 0 | 0 | 0 | 0 | 32,337 | 32,337 | <32,337> | 0 | <32,337> |
| 6172 Rental Of Premises (Child account) | 0 |  |  | 0 | 54,150 | 54,150 | <54,150> | 0 | <54,150> |
| 6175 Vehicles Operation And Maintenance (Child account) | 0 |  |  | 0 | 3,105 | 3,105 | <3,105> | 0 | <3,105> |
| 6176 Operation And Maintenance Of Equipment (Child account) | 0 |  |  | 0 | 1,028 | 1,028 | <1,028> | 0 | <1,028> |
| 6177 Other Operating Costs (Child account) | 0 |  |  | 0 | 8,045 | 8,045 | <8,045> | 0 | <8,045> |
| 6178 Electricity (Child account) | 0 |  |  | 0 | 2,165 | 2,165 | <2,165> | 0 | <2,165> |
| 6181 Water (Child account) | 0 |  |  | 0 | 260 | 260 | <260> | 0 | <260> |
| 6183 Insurance (Child account) | 0 |  |  | 0 | 1,067 | 1,067 | <1,067> | 0 | <1,067> |
| 6187 Postal And Pouch Services (Child account) | 0 |  |  | 0 | 72 | 72 | <72> | 0 | <72> |
| 6190 Other Communications (Child account) | 0 |  |  | 0 | 2,402 | 2,402 | <2,402> | 0 | <2,402> |
| 6207 Security Services (Child account) | 0 |  |  | 0 | 23,565 | 23,565 | <23,565> | 0 | <23,565> |
| 6251 Courier Services (Child account) | 0 |  |  | 0 | 593 | 593 | <593> | 0 | <593> |
| 6255 Telephone Costs (Child account) | 0 |  |  | 0 | 3,043 | 3,043 | <3,043> | 0 | <3,043> |
| 6300 General Operating Expenses Budget (Child account) | 271,252 | 0 | 0 | 0 | 0 | 0 | 271,252 | 0 | 271,252 |
| 6303 Pouch & Remailing (Child account) | 0 |  |  | 0 | 44 | 44 | <44> | 0 | <44> |
| 6304 International Courier (Child account) | 0 |  |  | 0 | 75 | 75 | <75> | 0 | <75> |
| 6400 General Overhead Expenses Budget (Child account) | 44 |  |  | 0 |  | 0 | 44 | 0 | 44 |
| Total Expenses | 5,390,998 | 0 | 21,102 | 21,102 | 1,078,307 | 1,099,409 | 4,291,590 | 0 | 4,291,590 |

V bPrinted on: 02-OCT-06 10.54.18 (Via FPMIS)

TF Project Status Report Split by Prior/Current/Future Years (Annual Values)

Activity: TF2A24AS03216

Expenses Include: C. Actuals + Hard CMTs + Soft CMTs

Up to Period: 2006-13

TF Activity: TF2A24AS03216 121614 UNTS/RAF/010/GEF (Project) ¦ Organisation: N/A

|  |  | Prior Years | Current Year 2006 Up To:2006-13 | Cumulative Up To 2006-13 | Future Years | Project Total |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | 2003 | 2004 | 2005 | 2006 | CUMULATIVE | 2007 | 2008 | 2009 | 2010 | TOTAL |
|  |  | Budgets | Expenses | Balance | Budgets | Expenses | Balance | Budgets | Expenses | Balance | Budgets | Expenses | Balance | Budgets | Expenses | Balance | Budgets | Expenses | Balance | Budgets | Expenses | Balance | Budgets | Expenses | Balance | Budgets | Expenses | Balance | Budgets | Expenses | Balance |
| Funds Received |  |  | 0 | <894,559> | 894,559 |  | <8,697> | 8,697 |  | <10,427> | 10,427 |  | 1,242 | <1,242> | 0 | <912,441> | 912,441 |  |  |  |  |  |  |  |  |  |  |  |  | 0 | <912,441> | 912,441 |
|  | 3001 Contributions Received In Advance (Parent) |  | 0 | <894,559> | 894,559 |  | <8,697> | 8,697 |  | <10,427> | 10,427 |  | 1,242 | <1,242> | 0 | <912,441> | 912,441 |  |  |  |  |  |  |  |  |  |  |  |  | 0 | <912,441> | 912,441 |
| Expenditure |  |  | 53,196 | 53,196 | 0 | 86,678 | 86,678 | 0 | 672,974 | 672,974 | 0 | 2,500,635 | 286,560 | 2,214,075 | 3,313,484 | 1,099,409 | 2,214,075 | 1,815,117 | 0 | 1,815,117 | 0 | 0 | 0 | 0 | 0 | 0 | 262,398 | 0 | 262,398 | 5,390,998 | 1,099,409 | 4,291,590 |
|  | 5011 Salaries Professional (Parent) |  | 0 | 0 | 0 | 40,336 | 40,336 | 0 | 201,205 | 201,205 | 0 | 206,000 | 44,984 | 161,016 | 447,541 | 286,525 | 161,016 | 172,000 | 0 | 172,000 | 0 | 0 | 0 | 0 | 0 | 0 | 4,795 | 0 | 4,795 | 624,336 | 286,525 | 337,811 |
|  | 5012 Salaries General Service (Parent) |  | 0 | 0 | 0 | 0 | 0 | 0 | 19,250 | 19,250 | 0 | 26,400 | 21,983 | 4,417 | 45,650 | 41,234 | 4,417 | 35,500 | 0 | 35,500 | 0 | 0 | 0 | 0 | 0 | 0 | <14,150> | 0 | <14,150> | 67,000 | 41,234 | 25,766 |
|  | 5013 Consultants (Parent) |  | 0 | 0 | 0 | 0 | 0 | 0 | 44,761 | 44,761 | 0 | 817,380 | 77,264 | 740,116 | 862,141 | 122,024 | 740,116 | 478,290 | 0 | 478,290 | 0 | 0 | 0 | 0 | 0 | 0 | 44,799 | 0 | 44,799 | 1,385,230 | 122,024 | 1,263,206 |
|  | 5014 Contracts (Parent) |  |  |  |  |  |  |  | 48,901 | 48,901 | 0 | 200,000 | 10,450 | 189,550 | 248,901 | 59,351 | 189,550 | 200,000 | 0 | 200,000 |  |  |  |  |  |  | 51,099 | 0 | 51,099 | 500,000 | 59,351 | 440,649 |
|  | 5020 Locally Contracted Labour (Parent) |  |  |  |  | 206 | 206 | 0 | 21,329 | 21,329 | 0 | 19,200 | 19,569 | <369> | 40,735 | 41,104 | <369> | 2,500 | 0 | 2,500 |  |  |  | 0 | 0 | 0 | <329> | 0 | <329> | 42,906 | 41,104 | 1,802 |
|  | 5021 Travel (Parent) |  | 13,131 | 13,131 | 0 | 19,436 | 19,436 | 0 | 104,750 | 104,750 | 0 | 497,034 | 15,600 | 481,434 | 634,351 | 152,917 | 481,434 | 321,865 | 0 | 321,865 | 0 | 0 | 0 | 0 | 0 | 0 | <13,029> | 0 | <13,029> | 943,187 | 152,917 | 790,270 |
|  | 5023 Training (Parent) |  | 0 | 0 | 0 | 0 | 0 | 0 | 475 | 475 | 0 | 203,000 | 0 | 203,000 | 203,475 | 475 | 203,000 | 257,991 | 0 | 257,991 | 0 | 0 | 0 | 0 | 0 | 0 | 24,525 | 0 | 24,525 | 485,991 | 475 | 485,516 |
|  | 5024 Expendable Procurement (Parent) |  | 0 | 0 | 0 | 0 | 0 | 0 | 7,692 | 7,692 | 0 | 45,676 | 395 | 45,281 | 53,368 | 8,087 | 45,281 | 110,011 | 0 | 110,011 | 0 | 0 | 0 | 0 | 0 | 0 | <7,692> | 0 | <7,692> | 155,687 | 8,087 | 147,600 |
|  | 5025 Non Expendable Procurement (Parent) |  | 23,706 | 23,706 | 0 | 17,597 | 17,597 | 0 | 68,755 | 68,755 | 0 | 177,000 | 21,709 | 155,291 | 287,058 | 131,767 | 155,291 | 25,000 | 0 | 25,000 | 0 | 0 | 0 | 0 | 0 | 0 | 34,373 | 0 | 34,373 | 346,431 | 131,767 | 214,664 |
|  | 5027 Technical Support Services (Parent) |  |  |  |  |  |  |  | 21,980 | 21,980 | 0 | 18,815 | 8,360 | 10,455 | 40,795 | 30,340 | 10,455 | 13,141 | 0 | 13,141 |  |  |  |  |  |  | 24,909 | 0 | 24,909 | 78,845 | 30,340 | 48,505 |
|  | 5028 General Operating Expenses (Parent) |  | 11,524 | 11,524 | 0 | 1,179 | 1,179 | 0 | 72,622 | 72,622 | 0 | 62,800 | 46,507 | 16,293 | 148,125 | 131,832 | 16,293 | 33,809 | 0 | 33,809 | 0 | 0 | 0 | 0 | 0 | 0 | 89,318 | 0 | 89,318 | 271,252 | 131,832 | 139,419 |
|  | 5029 Support Costs (Parent) |  | 4,836 | 4,836 | 0 | 7,880 | 7,880 | 0 | 61,179 | 61,179 | 0 | 227,330 | 19,740 | 207,590 | 301,225 | 93,635 | 207,590 | 165,010 | 0 | 165,010 | 0 | 0 | 0 | 0 | 0 | 0 | 23,855 | 0 | 23,855 | 490,090 | 93,635 | 396,455 |
|  | 5040 General Overhead Expenses (Parent) |  |  |  |  | 44 | 44 | 0 | 75 | 75 | 0 |  |  |  | 118 | 118 | 0 |  |  |  |  |  |  | 0 | 0 | 0 | <75> | 0 | <75> | 44 | 118 | <75> |
|  | Total Expenditure |  | 53,196 | 53,196 | 0 | 86,678 | 86,678 | 0 | 672,974 | 672,974 | 0 | 2,500,635 | 286,560 | 2,214,075 | 3,313,484 | 1,099,409 | 2,214,075 | 1,815,117 | 0 | 1,815,117 | 0 | 0 | 0 | 0 | 0 | 0 | 262,398 | 0 | 262,398 | 5,390,998 | 1,099,409 | 4,291,590 |
| Balance |  |  |  | <841,363> |  |  | 77,981 |  |  | 662,547 |  |  | 287,802 |  |  | 186,968 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 186,968 |  |

REMAINING FUNDS, BY OUTPUT AS ON 15 OCTOBER 2006

| PROJECT COMPONENT S/OUTPUTS | ORIGINAL BUDGET ESTIMATES AS IN PROJECT DOCUMENT | ESTIMATES BASED ON BUD REV ”B” GEF | EXPENDITURES AS ON 15 OCTOBER GEF | ESTIMATED REMAINING FUNDS AS ON 15 OCTOBER GEF |
| --- | --- | --- | --- | --- |
|  | TOTAL | CO-FINANCING | GEF |  |  |  |
| Component A: Joint Management |  |  |  |  |  |  |
| Output A1: Expertise | 731,700 | 35,000 | 696,700 | 1,875,898 | 789,000 | 1,086,898 |
| Output A2: Stake Holder Participation | 934,850 | 100,000 | 834,850 | 386,050 | 0 | 386,050 |
| Output A3: Policy initiatives | 360,800 | 315,000 | 45,800 | 291,571 | 0 | 291,571 |
| Output A4: Monitoring and evaluation | 161,675 | 0 | 161,675 | 90,583 | 48,000 | 42583 |
| Total A: | 2,189,025 | 450,000 | 1,739,02525 | 2,644,102 | 837,000 | 1,807,102 |
| Component B: Completed TDA |  |  |  |  |  |  |
| Output B1: Basin water resource analysis | 1,966,820 | 1,426,000 | 540,820 | 603,428 | 130,000 | 473,428 |
| Output B2: Socio-economic analysis | 720,200 | 200,000 | 520,200 | 464,418 | 0 | 464,418 |
| Output B3: Super-imposed frameworks | 94,069 | 0 | 94,069 | 103,000 | 59,000 | 44,000 |
| Output B4: Environmental assets | 117,630 | 0 | 117,630 | 125,000 | 0 | 125,000 |
| Output B5: Alternatives | 500,576 | 0 | 500,576 | 116,367 | 0 | 116,367 |
| Output B6: Water management models | 127,450 | 0 | 127,450 | 116,367 | 0 | 116,367 |
| Output B7: Criteria | 90,140 | 0 | 90,140 | 44,100 | 0 | 44,100 |
| Total B: | 3,616,885 | 1,626,000 | 1,990,885 | 1,572,680 | 189,000 | 1,383,680 |
| Component C: SAP Formulation |  |  |  |  |  |  |
| Output C1: Technical & Policy implications of options | 111,660 | 0 | 111,660 | 217,128 | 0 | 217,128 |
| Output C2: Joint Management plan negotiated | 417,040 | 0 | 417,040 | 214,000 | 0 | 214,000 |
| Output C3: Commitments defined | 137,190 | 0 | 137,190 | 83,000 | 0 | 83,000 |
| Output C4: SAP document produced | 245,210 | 0 | 245,210 | 24,000 | 0 | 24,000 |
| Output C5: SAP finance mobilized | 259,900 | 0 | 259,900 | 146,000 | 0 | 146,000 |
| Total C: | 1,171,000 | 0 | 1,171,000 | 684,128 | 0 | 684,128 |
| Project Support Services | 490,091 |  | 490,090 | 490,090 | 98,478 | 391,612 |
| TOTAL | 7,467,000 | 2,076,000 | 5,391,000 | 5,391,000 | 1,124,478 | 4,266,522 |

ANNEX 7.	PROGRESS AS REPORTED BY THE PMU UP TO OCTOBER 2006

Progress with the project objectives and targets

| OBJECTIVES AND TARGETS | PROGRESS ACCORDING TO THE PMU |
| --- | --- |
| Project Objective To alleviate imminent and long-term threats to the linked land and water systems of the Okavango River through the joint management of the Okavango River Basin water resources and the protection of its linked aquatic ecosystems, comprising all wetlands, fluvial and lacustrine systems, and their biological diversity | Very little progress was made to meet the project’s objective. Although sharing the same River Basin, apparently the three riparian countries still have different perspectives on the utilisation of the Okavango natural resources, mainly soil and water. Due to the fact that the establishment of National Coordination Units did not happen simultaneously (the Botswana’s NCU is still to be established), the PMU had difficulties in promoting dialogue among the three riparian countries towards setting strategies for the joint management of the Okavango River Basin. |
| Purpose One To overcome current policy, institutional, human resource and information barriers and constraints to co-ordination and joint management of the basin | Very little has been achieved. But it is important to mention the establishment of the PMU in Luanda and the establishment of the Angolan and Namibian National Coordination Units and the Angolan and Namibian Intersectoral Committees. There is some effort by the PMU, through the National Coordination Units to bring the three riparian countries together (co-ordination and joint management) of the Okavango River Basin. However, currently there are still policy, institutional and human resources barriers. In relation to information, there is a great need and willing by three countries to share hydrological information being generated in the Basin. As a result of this, the work of the OKACOM/OBSC Hydrologic Task Force was resumed in July 2006. Terms of Reference for the Task Force were designed and will be submitted to OKACOM for approval. The riparian countries plus two major projects with activities in the Okavango River Basin, namely GEF EPSMO and IRBM have planned to meet regularly and discuss issues related the hydrological work to be carried out in the Basin as a whole. With the completion of 5 hydrometric stations in the Angolan portion of the Okavango Basin, the sharing of information among the riparian countries is to start very soon. This exercise will be made on a regular basis, allowing all the actors to know what is happening in the neighbouring countries. Another relevant element of the exercise on sharing hydrological information is the harmonisation of data that was set one of the main priorities by the riparian countries. |
| Purpose Two To complete a transboundary analysis to underpin a programme of joint management | There is already a preliminary TDA carried out during the PDF-B phase. This TDA document should be seen as a basis for the completion of the TDA work envisaged by the project. However, the gaps identified in preliminary TDA should be updated to bring the participating countries to the same level. One of the elements to be fed into the TDA is the generation of the hydrological information on the Okavango River Basin. For this effect 5 out 12 hydrometric stations were rehabilitated in the Angolan portion of the Okavango River Basin with the financial support of the project. The rehabilitated stations entered into operation at the end of May 2006 and were handed over to the Government of Kuando Kubango province, through the Provincial Directorate of Energy and Water (DPA). Any important element linked with the TDA is the establishment of bodies like the National Coordination Units (NCU), the National Intersectoral Committees (NISC) and the Technical Task Teams (TTT), which are instrumental for the TDA exercise. Currently Angola and Namibia have set up their National Coordination Units (NCU). Namibia has also set up its National Intersectoral Committee (NISC). Members of the NISC-Angola are already nominated by their parent ministries and NISC-Angola itself is in a process to be established. Angola and Namibia have also identified their potential candidates to be part of the Technical Task Group (TTT). NCU, NISC and TTT are bodies that will facilitate the TDA work at regional level. The establishment of NCU, NISC and the nomination of candidates for the TTT in Botswana is not yet done |
| Purpose Three To facilitate the formulation of an implementable programme of joint management to address threats to the basin’s linked land and water systems |  |
| Specific Target One A Transboundary Diagnostic Analysis (TDA) | Very little progress has been made on the TDA. However, some progress has been made in relation to: a) rehabilitation of the first 5 hydrometric stations in the Angolan portion of the Okavango Basin; b) review of relevant GIS systems in all three riparian countries that recommended a framework for setting up an Okavango River Basin-wide GIS system for the project |
| Specific Target Two A Strategic Action Programme (SAP) | There is no progress in relation to the SAP. The SAP is an exercise that will take place only after the completion of the TDA. As it was mentioned above very little progress was achieved on the TDA. |

Progress achieved with project components and outputs

| COMPONENTS AND OUTPUTS | AS REPORTED BY PMU |
| --- | --- |
| Component A: Strengthened mechanisms for joint management of the ORB |
| Output A1 Expertise in the riparian countries strengthened to drive both inter-governmental and intra-governmental technical and policy initiatives in river basin planning and management for the ORB |  |
| Output A2 Basin-wide mechanisms for stakeholder participation in basin management established and tested to ensure consensus, replicability and taking to scale |  |
| Output A3 Policy, legal, institutional and human resource initiatives launched and linked to national policy reviews to co-ordinate river basin resource management approaches across the basin |  |
| Output A4 Monitoring and Evaluation Procedures for SAP implementation |  |
| Component B: Completed transboundary diagnostic analysis (TDA) |
| Output B1 Water resource assessment and analysis completed to determine hydro-environmental processes, characteristics and limits | The 5 rehabilitated hydrometric stations in the Angolan portion of the Okavango Basin entered into operation on 29 May 2006. It is expected that the new set of hydrological information to be gathered will facilitate a better interpretation (in terms of quality) of water resources available in the Basin and how water resources ca equally be used by the riparian countries. |
| Output B2 Socio-economic analysis completed to establish current and future patterns of river basin resource use and levels of demand |  |
| Output B3 Water resource and socio-economic analysis super-imposed to define environmental system limits and parameters |  |
| Output B4 Environmental assets of the ORB described and valued to structure models |  |
| Output B5 Comprehensive set of water resource alternatives for the ORB assessed to structure model scenarios and tested for replicability and taking to scale |  |
| Output B6 Water resource development and management models used to produce water resource management options |  |
| Output B7 Economic and environmental criteria produced to guide water resource planning and development decisions |  |
| Component C: SAP Formulation |
| Output C1 Technical and policy implications of joint management options evaluated | The project did not reach yet this stage. |
| Output C2 Joint management plan |  |
| Output C3 Commitments to SAP implementation defined including, policy, legal, institutional, human resource arrangements |  |
| Output C4 SAP document produced and endorsed by riparian governments through integration of outputs C1- C3 in collaborative process with basin stakeholders and SAP partners |  |
| Output C5 SAP finance mobilised in preparation for implementation |  |

# Footnotes

Pinheiro, Isidro, Gabaake Gabaake and Piet Heyns (2002) Cooperation in the Okavango River Basin: The OKACOM perspective.  Chapter 5 in Turton, Anthony (Ed) (2002)  Transboundary Rivers, Sovereignty and Development : Hydropolitical drivers in the Okavango Basin.  African Waters Issues Research Unit, Pretoria

Training course on the TDA/SAP approach in the GEF International Waters Programme  (undated)  Trainee Manual – Module 1 : Overview of the TDA/SAP Process.

Agreement between the Governments of the Republic of Angola, the Republic of Botswana and the Republic of Namibia on the Establishment of a Permanent Okavango River Basin Water Commission. 1994

Where the focus has been on post-war rehabilitation, poverty and governance

Agreement between the Governments of the Republic of Angola, the Republic of Botswana and the Republic of Namibia on the Establishment of a Permanent Okavango River Basin Water Commission. 1994

Pinheiro, Isidro, Gabaake Gabaake and Piet Heyns (2002) Cooperation in the Okavango River Basin: The OKACOM perspective.  Chapter 5 in Turton, Anthony (Ed) (2002)  Transboundary Rivers, Sovereignty and Development : Hydropolitical drivers in the Okavango Basin.  African Waters Issues Research Unit, Pretoria

Krugmann, Hartmut – CTA/Project Manager  (2005) Environmental Protection and Sustainable Management of the Okavango River Basin (EPSMO).  UNTS/RAF/010/GEF.  Inception Report, 04 April 2005

One potential partner even suggested that there should be an attempt to blend the three LogFrames.

Agreement between the Governments of the Republic of Angola, the Republic of Botswana and the Republic of Namibia on the Establishment of a Permanent Okavango River Basin Water Commission. 1994

Even to the extent that the blending of LogFrames should be considered.

The ratings will be Highly Satisfactory, Satisfactory, Marginally Satisfactory, Unsatisfactory and N/A.

# Text boxes

NCU (Angola)

NCU (Botswana)

NCU (Namibia)

PROJECT MANAGEMENT UNIT (PMU)

PROJECT  STEERING COMMITTEE (PSC)

OBSC, UNDP, FAO, PMU

OBSC

OKACOM

Cabinet (Namibia)

AAAA (A (

Cabinet (Angola)

AAAA (A (

Cabinet (Botswana)

AAAA (A (

PROJECT STEERING COMMITTEE

Govts of Angola, Botswana, Namibia thru’ 3 OKACOM Co-Chairs, UNDP, GEF and FAO

Co-Chairs : UNDP Res Rep (Angola) with the OKACOM country Commissioner on rotation

Other OKACOM members

FAO Technical Support

under PM

leadership

UNDP

Country Offices

OBSC

Technical

Advice

GOVERNANCE LEVEL

OPERATIONAL/IMPLEMENTATION LEVEL

PROJECT

MANAGEMENT

UNIT

FAO

Budget Holder

financial

reporting

NCU

Botswana

PM reports on progress

PSC provides policy and guidance

NCU

Angola

NCU

Namibia

PM coordination

Component 2

TDA

Component 1

Institution Building

OBSC

Component 3

SAP

thru’ consultant

OKACOM

Secretariat

support &

monitoring

advice &

support

financial

management

support

thru’ consultant

coordination

facilitation

technical

input with

TTT