Esenguly etrap Chekishlyar village community’s Action Plan

(2005-2010)

Ashgabat - Chekishlyar

2005

TABLE OF CONTENT

Credits	3

Brief Action Plan, village Chekishlyar	4

Introductory	9

General information about the community	10

Village history	10

Geographical and climate conditions	11

Social and economical information	12

Employment	13

Natural resources utilization	14

Social facilities	15

Chekishlyar community action plan	19

Community’s vision	19

Discovered problems and their primary reasons	20

Ways to solve problems and its priorities	25

Action Plan implementation structure and schedules	33

Necessary resources for the plan’s implementation	36

Evaluation of finance needs of community	36

Investments sources	37

Attachment 1.  Full Action Plan, village Chekishlyar Esenguly etrap, 2005-2010	38

Attachment 2.  Historical information about Chekishlyar.	40

Attachment 3.  Research conduct for composing the Action Plan for village Chekishlyar of Esenguly etrap.	41

Attachment 4.  Research summary results.	42

Attachment 5.  Cause and effect tree	58

Attachment 6. List of members of Acton Plan Execution Committee, village Chekishlyar	61

Notes	62

## Credits

With special gratitude to the Hyakimlik (local authorities) of Esenguly etrap and personally to Mr. Garmamedov Rakhman Berdyewich, village’s archin (village’s local authority office chairman) Juma Yakubow, director of municipal utilities of Esenguly etrap, Halk Wekili (people’s delegate for National Council) Amaniyaz Gylyjow, village Chekishyar’s head imam Gurban Nurmamedow, school’s teacher Tagan Nazarow, and Tacis/ IMC Team directed by David Burton, as for invaluable input into this work.

## Brief Action Plan, village Chekishlyar

| Project \ Measures | Basic Goals | Core Actions | Time | Required Resources (approx.) | Including Co-financing for Required Resources | Steakholders / Potential Partners |
| --- | --- | --- | --- | --- | --- | --- |
| Provision of potable water delivery for residents of the village, with their participation | Potable water delivery for residents of the Chekishlyar village, with their participation | Water carrier purchase Creation and implementation of water delivery and distribution system | 6 - 12 months | $15 000 | Establishing system for money gathering for maintenance of water carrier and driver’s salary, participation in water carrier purchase | Esenguly etrap Hyakimlik, Esenguly etrap Municipal Utilities Service, residents and village authorities of Chekishlyar, oil companies |
| Provision of potable water delivery for residents of the Chekishlyar village | Population’s health improvement | Preparation (construction) and restoration of facilities building Purchase and installation of equipment for sea water desalinization Creation and implantation of water distribution system’s management and maintenance with participation of local residents | 12-18 months | $20000 -$40000 depending on purification technology and purchase of supplementary equipment | Construction/preparation of facilities building, participation in equipment purchase, Establishing system for money gathering for equipment maintenance (spare parts, etc.) | Esenguly etrap Hyakimlik, Esenguly etrap Municipal Utilities Service, water facilities service and Agyzsuw enterprise, residents |
| Wells’ modernization and improvement of ground water use in Chekishlyar | Improvement of potable, domestic and irrigation water supply for village residents | Wells’ repair and modernization including water lift equipment installation where applicable etc. Implementation upon ‘pilot’ basis new technologies of fresh water lenses use Development and implementation of control system for water quality and wells’ condition with participation of local residents | 8-10 months | $8000 | Participation in implementation and partial investment into materials | Esenguly etrap Hyakimlik, Esenguly etrap Municipal Utilities Service, water facilities service and Agyzsuw enterprise, residents |
| Bakery opening in Chekishlyar village | Population provision improvement | Preparation (construction) and restoration of facilities building Purchase and installation of equipment | 6-8 months | $6000 | Participation in implementation and partial investment by community | Village’s archin |
| Repairs and opening of club-house with participation of community of Chekishlyar village | Improvement of leisure of population | Purchase and delivery of construction materials Repair works Organizing program for arrangements | 8-10 months | $5000 | Participation in implementation and partial investment | Village’s archin, Culture Department of Esenguly etrap |
| Implementation of hard waste collection system, with population’s participation | Improvement of waste collection with resident’s participation Improvement of sanitary conditions in village | Tractor with trolley purchase Appointment of responsible managers, composing schedules and introduction of waste collection system Construction of waste collection points (waste receivers) Conduct of training for waste separation | 12 months | $ 15 000 | Provision of construction materials for waste collection points Election of head responsible person for collecting funds for tractor maintenance and driver’s salary | Esenguly etrap Hyakimlik, Esenguly etrap Municipal Utilities Service, residents and village authorities of Chekishlyar |
| Introduction of liquid waste collection system, with population’s participation | Improvement of liquid waste collection with resident’s participation Improvement of sanitary conditions in village | Purchase of vehicle for liquid waste collection Driver’s selection, appointment of responsible people Preparation of waste discharge point | 12 months | $ 15 000 | Election of head responsible person, collecting funds for vehicle maintenance and driver’s salary Partial investments into equipment, if possible | Esenguly etrap Hyakimlik, Esenguly etrap Municipal Utilities Service, residents and archinlyk (village authorities) of village Chekishlyar |
| Implementation of heating system in village’s school with resident’s participation | School’s conditions improvement, with participation of residents | Construction materials purchase Installation of gas heating system in school | 9 months | $ 8 000 | Steam boiler, equipment delivery, construction materials and labor for equipment installation and gas delivery Funds collection for maintenance and support | Esenguly etrap Hyakimlik, Esenguly etrap Municipal Utilities Service, pupils’ parents |
| Establishment of sewing training workshop at village’s school | Provision of labor training for female pupils | School’s classroom restoration Equipment purchase and installation Sewing training plan development | 6 months | $ 7 000 | Construction materials and labor for classroom restoration, equipment safety protection (door, window iron bars) Reimbursement for equipment’s maintenance | Etrap’s Education Department, pupils’ parents and village authorities |
| Establishment of sewing co-operative (production association) from local seamstresses | Provision of additional income resources Provision of quality sewing service | Restoration and preparation of room(s) or building Equipment purchase and installation Training (practice) for pattern-sewing skills | 12 months | $ 5 000 – $10 000 | Construction materials and labor for room restoration, provision of room in one of private houses or building construction, private investment into equipment purchase, other investment to cover fund that is not provided by donors | Seamstresses group and their families, village’s authorities |

| Establishment of cooperative for fishing, processing and sale of fish products in Chekishlyar | Provision of additional income resources from fine-mesh fishing | Establishment of cooperative fishery with 10 or more fishing teams Purchase of equipment for fishing improvement (sounding-lead, boats, fishing nets etc.) Purchase and installation of fish storage (freezer) and processing (smoke-shed) Smoking and other processing methods, training for participants Establishment of marketing links for production sale | Up to 20 months | $ 25 000 – $ 160 000 (if foreign experts are involved) | Provision of room; repair and preparation works for installation of processing equipment Partial funding for equipment purchase Input for cooperative establishment and structure defining | Village’s archinlyk, Fishing Inspectors, Balkanbalyk Association, fisher’s teams and their families’ representatives |
| --- | --- | --- | --- | --- | --- | --- |
| Establishment of fish storage facility (freezer) with participation of local residents | Fishery income improvement for local community | Repair and preparation of room for storage facility Freezer purchase and installation Development and establishment of work process, utilization and maintenance of facility | Up to 5 months | $ 5 000 + (depending of freezer capacity) | Room provision for freezer, repair and preparation works Funds collection or service fee payment for storage facility upkeep | Village’s archinlyk, Fishing Inspectors, Balkanbalyk Association, fisher’s teams and their families’ representatives |
| Small size fish growing farm establishment | Alternative income resources provision Decrease of fishing load on Caspian sea bio-resources | Methods selection and project development Fish growing construction and creation of fishery ponds on seacoast - additional Equipment purchase and installation Fish growing training | Up to 20 months | $20 000 + (depending on process capacity and number of farms) | Provision of rooms, material and labor for repair and preparation works, partial funding for works and equipment purchase Training may be conducted by LLC RIF in frames of other projects | Village’s archinlyk, Fishing Inspectors, LLC RIF, Balkanbalyk Association, fisher’s teams and their families’ representatives |
| Establishment of credit fund for small businesses creation by village residents | Funds provision for small businesses establishments | Fund collection Responsible people appointment and coordination of loan portfolio and other issues Business basis and planning training | 9 months | $ 5 000 – $10 000 ( depending of fund size) | Partial provision of funding (around $1000) Training may be provided by USAID PRAGMA project trainers | Village’s archinlyk (village authorities), residents, USAID PRAGMA, Balkan branch of Entrepreneurs Union, local banks |

| Establishment of boat repair workshop (with store) | Boat repair service and spare parts provision for fishers | Repair and preparation works Equipment and spare parts start kits purchase Spare parts network and pricelist creation Entrepreneurship training | 12 months | $ 7 000 – $10 000 | Room provision and expenses covering for preparation and repair works Partial investment into equipment and spare parts purchase | Fishers of Esenguly and Chekishlyar villages |
| --- | --- | --- | --- | --- | --- | --- |
| Non-irrigation agricultural production development in North part of Chekishlyar village | Alternative income resources development for local residents | Melons and vegetables growing training for local residents New seeds and small tools for growing provision | 12 months | $ 3000-5000 | Labor provision, tools partial funding, management support for training and hosting professionals | Desert Institute, agricultural advisors, village’s residents |
| Chekishlyar village Telephone network modernization | Improvement of living conditions for residents | Installation of telephone lines in village Repair of existing telephone station | 12 months | $5000-10,000 | Labor provision, partial funding for materials Local authorities: telegraph polls, materials | Esenguly etrap Hyakimlik, local Turkmentelecom branch |
| Paramedical service point establishment in Chekishlyar village | Provision of medical and first aid service | Permit authorization from Health Care Department Room preparation Equipment purchase Work schedules and payment development, nurse training | 12 months | $7000 | Room provision and preparation (room redecoration) | Esenguly etrap hospital, local gengeshi, Esenguly Art School |
| Kindergarten establishment in Chekishlyar village | Provision of children care and development in pre-school period Residents’ living conditions improvement | Permit authorization (licensing) for establishment Facility (building) repair Furniture and children care equipment repair | 12 months | $3000-7000 depending on quantity of furniture and equipment | Building provision, it’s repair (partial funding), authorization and payment for license, further functioning support | Local authorities, local social provision department, Esenguly etrap hospital |
| Computer training class and resources center establishment in Chekishlyar school | Provision of training for computer skills to youth Local residents’ access to information and information technologies | Room repair, eclectic power distribution works Computer and office appliances purchase, delivery and installation Training courses establishment | 10 months | $ 5000-8000 | Room provision and repair, electric power distribution funding | Local authorities, Education department of Esenguly etrap, Chekishlyar village school’s management |

| Beauty shop establishment in Chekishlyar village | Provision of service for male and female residents Service for newly-weds | Rooms’ repair and preparation Equipment purchase and installation | 10months | $ 3000-5000 | Rooms’ provision and repair, partial funding for purchase | Local archinlyk (village authorities) |
| --- | --- | --- | --- | --- | --- | --- |

## Introductory

This plan is developed upon Tacis/IMC Caspian Coastal Communities’ Sustainable project implementation, aimed to assist development of coastal communities and decrease of its impact on biological resources of Caspian Sea.

Seacoast population development is priority task of the Strategic Action Plan, adopted by Caspian region countries as an attachment to Caspian Framework Convention, signed and ratified by Turkmenistan.

Development of this plan is one of the components of the project for coastal communities’ strengthening, which provides assistance for communities’ sustainable development.  The plan elaboration work contained actual conditions research and detection of community’s leaders, conducting trainings and seminars for stable development, conducting research based on PRA methods (participatory rural appraisal), further processing of gained information and the mutual plan development.

Stable rural regions development is also a priority goal for social and economic development of the country, which is referred to in national state programs, including National Action Plan for Nature Protection and National Caspian Action Plan.  Improvement of living conditions and income increase, including salaries, is also one of priorities of the strategy for social and economic development of Turkmenistan until year 2020.

In frames of accepted programs of the country, implementation of the project for sustainable development of the Caspian region communities, this plan is proposing measures for development of Chekishlyar village (Esenguly etrap) community by improvement of living conditions, small business enterprises’ establishment and improved use of natural resources.

## General information about the community

### Village history

There is no known date of birth of the village.  Historians and Russian explorers (from the end of Middle Age to 18th century) found this village as large and only sea-port center in South-East region of Caspian Sea, where brisk trade of salt and oil in exchange for flour and other goods was taking place.  According to local elders, in near standing village Aulbazar was a large market place.  There are assumptions about prisoners of war exchange that took place here; between Turkmen nomads and Iranians (which were captured during forays).

When Russian army disembarked and moved toward inner land of Turkmenistan in the end of 19th century, this port gained strategic importance.  From that time till the mid of 20th century, Chekishlyar had large pier.  Ships from Astrakhan were visiting the port for exchange of fish for flour and other necessary goods.

In 30th of the last century, there was a carpet co-operative established and opened in the village.  It is still in operation and provides job for 28 members of the village’s community.  I present time this co-operative is part of the carpet factory in Esenguly village, which is famous for its high quality carpet production among alike in the country.

Around the village, the boundary line of the Khazar Nature Reserve (in past – Esenguly Reserve), which did not cause obstacles to local residents for growing vegetables, melons and gourds on land around houses and melleks (land plots).

In the middle 1950th, fishers were gathered into fishery co-operative, provided with large boats for fishing, and there was large size refrigerator for fish installed.  Fish resources were in satisfying condition for daily fishing at that time, therefore this co-operative was flourishing.  In the middle 90th, the enterprise was closed and since that time fishers are occupied with fishing privately.

### Geographical and climate conditions

Village Chekishlyar is located to the North from the etrap center Esenguly,

37.61 degrees of latitude and 53.93 degrees of longitude, in Southern part of Turkmen section of Caspian Sea.

The village is a part of Esenguly etrap, and it has its own local authority institution – gengeshi, or village’s council.  Village is governed by archin and his deputy, who is responsible for secretary work.

Climate in village is considered as mild comparing to other regions of Turkmenistan.  Year average temperature is 16oC, which is the highest index from whole country’s Caspian seacoast.  Also, the largest yearly rainfall (up to 212 mm in average) is recorded here.  At the same time, there are much less winds here, comparing to other seacoast regions of the country, which makes this region more humid and mild in terms of climate (Table 1).

There is no open water sources in the village, except to the sea water.  There are 6 wells in the village, among which only two are in operation and rest are salinized.  Water from these wells is used for technical purposes, irrigation and livestock.  There are thin sweet water underground lenses to the north from the village.  Water in these aquifers is potable, but because of its small size and low level of recovery, these wells are not used for drinking.

Table 1: Climate data in Chekishlyar region

| Index/Months | I | II | III | IV | V | VI | VII | VIII | IX | X | XI | XII | Year |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Rainfall yield, mm | 20 | 24 | 30 | 21 | 15 | 10 | 9 | 9 | 15 | 20 | 26 | 25 | 212 |
| Average monthly and yearly air temperature, centigrade | 4,0 | 5,5 | 8,8 | 14,4 | 20,0 | 24,2 | 26,9 | 27,3 | 23,9 | 17,5 | 10,8 | 5,9 | 15,8 |
| Average monthly and yearly relative humidity, % | 80 | 76 | 75 | 72 | 68 | 65 | 69 | 69 | 66 | 68 | 72 | 79 | 72 |

Beside those wells, there is a well in 2 km to the South from the village, which provides low saline water. This and other utilized wells require rehabilitation and cleaning (see Enclosure 3).

According to elders, in the beginning of the last century there was big garden to the north from the village; where there were unique brands trees grown.  For instance, one of fig brands is called “Chekishlyar”. According to official historical records, all forests of Esenguly region were located as one ‘West-Chekishlyar forestry” 565 thousand square hectares large, out of which 108 thousand hectares are covered by forest.

Sea level changes generally effecting roads and water conditions in Chekishlyar.  Floods were more frequent in the end of 19th – beginning of 20th century and caused much inconvenience; but at the present time they happen rarely and last time they were recorded in 50th.  Most of houses in the village are built on piles.

### Social and economical information

In time when research was conducted, the population of the village with its satellite village Aulbazar was 1,380 people, among which 52% were women and 48% were men.  Villager’s age diagram is presented in Table 1.

According to conducted research, 75% of residents have an average income, around 5% - reach and 20% have low level of income and life.  This is while ‘wealthy’ is defined by number of family members working for oil industry or government and have regular monthly salary (family is considered as reach if two members have such a job).  Other index for being wealthy is possession of large number of cattle (more then 10 camels and 1 cow).

If there is one member of family working, and family possess few cattle and mellek (land plot), family is considered as medium size income.  Lowest income (or poorest) families defined as if there is no one of members getting regular salary, family that have disabled members and no more than 1 cow, camel or other cattle.

### Employment

In present time, there are 280 people from the village who work officially (21% of population).

Historically, the main source of income for village’s population was fishing and hunting.  After closing down fishery in the 90th, and because of oil and gas extraction field development in 12 km to the North from village (Keymir deposit) and further to the North (Akpatlauk, Okarem, Kamyshlydja), oil and gas industry became the main employer for villagers.  In present time, there is opening of branch of Nebitdag Oil Drilling Works and other oil companies planned in the village.

Other important employment source is government institutions.  At present time there are 28 residents of the village working for the government.  Additional income provision source are salaries of those employed by municipal service institutions.  At present, there are 25 village’s residents employed in these institutions.  Both of these sources provide income monthly and therefore considered as stable and reliable.

Following by importance income sources are fishing, small size farming and trade/commerce. Approximate structure of population’s employment is given in diagram 2.

### Natural resources utilization

Natural resources are considered as basis sources for income, and include natural biological (fish, wild fowl) and agricultural resources.

Biological resources include fish that is catch in all year seasons, and waterfowl, which is shot mostly in winter. Biological resources provide food practically for all families of Chekishlyar. See enclosure 2 and attachment 4 for diagrams of biological resources utilization.

Agricultural income resource is cattle, which is possessed by practically each family (100 camels, 2,500 sheep and few cows as reported by local authority) and growing vegetables and other plants.

After cattle murrain in the beginning of 90th, village residents hold mostly camels and small cattle.

Cultivation is carried out in the North part of Chekishlyar and in 1 km to the North from Aulbazar village, where there are unofficially occupied farmer fields located. This is territory of Esenguly part of Khazar Preserve (10 hectares field assigned for Gyzyl-Etrek Experimental Station). These fields are used by farmers from Chekishlyar and Esenguly for growing grapes, figs, melons and watermelons, some vegetables and other fruit trees.  For cultivation, non-irrigation method is used (see enclosure 3).

### Social facilities

There are 300 pupils school in the village.  Also, there is medical care house facilitated by one doctor and one nurse.  There is Culture House with small library and small mosque supervised by imam.

In the South part of the village there is border guard military unit, guarding coastal waters.

There is also radio-television transmission booth with antenna 353 meters high, serving for amplifying television and radio signals.

Planning process description

Planning process contained the following stages:

General research and information collection was carried out in frames of measures for TACIS grant program support.  Main goal of grant program support was to reveal potential projects aimed to improve community’s life conditions, and to increase its capabilities.  Beside this, there was assistance provided for agricultural projects, where there was local residents’ lack of knowledge.  Upon these activities, there was information about coastal communities collected; preliminary evaluations of its conditions were conducted, as well as evaluations of their main difficulties and possible solutions.  Implementation method included semi lattice interview and brainstorming for detection of problems and solutions.

Detection of leadership potential in communities and work with leaders was aimed to reveal potential leaders in communities; which could be involved in further work in the project frames.  For this purpose, the expert visited the village, who conducted semi structured interview with the village residents to discover potential leaders of community.  As result, there were three persons defined and they were involved in seminars’ and researches’ conduct.  Same people were invited to participate in programs for potential enhancement of leaders and facilitators, which were carried out upon programs for technical assistance by other donors.

Research process preparation included administration and organizing measures in general.  There was planning seminar conducted with participation of 20 activists from the community, where they were introduced to the sustainable development concept and action planning process for stable development.  The plan of research conducting was composed jointly by project team and local leaders and activists, responsible people from community’s members were appointed, and schedules and place of research were defined.

Measures for action plan preparation

Planning measures were aimed to involve local residents into community’s action plan preparation, including determining basis social and economical difficulties and ways to resolve them, historical tendencies in natural resources use, etc.  To conduct the research, the “Participatory rural appraisal” method was used. It was made during three days in local school and Culture House with participation of five project professionals and three local activists (potential leaders of community).  List of conducted researches and brief research outcomes’ overview is given in Attachments 3 and 4.

After preparation of first version of the plan, public discussions were carried out, where the plan and practical issues for its implementation were discussed.  Leaders, activists, local authority members and community members participated in those discussions.  As result, corrections for the action plan were prepared and collected, required measures were finally defined, and priorities for community’s actions were chosen.

## Chekishlyar community action plan

### Community’s vision

Residents of Chekishlyar envision community’s future as with improved ecological conditions of environment around the village, stable social development of the village and improvement of social and economical conditions of community’s members.  To achieve this, community’s members are ready to work mutually, increasing potential for resolving community’s problems.

Improvement of environment conditions is at first depended to sea fish population recovery.  Community believes that in future, there must be fish enough to cover its demand and demand of future generations.

As for village, community envisions Chekishlyar as oasis, where there are gardens planted.  According to elders, in past there were lots of fruit trees growing in the village, making it green as garden.

Village’s social condition improvement, first of all is related to social sphere of life and social services.  Community envisions village with paved streets, clean, where there is fuel filling station, and functioning kindergarten. There are improved conditions in local school; including gym and heating system.

Personal economical and social conditions improvement is related to existence of new enterprises and service, according with community members’ vision.  They include small bakery, fish smoking workshop for fish production processing, and sewing workshop.  Village will be fully provided with dairy and other food production.

### Discovered problems and their primary reasons

Conducted work revealed problems and urgent issues in the village, which can be divided by the following categories:

Problems related to environmental conditions of the village

    - Problem of water supply for drinking and technical needs is major problem for the whole Caspian region of Turkmenistan. In Chekishlyar it is redoubled by absence of surface and lack of ground water sources (see Attachment 4).

At present time community depends on the following sources of water:

      - Water purification facilities in Esenguly (16 km to the South from  Chekishlyar) were build to supply two villages with water, but because of lack of transportation means (there is no water carrier in the village) and low production outcome, these facilities can not cover the demand for water.  Besides this, local residents consider chemical which are used in these facilities for processing as unhealthy.

      - Local wells, allowing utilizing fresh water aquifers, which are numerous in this region, can not cover the demand of drinking water because of low outcome, also because of lack of studies and application of primitive technologies.

      - Rain water is traditionally used in 80% of families, which collect rain water from roofs of houses with help of gutters and large capacity storage tanks.  Only limit for using this source is that there is small rainfall in summer time.

      - Other water sources including purification facilities, installed at oil and gas enterprises.

Primary root problems are absence of adequate water delivery, absence of ground water extraction technologies, and absence of local water purification facilities.

Primary reasons: Primary reasons for lack of water supply are absence of system of fund collection for investments, weak community organization, and absence of technical support for studying and utilization of existing ground water sources.

    - Another problem that was defined by community, is decrease of fish population and related to it decreases of income from fishing.

According to community members’ opinion, practically all households have access to sea and fishing, which provides up to 70% of income (see enclosure 2).

Although sea fish population (and fish catch, accordingly) is continually decreasing because of problems of the Caspian Sea, population of fine-mesh fish in sea is directly depended on water presence in Atrek river during sponging time.  For instance, in years 1998 and 2004 and even in 2005, water discharge increase in river led to rapid fine-mesh fish catching growth (vobla, sazan).  Also, fishers are interested in fish breeding, but they do not have knowledge and experience in this area.

    - Absence of waste management system, mainly for hard waste, worsens sanitary epidemiological conditions around the village and inside it.  A present time, large fields around the village are covered with hard waste. Primary reasons for this situation are absence of funds for waste vehicle’s purchase, absence of waste management system and weak knowledge by residents.  Same picture is observed with liquid waste, where because of absence of technical facilities lavatory pits are filled and not cleaned for long time.

Social and Economical problems of the village

    - Unemployment, presence of unemployed community members, usually young people.  Although there are some jobs in oil companies around the village, the lack of jobs for young people is very worrying factor for the community members. Although there is no official statistics, local authorities in the village estimate 200 to 300 unemployed people (excluding women).  Most of women are occupied with household and home business, thus they are not considered as unemployed.  In their free time, they make carpets, which allow them to have small income (see Attachment 4).

Basis primary problems are low level of professional skills, insufficient development of local business and absence of support for private business in the village.  Low level of professional skills is caused by absents of labor training in school and absence of training education institutions.  Beside this, girls and young women are not allowed to travel to other towns for getting labor training (for instance, in Turkmenbashy).

Insufficient business development is another reason for unemployment in the village.  It is, at first, related to lack of funds for starting capital for commerce business and lack of knowledge for business organizing and establishing.

    - Agricultural business insufficient development causes insufficient supply of vegetable product and insufficient livestock breeding.  Main primary reasons for lack of agricultural business are lack of drinking water for cattle and lack of forage, which has to be delivered from reach agricultural regions.  Lack of drinking water, caused by failure and salinization of wells suppresses camel and other cattle breeding.

Primary reasons for lack of cultivation are lack of irrigation water, absence of tractors for more intensive cultivation in broader fields, and lack of knowledge about cultivation.  Absence of access to seeds and chemicals (fertilizers etc.) on one hand makes agricultural production ecologically pure, on other hand it keeps it on low level.

    - Fishery management problems.  Because of high dependence level on sea resources, whole population is worried about difficulties related to fishing.  Fishers consider weak fishery service infrastructure and lack of storage system, fish processing and marketing as primary problems.

At present time, fishers purchase boats’ and motors’ spare parts, nets and other fishing equipment in neighboring Iran or in Turkmenbashy town (400 km away).  Absence of spare parts shop and repair workshop in the village is related to lack of spare part provision system, lack of funds for business and possibly small quantity of potential clients.  By mains of the same reasons, there is no boat and motors’ repair shop in the village; fishers carry out repair works on expensive motors themselves.  Because there is no aluminum welding machine, boat repair is considered as practically impossible.

Other problem is fish processing and sale.  Because of increase of water in Atrek River during flood periods in 2004 and 2005, the fine-mesh fish (vobla, sazan) catches were increased sufficiently.  As there is no storage facility, prices for this fish dropped to 2,000-3,000 manat per kilo, which decreased fishers’ income significantly.  Fish processing is carried out traditionally, by pickling and drying fish in open air.  Lack of adequate marketing, new equipment and new technologies knowledge causes fishers not to utilize fish smoking and sale fish as fresh.  Weak community’s organization and lack of funds for equipment purchase are primary reasons for low income from fishing.

Community’s social life condition’s problems

    - Lack of developed business infrastructure, including numerous social services for the village.  Life conditions’ level is significantly lowered because there is no access to social services.  Absent services are: sewing workshop, hairdressers, wedding hall.  These problems related directly to community members’ lack of business skills, lack of starting funds and lack of professional training.

    - There are other problems related to the daily life of community, which cause discomfort and difficulties, including:

      - Absence of paved streets in the village which causes transportation difficulties in winter time.  Only a third part of the main road through the village is paved with asphalt-concrete.

      - Absence of regular transport to the regional center Esenguly (16 km) and Balkanabat town (250 km).  Village depends only on its own transport; one bus provided by regional auto park and is often under repair.

      - Medical aid post in the village does not provide coverage for population’s demand in medical service, particularly in medicinal procedures.  Its personnel are not always accessible and residents experience lack of trust to them, which causes them to appeal for medicinal service to other community’s members which obtain medical education.  Last ones do not possess proper rooms and equipment for carrying out medicinal procedures.

    - Social problems related to the village school, which was built in first half of the last century.  For several decades, there was no restoration of its building done, there is not heating which causes children ill in winter time.  More then 50% of children do not come to the school during winter months.

Lack of professional training in the school is one of primary reasons for business insufficient development, low employment level among young people and other problems.

Other problems related to the school are lack of educational literature, absence of gym and facilities for supplying pupils with drinking water.

### Ways to solve problems and its priorities

Solutions for listed above problems may be grouped in three main directions (objectives).

Objective 1: Village social life improvement by involvement of all residents to solve its problems

Life conditions including access to water, electricity, communication and other services determine common weal and population’s life level, which is one of the most important aspects of development. In Chekishlyar life conditions are not corresponding to modern village life standards.  Community’s members are ready to participate in solving this problem.  It is expected that life conditions level, sanitary hygienic conditions and potential of solving its problems will grow.

Main measures for improvement include organizing uninterrupted water supply by establishment of delivery system, existing water sources’ modernization and establishment of village’s own drinking water production facilities.  Other measures are establishment of waste management system (hard and liquid), kindergarten, telephone communication modernization, streets paving etc.

Objective 1:   Village social life improvement by involvement of all residents to solve its problems

Expected implementation activities as fulfilled until year 2010:

-  Village’s residents are fully supplied with water for drinking and technical needs from various sources

-  Sanitary hygienic situation in the village is improved; waste management system is in function

- Social life conditions in the village are improved: school obtains higher functioning conditions; telephone communication system is modernized, roads are built; village club, new medicinal aid post and kindergarten are opened and functioning.

| Project \ Measures |  | Basic Goals |  | Project’s Term |  | Expected results |
| --- | --- | --- | --- | --- | --- | --- |
| Provision of potable water delivery for residents of the village, with their participation |  | Provision of potable water delivery for residents of the Chekishlyar village, with their participation |  | 6-10 months |  | At least 80% of population have access to delivered water at reasonable price Community controls water delivery and it’s fair distribution by mains of water management system |
| Provision of potable water delivery for residents of the Chekishlyar village |  | Population’s health improvement |  | 12-18 months |  | Village’s residents possess their own reliable drinking water source Community controls and manages the system of delivery including maintenance/support |
| Wells’ modernization and utilization of ground water improvement measures in Chekishlyar village |  | Improvement of potable, technical and irrigation water supply for village residents |  | 8-10 months |  | Aquifers and utilization possibilities are studied All functioning wells in the village and around it are repaired and work Water supply for technical, irrigation use and cattle is improved |
| Introduction of liquid waste collection system, with population’s participation |  | Improvement of liquid waste collection with resident’s participation Improvement of sanitary conditions in village |  | 12 months |  | Sanitary conditions in the village are improved Liquid waste management system is established with participation of community Community manages liquid waste disposal process |
| Chekishlyar village Telephone network modernization |  | Improvement of living conditions for residents |  | 12 months |  | Telephone station is installed and functioning Residents have access to telephone lines |
| Paramedical aid post establishment in Chekishlyar village |  | Provision of medical and first aid service |  | 12 months |  | Medical service is improved in the village All residents of the village have access to improved medical service |
| Implementation of heating system in village’s school with resident’s participation |  | School’s conditions improvement, with participation of residents |  | 9 months |  | School functioning in winter time is improved significantly Children sickness rate is decreased School attendance in winter time is improved |
| Chekishlyar school’s restoration with participation of residents |  | School functioning condition’s improvement, with participation of local residents |  | 10-12 months |  | School studying conditions are improved Children sickness rate is decreased |
| Road improvement in Chekishlyar |  | Life level improvement |  | 10-18 months |  | Passenger and cargo transportation conditions are improved (especially in winter time) |
| Establishment of kindergarten in Chekishlyar |  | Provision of children care and development in pre-school period Residents’ living conditions improvement |  | 12 months |  | Preschool children’s’ care is improved |
| Restoration and opening of social club with participation of community of Chekishlyar village |  | Improvement of leisure of population |  | 10 months |  | Access possibility for children, youth and other residents There is place for conduct public arrangements, celebrations etc. |

Objective 2: Community’s economical potential growth by mains of small business development

Although it is possible to consider Chekishlyar as successful in terms of employment because presence of oil and gas companies in region and accessibility to sea resources, population of village still experience difficulties because of unemployment rate. Lack of professional skills training limits employment possibilities for male residents of the village.  Traditional mentality, lack of transportation mains and funding, and absence of training facilities in the village makes young women in the village suffer from lack of employment as well.

Therefore Chekishlyar community envisions solution to this problem in developing other income sources by establishing new services and businesses, and by organizing training for youth.  One of solutions for young women is establishment of sewing workshop as alternative for hard and labor-intensive carpet making.  Establishment of professional training and opening of resource center may provide skills in information technologies and other skills for youth.

New income sources development will also lead life level in the village to grow, as number of offered services will increase.  For instance, establishing new bakery, hairdressers and other businesses will cause creation of new services for the village residents.  Creation of loan fund for establishment of small business is planned, which will allow residents to open new businesses.

Objective 2:   Community’s economical potential growth through small business development

Expected implementation activities as fulfilled until year 2010:

- Conditions for establishment of new businesses are improved in Chekishlyar, including business management training, improvement of professional skills of youth and existence of finance resources

- Part of population occupied with small business is grown, and dependence on natural resources and other traditional income sources is decreased

- Life conditions in the village improved as there are new services offered

| Project \ Measures |  | Basic Goals |  | Project’s Term |  | Expected results |
| --- | --- | --- | --- | --- | --- | --- |
| Bakery establishment in Chekishlyar |  | Provision for population improvement |  | 6-8 months |  | Bakery for baking bread with capacity at least 300 loafs a day is opened Demand for bred in the village is fully covered |
| Establishment of sewing training workshop in the village’s school |  | Provision of professional raining for the village’s girls |  | 6 months |  | Girls have access to professional skills training for dress-making and sewing Women population’s income increase |
| Sewing co-operative establishment with employment of local seamstresses |  | Provision of alternating income sources Provision of quality sewing service |  | 12 months |  | Employment and stable income sources increase Demand for sewing production and modeling services is fully covered |
| Village’s residents small business fund creation |  | Provision of loan funds for establishment of small business |  | 9 months |  | Residents have access to funding for creation of new business or other income sources Business management knowledge improved Village’s economy is developing by mains of opened new small businesses |
| Establishment of beauty shop in Chekishlyar |  | Provision of service for men and women New-weds services for wedding preparation |  | 10 months |  | Men and women have access to beauty shop service |
| Establishment of computer class and resource center in Chekishlyar school |  | Provision of computer skills training to youth Residents’ access to information and information technologies |  | 10 months |  | Computer training courses are opened for school pupils and residents Residents have access to information technologies Employment and access to higher education are grown |

Objective 3:  Fishing development and sustainable use of other natural resources

Utilization of natural resources is basis for villagers’ life support.  In present time, residents significantly depend on sea resources, especially fish.

Therefore fishing, fish processing and marketing, and introduction of fish breeding technologies are aimed to increase income at keeping catch level or even lowering it.  Establishment of fishing co-operative that will utilize fine-mesh fishing is planned.  Co-operative will employ 10 to 20 fishers who will possess necessary equipment and will be trained to use modern catch technologies, full processing cycle and developed marketing network for fish realization.  As this business will grow, there will be more members employed and stable income work provided for youth.

Agricultural business development including cultivation of vegetable, fruit and melons with utilization of sprayless irrigation technologies may cause residents’ income growth and provide occupation, at the same time providing vegetables and fruits for village’s demand.  Utilization of modern irrigation technologies (dripping irrigation etc.), introduction of modern cultivation methods and modern seed materials will allow knowledge growth and provide alternating income source, as well as growth of income from existing production.

Objective 3:   Fishing development and stable utilization of other natural resources

Expected implementation activities as fulfilled until year 2010:

-	Fine-mesh fishery co-operative established and functioning, with employment of stable biological resources utilization

-	In the village and around it, there are vegetables and fruits grown for village’s demand and provision additional income

- 	Village fishers possess infrastructure for effective fishing management

| Project \ Measures |  | Basic Goals |  | Project’s Term |  | Expected results |
| --- | --- | --- | --- | --- | --- | --- |
| Establishment of co-operative for fishing, processing and sale of fishery production in village Chekishlyar |  | Provision of additional income resources from fine-mesh fishing |  | 20 months |  | Income increased for at least 10 fishers and their families, because of stable utilizing of fish resources including fine-mesh fishing and fish processing Provision of at leas 6 work places at fish processing facilities Sturgeon catch declined on account of increase from fine-mesh catch and fish processing income |
| Establishment of fish storage facility (freezer) with participation of local residents |  | Fishery income improvement |  | 5 months |  | Income increase through the possibility to freeze and store fresh fish, for at least 20 fishers and their family members Job provided for at least 4 community’s members |
| Small size fish growing farm establishment |  | Alternative income resources provision Decrease of fishing load on Caspian sea bio-resources |  | 20 months |  | On piloting basis, small farm for fine-mesh fish and sturgeon breeding is developed in coastal waters At least 2 families will gain stable income from fish growing and sale At least 20 community’s member will learn methods for fish growing |
| Establishment of boat repair workshop (with store) |  | Boat repair service and spare parts provision for fishers |  | 12 months |  | Provision of boat and motor spare parts is improved Safety of sea fishing is improved Stable income for at least 2 families is provided |
| Agricultural production establishments development with non-irrigation technologies in North part of Chekishlyar village |  | Alternative income resources development for local residents |  | 12 months |  | Provision of alternative income sources for village’s residents Provision for vegetables and fruits demand in the village |

### Action Plan implementation structure and schedules

For implementation of action plan in Chekishlyar, community organized a committee from main leaders of community, who will monitor implementation of action plan, control projects execution and represent community in negotiations with donors and other organizations.  On behalf of whole community, this group will meet once in three months to discuss current situation, project support and make conclusions for further development of community.

Projects and measures upon action plan will be carried out personally by leaders and responsible people from community, who will be considered as project leaders.  Execution committee will create monitoring group from two members, which will monitor projects’ implementation on community’s behalf.  Results of this monitoring will be reported during execution committee meetings.  Upon those results execution committee will make conclusions about further projects’ works and offer support from community.

Whole community will conduct meetings yearly, where execution committee will report about development plan and propose changes.  Action plan implementation structure is given in diagram 3.

Community of Chekishlyar village plans to complete the plan until year 2010.  In preparation process there were priorities defined for measures’ implementation.  Basic priorities’ directions considered as the following: water supply improvement projects and waste management. School’s heating system modernization and establishment of medical aid post are also considered as high priority projects.  Among the projects aimed to increase income, bakery establishment and sewing training workshop defined as of high priority.

Measures’ implementation yearly schedules in accordance with community’s activists are given in table 2.

Table 2:   Measures of village Chekishlyar Action plan yearly schedules

2006

Implementation of heating system in village’s school with resident’s participation

Introduction of hard waste collection system, with population’s participation

Paramedical aid post establishment in Chekishlyar village

Establishment of sewing training workshop at village’s school

Chekishlyar village Telephone network modernization

Computer training class and resources center establishment in Chekishlyar school

Chekishlyar school restoration with participation of community

Establishment of fund for small businesses creation by village residents

Establishment of co-operative for fishing, processing and sale of fishery production in village Chekishlyar

Establishment of fish storage facility (freezer) with participation of local residents

Provision of potable water delivery for residents of the village, with their participation

2007

Bakery opening in Chekishlyar village

Provision of potable water delivery for residents of the village

Wells modernization and utilization of aquifers improvement in Chekishlyar

Restoration and opening of social club with participation of community of Chekishlyar village

Small size fish growing farm establishment

2008

Agricultural business development with utilization of traditional sprayless irrigation technologies in the North part of Chekishlyar village

Kindergarten establishment in Chekishlyar village

Beauty shop establishment in Chekishlyar village

Roads improvement in Chekishlyar

Establishment of boat repair workshop (with store)

2009

Establishment of sewing co-operative (production association) from local seamstresses

Introduction of fluid waste collection system, with population’s participation

## Necessary resources for the plan’s implementation

### Evaluation of finance needs of community

Each project was evaluated in terms of possible expenses upon proposed measures.  Beside that, discussions with community’s representatives were carried out, inputs/investments from community and from other steakholders.

Whole necessary for the plan implementation sum is estimated as 7,875,000,000 manats (estimation based on prices’ records by Sep. 1, 2005).  Projects’ implementation costs vary from 125,000,000 to 1,750,000,000 manats, 340,000,000 manats in average for each measure.  Most costly are projects where there is requirement to invest into equipment purchase (water supply project) or where there is foreign expertise is to be engaged (fishers co-operative establishment); less costly are projects for social services and existing infrastructure repair; least costly are projects providing new service (bakery, beauty shop and other)

According with action plan, there are following schedules of investments for its implementation by years:

2006	 	3,850,000,000 manats

2007	 	2,350,000,000

2008	 	1,100,000,000

2009	 	200,000,000

2010	 	375,000,000

Main part of investments, almost 80% of whole value is consumed during first two years of action plan implementation.  During this period, most important objectives must be achieved, including water delivery and hard waste management system, school’s repair and establishment of sewing training workshop.

### Investments sources

Chekishlyar community is ready to propose input, including money, for achieving community’s objectives. It is ready to create institutions and cover

systems’ functioning support.  Actual community’s investment (as on Sept. 1, 2005) is 2,375,000 manats, which is 30% of expenses for action plan measures.    Input includes offering rooms and construction where it is required, repair and preparation works, and covering expenses for functioning.

At the same time, Chekishlyar community is in support need for equipment purchase and other large investments.  This is related to purchase of vehicles for water delivery and waste transportation, water purification equipment, training for fish co-operative workers and other large investments.  Description of community’s investment and required resources is given in the Attachment 1.

## Attachment 1:   Full Action Plan, village Chekishlyar Esenguly etrap, 2005-2010.

## Attachment 2:   Historical information about Chekishlyar.

From Astrabad Sea Station Director’s report about Turkmen of the South-East coast of the Caspian Sea and their household and lives

May 6, 1859

...5) Village Chekishlyar is located in 15 versts to the North from Gasan-Guly village, almost on the coast.  There are 200 or more yurts (households); residents are occupied with fishing and salt trade, as well as other small goods trade.  Boats from this village are almost never going for piracy, because Turkmen know their {village’s} disadvantageous location: in case of punishment, rowing boats may approach by cannon-shot because of deep coastal waters there.  Climate there is considered as even better than in Gasan-Guly, and soil is fair, and Turkmen grow melons, watermelons and other {plants}…

Russian-Turkmen relationships in 18-19 centuries (before annexation of Turkmenistan to Russia), Archive Documents Collection, Science Academy of Turkmen SSR, Ashgabat, 1963

From book of V. A. Tugan-Mirza-Baranovskiy “Russian in Akhal-Teke, year 1879”

...

Chekishlyar, small village of Turkmen-yomuds, located in southern part of east coast of the Caspian Sea, from 1871 had small number of yurts, its residents together with residents of neighboring villages were occupied mainly by piracy along the Persian coast.

....

Coast, on which Chekishlyar is locates, is extremely bad.  Often, during strong storms with wind from sea its large part is flooded.  According to elders, there was big flood in 1855 which covered land as far as 17 versts.

Soil in Chekishlyar and around it is of loose coarse sand, mixed with small sea shell mass; somewhere there are quite large salt-marshes.  Everywhere one fastens his eyes, there is not a single plant and this is causing depressing impression on person who is not adapted to such environment; monographic brown-black color irritates nerves.  Chekishyar’s surrounding is somber - there is greenish-blue sea from one side and sand desert from another.  Only height, White Hill, is located in 12 km to the north from fortification; this is quite high (about 300 feet) lime hill, considered in past as border sign between Russia and Persia.

## Attachment 3:   Research conduct for composing the Action Plan for village Chekishlyar of Esenguly etrap.

PRA Conduction Plan

Conduction term:  April, 23-25, 2005

Women – 2 groups 15-20 persons each

    - Historical outline

    - Income -  round diagram

    - Problems gallery

    - “We can” diagram

    - Welfare level research

    - Objective’s ranking – pare analysis matrix

    - Cause-and-effect tree examination

    - Brain storm  – alternative ways to solve problems (criteria matrix)

Men – Fishers – 2 groups 15-20 persons each

- Problems gallery

- Pare analysis matrix

- Daily schedules

- Round diagrams – income sources (dependency on bio-resources, to determine potential sources for future income)

- Occupation calendar for fishers

- Location’s map

- Tendencies diagram – 1990 – 2005 (to determine tendency in fish catch and hunting) – interviewing about causes

- Exposure of alternative solutions to problems.

- Community’s vision for the future / alternative income sources

Young Women – 1 group 20 persons

- Problems gallery

- “We can” diagram

- Cause-and-effect tree

- Daily schedules

Young People – 1 group 20 persons

- PRA results discussion

- Revealing alternative solutions for problems

Village’s School Activists – 1 group 5 persons

- Problems gallery

- Revealing alternative solutions for problems

- Heating problem solutions matrix by criteria

## Attachment 4:   Research summary results.

Report 1

Community: village Chekishlyar, Esenguly etrap, Balkan velayat

Method: “Historical outline”

Analysts: women group, 15 persons from 30 to 57 years old.

Employment: Tree women work for carpet co-operative (Esenguly), rest are jobless (housewives)

Discoveries:

| Years 1935-1938 |
| --- |
| There was international sea port in Chekishlyar. Work places. Ships from Astrakhan exchanges flour for fish and other goods. Natural products. Beginning of intensive barter between neighboring villages. | Lack of drinking water. Water is delivered from remote wells around the village. |
| 1938-39 Establishment of carpet co-operative, this is functioning till now. There are 27 members in it. |  |
| Thirties |
| Began to occupy melleks (land plots) for growing melons and watermelons, utilizing land aside protected preserve zone. |  |
| Abundance of fish, population’s demand for it is fully covered. |  |
| Years 41-45 |
| Once in half a year ship arrives which collected catch fish and distributed coupons for cooking oil and flour. | Resources mobilization for WW II. |
| Fifties |
| Purchased ships and established collective farm, which built 4 water storages | Lack of drinking water. Water is excavated from remote wells; also coupons for water were distributed (1 coupon in exchange for 3 buckets of water). |
| 1990s |
| Water storages are not used since 1990 as water was delivered by trucks. One water truck was ordered for 4 families. | Water storages wearied out and became useless. |
| 1990 – Water trucks number increase in Esenguly. | Cattle plague occurred in neighboring villages. Provision of milk decreased. |
| 1993 |
| Gasification of village. |  |
| 2001 – 2002 |
|  | Medical workers decline. |
| Establishment of small shops. |  |
| Barter exchange intensified. |  |
|  | Fishing farms broke apart. Unemployment is grown. |
| 2005 |
|  | Medical workers and teachers decline. |
| Dress sewing and embroidery always provided good income. |  |

Conclusions:

- From the moment of village’s birth until now problem of lack of water is actual.  During 30th water problem was solved by women who delivered it from remote wells.  In 50th, water from water collectors was distributed by coupons.  Today 70% of population possesses personal collectors and systems of rain water collection from roofs.  Since ninetieth, in cases of lack of water, residents buy water in addition from water desalinating facilities in Esenguly; sometime four families will pool in money for 1 water truck.  There is a problem with water delivery: from April until August each year, residents have to wait their turn in line for water.  Mr. Garaja, Chekishlyar resident, possesses his own water truck.

- Residents cultivate melons and watermelons since the thirties on their owned melleks (land plots); they do not cultivate other plants because of lack of water for irrigation.  Melleks are usually located nearby houses. Water is located in small aquifers 2 meters deep and therefore is of various qualities.

- 1938-39.  Carpet co-operative is established, which is working still.

- This co-operative plays significant role in women’s life, as it provides jobs (payment guaranteed for each waved carpet) for many of them.  Home-workers deliver carpets to this co-operative, which in turn provides threads, estimates carpet’s value and sells it.  But salary in co-operative is delayed from 3 to 6 months. Women mentioned that waving carpets is recouping business and it is not profitable for women to sell their carpets themselves.

- In ninetieth, there was cattle plague.  Since that time its number is not restored, which negatively effects milk production supply for the village.

- There are representatives of the Maslakhat (National Council) of Turkmenistan in the village.

Report 2

Method: “Problems gallery”

Analysts: group of women from 15 persons from 30 to 57 years old.

Discovered problems’ groups:

| - Lack of water for drinking and technical purposes | 8 |
| --- | --- |
| - Unemployment (lack of jobs) for population | 10 |
| - Absence of kindergarten in the village | 1 |
| - Critical shortage of water delivery trucks | 1 |
| - Necessity for additional medical service post | 2 |
| - Medical workers shortage | 1 |
| - Necessity for establishment of sewing co-operative in the village | 1 |
| - Private doctor service necessity | 1 |
| - Difficulties in organizing small business | 1 |
| - Absence of heating system in the village’s school | 3 |

Conclusions:

- There are many unresolved social living problems in the community (10 are named);

- Most of vote (by 10) was given to the problem shortage of jobs in the village. Women envision solution for this problem in establishing enterprise for sewing services like one that exists already.  They noted that there are large orders for sewing possible (school aprons etc. – opinions about such orders are divided; some shared opinion that it is impossible to get such orders)

- Community already has tried to solve problem of absent kindergarten.  They composed appeal letter to Hyakimlik (local authorities), which responded that village is too small for such establishment, therefore it is not expedient.  At the same time, women say that they do not have permanent jobs and money to afford kindergarten fees.

- Many desire to start small commerce business, but do not have capital to start it.

- Problem of the first importance is water provision.  There are two ways water is provided for the village:

1)  By mains of water collectors that provide rain water for drinking, which is collected in special reservoirs for water storage (howuz).  Many households have per 2 such collectors.   According to women, 70% of households do possess such system.  Only 30% do not have this system and water reservoirs.

2) When collected water is not enough, residents purchase water delivered from Esenguly by water truck (each truck delivery costs 100 thousand mantas). Water is then transferred to the garden pools (howuz).

Water from desalination facilities in Esenguly delivered untimely, for there is big line; if water is delivered from berth, its cost rises to 230 thousand manats per truck (according to residents, Esenguly desalination facilities’ capacity is not enough in dry period of the year).

Water consumption by households varies and depends on number of family member, livestock and melleks.  Howuzes are filled in 3-4 times a year.

Moreover, water provision issue is seasonal.  In the period from February to April (rainy period), water consumed without limits because of significant refill of collected rain water.   From May to August, strict limitation of water consumption is required.  At this period, lack of water is sensed in whole etrap because of insufficient capacity of desalination facilities in Esenguly, also because water delivery to Chekishlyar turns only after demand for water in Esenguly and surrounding inhabited places is met.

According to unanimous opinion of analysts, this problem may be solved only if water truck for community’s own needs is purchased; but question lack of money for water purchase is still unresolved.

- Women expressed displeasure about medical service level in the village.  Schedules and scope of existing medical post do not meet resident’s needs; therefore they often have to appeal for medical care to persons who practice medical activities home privately.  These people carry out medical care not in dedicated for medical purpose rooms and without a license.  Therefore establishment of new medical care post in the village is welcomed.

Report 3

Method: “Round diagrams” Income.

Analysts: group of women from 15 persons from 30 to 57 years old.

Discovered facts:

Rejepbibi:   2 adults and 4 children in family.

Income:

- Carpet waving in co-operative

- Husband’s salary

- Small commerce

- mellek (land plot) for family’s vegetable consumption (melons)

Amanbibi:  2 adults and 5 children in family.

Husband is disabled.

Income:

- private fishing

- carpet waving

- mellek (land plot)

Arazbibi: 2 adults and 3 children in family.

Income:

- salary

- carpet waving

Conclusions:

- Diagram analysis revealed that regular income such as salary is most reliable and stable income source, which is exceeding all other income sources value in percentage;

- Income from carpet waving may serve as alternative stable income source, but only if it comes from work in co-operative;

- Private fishing allows population supporting minimum living wage, but because of few objective reasons does not promote sufficient wealth growth.

- Expenditure diagrams from all respondents were about the same, showing that around 50% of family income is spent on food, around 35% is spent on cloths, and around 25% is spent for water and other technical needs.

Report - 4

Method: “We can...”

Analysts: group of women from 10 to 12 persons, 32 to 55 years old.

Employment: 1- works in kindergarten in Esenguly, 2 – work in co-operative, rest is housewives.

We can:

By efforts of whole community collect required funds and purchase village’s water truck.

We influence (on):

Establishing of the sewing co-operative in the village.  In case if room is offered and required equipment and materials are purchased, co-operative workers can significantly increase professional skills via experience exchange and additional training aimed to meet demand from potential customers.

We can not:

Have influence on unemployment problem, establishment of kindergarten and new medical care post.

Conclusions:

- During discussion, facilitators focused on the fact that existing community’s potential allows it to solve partly some of discovered problems.  But for community’s active members’ mobilization presence of leaders is important, who will promote organizing and process advance.   Obvious absence of such leaders, as well as absence of mutual discussing practice and solution finding for actual issues seems customary for this community.

Report 5

Method: “Chekishlyar community’s Wealth level research”

Analysts: group of women from 10 to 12 persons, 32 to 55 years old.

Process:

Facilitators asked the following question: what is percentage of low, medium and high income families in the village, and what defines those levels?

After brief discussion, analysts determined following proportions:

- Low income level households: 20%

- Medium income level households – 75%

- High income level households –  up to 5%.

Definition “high level” covers households where there is more than 1 member worked for government, family possesses good house, up to 10 camels, small shop, car etc.

“Middle level” definition covers families were there is at least one member works for government, family possesses 1 or 2 camels, 1 cow, mellek (land plot) etc.

“Low level” – families where there is no regular income, no or small number of cattle, some members are dependants (disabled, pensioners and orphans).

Discoveries:

- Chekishlyar households are subdivided by low (20%), medium (75%) and high (5%) levels of income.

- Reasons that prevent active wealth growth are lack of drinking and technical water, unemployment, fishing decrease and difficulties in fish production realization.

Method: “Reasons tree”.

Analysts: group of women from 10 to 12 persons, 32 to 55 years old.

Discoveries:

Women did highlight the following reasons:

* Everyone tries to solve his problems on his own.  There isn’t mutually taken solutions.

* There isn’t activist who would gather people and propose creation/collection of funds for the village’s water truck.

* This is serious problem.

* People do not want to pay for water.

Report 6

Group 1:  Young women

Analysts:  20 young women from 18 to 30 years old.

Method: Problems gallery

Information according to analysts:

-  Age categories:

18 - 20 years old – 13 persons;

21 - 25 – 5 persons

26 - 30 – 1 person

Over 30 – 1 person

-  employed: 2 work for carpet waving co-operative, rest are occupied with private carpet waving and dress sewing

-   Family status: all single

-   Education: 5 – are trained as seamstresses, 1 – bookkeeper; 4 –

Bakers, rest – school certificates

They revealed the following problems:

- Absence of sewing workshop – 18

- Absence of bakery  - 5

- Absence of beauty shop  (for brides, hairdresser) - 4

- There is no place for free time, there is no Culture House - 2

- Unemployment – 7

- No work for bookkeeper - 1

- There is no access to paramedical education  - 1

- Parents do not allow girls leave for education if this requires leaving the village.

Conclusions:

Single girls from traditional Turkmen families are not allowed to leave for education; therefore most girls are not educated for labor.  Most of them have studied in school only.

- By vote, young women named absence of sewing workshop in the village as most important problem.

- 4 women want to open bakery, but they do not have equipment for this (mixers, dough -mixers, pastry moulds etc.).  Because of bakery absence in the village, villagers have to travel to Esenguly (25 km away) for bakery products purchase.   During summer time transportation, these products are getting smashed, and creams are melting.

- In their daily lives, young women are occupied by the following:

1) Carpet waving,

2) Embroidery,

3) Dress making, household managing (cattle, house cleaning etc.).

- All earned money (income) they give to their family budget

- Two last problems were not common and considered as subjective (they were told by 2 women).

- Most women are occupied with hard carpet waving, which (according to their opinion) delivers insignificant income.  Monthly, 1 girl makes about 2 square meters of carpet, for which she is paid about 800 thousand manats.  Carpet waving is considered as hard labor by women, and they would rather occupy themselves with dress making considering is easier work than waving.

Method: “We can”.

Process: It was proposed to women to analyze the following problems, subdivided into three categories:

| We can solve problem ourselves | We can influence solution for problem | We can do nothing |
| --- | --- | --- |
| Bakery at home | Absence of sewing workshop | No jobs. |
|  | Absence of beauty shop | Parents do not allow girls to leave for education |

Conclusions:

- After discussion, women decided that they may resolve problem of absence of bakery workshop themselves, if they start baking cakes at home and thus create their permanent clients.

- There is strong opinion among women that sewing workshop will allow them to have good income.

- Most of women want to study, but they can’t because their parents do not let them leave the village, providing that they have no money for education and there are no jobs anyway even if women obtain professional education.

- Women’ self-esteem is low and they are diffident

- Employment perspective is defined only as working in sewing workshop.  They consider that there are many potential customers for such service in Chekishlyar.  At present time, many villagers order dress in sewing co-operative in Esenguly, because professional level of seamstresses in their own village does not meet their requirements.

Method: Detection of reasons for “sewing workshop absence”

Discoveries:

- There are 11 young women in the village who are occupied with dress making, having different professional level.

Reasons:

- Absence of modern sewing machines with various functions.

- Absence of room for sewing workshop, which does not allow clients to know working schedules and location.

- Low sewing quality (many women try to learn sewing themselves, there is no sewing master who would organize work and teach seamstresses).

Conclusions:

-  There are about 11 young women (younger than 25) occupied with dress making on professional basis (getting paid for this).  Only 6 from them can perform all operations for dress making (cutting, sewing, embroidery, embroidery attaching).  Rest of women can do only few of these operations.

- Women sew at their homes, using old sewing machines.

- Prior to holidays (Nowruz, Gurban-bairam etc.) there are many orders, but because women are not able to fulfill them, clients travel to order to Esenguly.

- Women proposed their vision of sewing co-operative:  no more than 11 women with different professional skills level will gather in special room and work there.  Each woman will serve one client, making dress from dress cutting to finishing. Collective will elect their master who will direct the work and if necessary, teach women.  If possible, they want to be occupied with dress modeling as well.

- Young women want to unite their efforts do they can purchase modern sewing machines with various functions and offer more various services to clients, which will provide possibility for higher pay.  Clients will know the location of the co-operative and women may keep services’ price at one level, but no higher than in Esenguly.

- Women assume that they may make national dress, school aprons (prior to September 1st), and they will look for potential orders.

Method: Daily routine: Gulkhumar – dressmaker, earns certificate, performs all functions for dress making

Discoveries:

8.00 – Breakfast (she is not occupied with household)

Begin to sew at sewing machine (accomplishing orders)

13.00 – Lunch

Until 19.00 is working (sewing)

19.00 – Dinner

20.00 – Stroll with girlfriends

She is working without weekends and able to make 25 to 30 dresses a month.  During holidays, she works about 16-18 hours a day because of abundance of orders.  She makes about 1 million 200 thousand manats a month.  During holidays, she can make so much in a week.

Conclusions:

- Gulkhumar is good example for female villagers in terms of showing how to make good money by dress making.

- Her monthly income is higher than that of women who are occupied with carpet waving.  At the same time, dress making is considered as less hard work than carpet waving.

- She has desire to teach young women to make dress (cutting and sewing).  She would like to learn dress modeling herself.

Method: Daily routine: Gyzylgul – home waver

Discoveries:

Daily routine (Gyzylgul, 18, single, jobless):

6.30 – Namaz (prayer)

Until 12.00 she starts working at loom, waving carpet

12.30 to 15.00 – Lunch

Until 19.00 – waves carpet

19.30 – 22.00 – Working at loom

Conclusions:

- Works at waving loom about 8 to 12 hours a day.

Report 7

School’s community:

Analysts: 5 persons, men, teachers and parents.

Method: Problems gallery.

Process: facilitator proposed to participants to tell about problems in village’s school. Analists were active.

Discoveries: Analists told the following problems:

- Absence of heating

- School wasn’t repaired for long time

- There is no canteen in the school

- Window frames are very old and could not be opened

- Absence of graphic study aids

- Absence of gym

- Lots of garbage around the school

- Drinking water problem – there is one large water tank supplying drinking water and one cup, used by all children.

Conclusions:

- Absence of heating is considered by analysts as most actual problem

- At the present time, school’s community tries to solve this problem, but in vain. Situation: there is small stove connected to flue in each classroom that is stoked by wood and coal.  Trees are practically absent in Chekishlyar, and is not delivered anymore from CIS countries.  Parents bring old planks but it is not enough to keep rooms heated.  There are stokers in the school; they stoke stoves once a day.  But fire goes off in 1 hour, and then there is no heating.  Thus the temperature in classrooms in winter time is only 3 to 5 centigrade above zero.  When the weather is cold, teachers are forced to dismiss junior classes home.  In the cold time, around 50% of pupils are absent.

Method: Criteria matrix.

| Problem’s solution variants | price | Health safety | Utilization durability | Implementation reality | Scores |
| --- | --- | --- | --- | --- | --- |
| Gas | 4 | 3 | 4 | 4 | 15 |
| Steam | 3 | 4 | 2 | 2 | 11 |
| Electric | 1 | 2 | 3 | 3 | 6 |
| Stoves | 2 | 1 | 1 | 1 | 5 |

Conclusions:

- installation of electric heaters is very expensive, because wiring in the school is old and was not repaired for last 30 years, thus creating high fire hazard.

- Steam heating variant is more attractive.  But it will not serve long because of pipe corrosion (wet climate and salt soil and water cause high corrosion from outside and inside pipe).  In few years pipes become worthless.

- Most attractive variant is gas heating – gas feeder pipe is crossing the school’s territory, and for the school, gas utilization is free.  But there is risk that gas heating will be prohibited from installation in public edifices.  Yet such a system is installed in the Health Care House and in school in neighboring village.   Tagandurdy Nazarov proposed to study this issue.  He is going to appeal to local deputy and hyakim and obtain official permission for gas heating installation in the school.  Variant: to design steam heating system the ways that will maximally depress corrosion (for instance, use fresh water and insulate pipes); it may be possible to install distillation equipment in the school.  In winter time, it may work to cover school needs, and in summer time it may be used to profit residents)

- Amanniyaz, people’s deputy, chairman of Esenguly Municipal Facilities Services, is also willing to join in efforts to solve this problem.  He proposes installation of steam boiler with heating capacity 1000 square meters.  He shared opinion that gas heaters of “Erge” type installation is permitted.  500 meters of pipe collectors d32-50 are required, as well as d20К (it was not defined how much).   Municipal Facilities Services Enterprise may provide 2 welders for welding pipes.

- Input/investment from parents is not discussed, but it may become the project’s part.

Report 8

Community’s name: village Chekishlyar, Esenguly etrap, Balkan velayat.

Analysts: 12 men – fishers and hunters

Method’s name: Problems gallery.

Discoveries: Analysts discovered the following problems:

- Lack of drinking water

- Absence of conditions for fish storage

- Absence fish processing facilities

- Difficulties with realization of wild fowl

- Absence of cleanliness/infestation

- Absence of trucks for removal of liquid waste from toilet pits

- Lack of spare parts for boat motors

- Absence of repair infrastructure

- Absence of fishery shop

- Absence of welding equipment and materials

Conclusions:

- There is no water distribution network in the village

- Water in functioning wells is not suitable for drinking because of high salinity level

- When new well are dug, they give good quality water, but with time they become salty

- Residents utilize rain water for drinking, which is collected from roofs with help of water trays into covered pools (lars) where it is stored.

- Not all residents possess such a system

- Used for technical purposes (and partly for drinking) water is delivered by water delivery trucks from Esenguly water desalination facilities

- Water delivery truck do not provide timely delivery, also each truck of water costs 100 thousand manats

- In average, each household in the village spends 100 thousand manta for water delivery

- Some fishers possess their own refrigerators for fish catch storage

- Large capacity refrigerators are expensive, therefore it is not profitable to by such refrigerators for private use

- Many fishers store their catch in Esenguly village’s refrigerator; this service is provided for a certain fee.  This refrigerator is the leftover from fishery collective farm

- Because of absence of conditions for long period storage, fishers are forced to sell their catch at lowest price season (sometime they are paid 2 thousand manats for a kilo of fine-mesh fish)

- Fishers use traditional methods for fish processing (salting, pickling) and practically do not use smoking

- Wild fowl is sold for small price on local marked in most of the time

- Infestation of the village is actual social problem for its residents

- There is not system for waste collection and disposal

- Absolutely whole population in the village is using toilet pits

- Because of absence of technical mains, toilet pits are overfilled, and liquid waste is not transported for disposal for long time

- Because of absence of stock and repair infrastructure, fishers have demand for boat motors’ spare parts  boat repair specialists

- Fishers are forced to purchase fishing gear and equipment from Iranians of abroad from Esenguly etrap, mainly in Turkmenbashy.

- Motors’ repair is carried out by fishers themselves

- For boats’ repair and other works, there are no welding materials, equipment and specialists

- Fishers do not believe in own potential to resolve these problems

Report 9

Community’s name: village Chekishlyar, Esenguly etrap, Balkan velayat.

Group: fishers and hunters

Analysts: 12 men – fishers and hunters

Method’s name: Pare matrix analysis.

Discoveries:

Using pares analysis method, the following list of priorities was delivered (1st place is most important):

- Lack of drinking water

- Absence of conditions for fish storage

- Absence of conditions for fish processing

- Difficulties with realization of wild fowl

- Absence of cleanliness/infestation

- Absence of trucks for removal of liquid waste from toilet pits

- Lack of spare parts for boat motors

- Absence of repair infrastructure

- Absence of fishery shop

- Absence of welding equipment and materials

Pare Analysis Matrix

|  | Lack of drinking water | Absence of conditions for fish storage | Absence of conditions for fish processing | Difficulties with realization of wild fowl | Absence of cleanliness/infestation | Absence of trucks for removal of liquid waste from toilet pits | Lack of spare parts for boat motors | Absence of repair infrastructure | Absence of fishery shop | Absence of welding equipment and materials | G | L |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Lack of drinking water |  | water | water | water | water | water | water | water | water | water | 9 | 1 |
| Absence of conditions for fish storage |  |  | storage | storage | storage | storage | spare parts | storage | shop | storage | 6 | 3 |
| Absence of conditions for fish processing |  |  |  | processing | processing | processing | spare parts | processing | shop | processing | 5 | 4 |
| Difficulties with realization of wild fowl |  |  |  |  | waste | toilet | spare parts | wild fowl | shop | Weldi-ng | 1 | 7 |
| Absence of cleanliness/infestation |  |  |  |  |  | toilet | waste | waste | shop | Weldi-ng | 3 | 6 |
| Absence of trucks for removal of liquid waste from toilet pits |  |  |  |  |  |  | spare parts | toilet | shop | Weldi-ng | 3 | 6 |
| Lack of spare parts for boat motors |  |  |  |  |  |  |  | spare parts | shop | spare parts | 6 | 3 |
| Absence of repair infrastructure |  |  |  |  |  |  |  |  | shop | Weldi-ng | 0 | 7 |
| Absence of fishery shop |  |  |  |  |  |  |  |  |  | shop | 8 | 2 |
| Absence of welding equipment and materials |  |  |  |  |  |  |  |  |  |  | 4 | 5 |

Conclusions:

- Participants believe that most actual problem in the village is lack of drinking water, which is caused by limited of natural fresh water sources and absence of fresh water delivery system from Esenguly desalination facilities

- There is necessity to introduce water utilization system based on self-funding and self-management

- In accordance with fish catch tendencies, it is necessary to establish fish storage and processing infrastructure

- Fishers see Caspian Sea as source that will allow them to provide income for their families, thus problems related to fishery are the main ones.

Report 10

Young men group

Ages:

From 15 to 20 years old – 0 persons;

21-25 – 15 persons

26-30 – 2 persons

Over 30 – 3 persons

In total there were 20 men.

Method: Daily routine:

Analyst: Rowshan, 26, jobless.

5.30 -7: waking up,

Before 8: breakfast; takes food provision and goes to river.

From 9 to 16.00: straightens nets if they are entangled, and catch fish.

After 16.00: straightens nets, returns home (if nets are not entangled, he returns home at 12.00). Late return from fishing may depend on boat failure; if so, towboat is employed; this causes later return.

After 16.00: works on mellek (land plot), where he grows melons and water melons.  Half of harvest goes to cover boat’s repair.

From 19.00 to 20.00: dinner.

20.30: meets with friends.

20.30 – 21.00: goes to sleep.

Rowshan possesses 4 camels in livestock.

Conclusions:

- Young people that do not have permanent jobs are occupied with fishing on Atrek River or in sea for about 4 to 8 hours a day.

- In good weather they go fishing every day, even in weekends.  They do not fish in bad weather.

Method: Daily routine: (23, works every second day in NGDU).

7: waking up

8-9: breakfast

10.00: going to fish on river.

12.00 – 16.00: returns from fishing.

After 18.00: watching TV

23.00: goes to sleep.

Report 11

Community’s name: village Chekishlyar, Esenguly etrap, Balkan velayat.

Group: fishers and hunters

Analysts: 12 men – fishers and hunters

Method’s name: Round diagram, income.

Discoveries:

Conclusions:

- Main income sources for households (particularly households, as respondents provided that several families are in close relationship and share their budget) of village are fishing, salary from oil companies, government and entrepreneurship

- Wealth of many households is directly dependant on the sea natural resources

- Employment by oil companies is limited by lo professional level

- Income level from sea resources vary depending on nature conditions and availability of sea resources

- Difference of income from sea in various households related to boats and fishing equipment availability, as well as storage and processing facilities

- Occupied in oil business and working for government people are practically not occupied with fishing

- Average age of those that are occupied with fishing is from 20 to 45 years

- In many cases, processing and storage is carried out by fishers themselves

- There is simple fish realization system in the village, processing is done by traditional methods

- Fish with caviar catches significantly increase level of income

- Entrepreneurship is mainly presented by small commerce/trade activities

Report 11

Community’s name: village Chekishlyar, Esenguly etrap, Balkan velayat.

Group: first group of fishers and hunters

Analysts: 12 men – fishers and hunters

Method’s name: occupation calendar.

Discoveries:

| Activities | Months |
| --- | --- |
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |
| Fishing | 10 | 12 | 20 | 24 | 24 | 15 | 15 | 15 | 18 | 23 | 10 | 10 |
| Fishing catch (1-low 10 high) | 10 | 10 | 10 | 10 | 9 | 5 | 5 | 5 | 7 | 7 | 7 | 10 |
| Hunting | 8 | 8 | 4 | - | - | - | - | - | - | 3 | 4 | 8 |
| Wild fowl (1-low 10 high) | 10 | 10 | 1 | - | - | - | - | - | - | 1 | 5 | 10 |

Conclusions:

- Occupation in fishing and hunting is directly dependant on natural conditions

- Fishing is much bigger occupation comparing to hunting

- Most of fishing days are in spring, late fall and early winter time

- Fish catches are biggest in winter time

- Not like hunting, fishing is taking place during whole year

- Residents practically do not hunt in spring and summer time

Report 12

Community’s name: village Chekishlyar, Esenguly etrap, Balkan velayat.

Group: fishers and hunters

Analysts: 12 men – fishers and hunters

Method’s name: Map of location

Discoveries:

- Village is located near the sea coast line

- There is paved with asphalt road going to the etrap center (20 km)

- There is one main street in the village, paved with asphalt half only; rest of streets are unpaved

- There are only three social facilities buildings in the village: school for 300 pupils, built in first half of 20th century, medical aid post, and club; all located near the village’s gengeslik (local authorities headquarters)

- At the school, there are football and basketball squares that require repair

- There is small musk in the center of village, where elders are gathering

- In southern part of the village there is 300 meters high tower used mainly for amplifying radio and TV signals

- All houses in the village are provided with gas and electricity

- There are 6 wells in the village, 3 in southern and 3 in northern parts of the village; only two of them (one on each site) are in function

- Near wells, there are cultivated lands, where olive, fig, grapes are grown.  Local traditional technology for irrigation with utilization of underground aquifers is used

- There are about little more than 10 trees in the village, most of them are old

- There is concrete pool with diameter about 3-4 meters and 2.5 meters deep located to the south-east form the village (around 200 meters away from sea coast; nearby there is pipe that delivers sea water for desalination).

- In 7 km to the north from Chekishlyar there is well; in the past time water was coming onto surface itself and it was used for cattle; today it is plugged with waste.

Conclusions:

- Because of lack of water, it is impossible to grow water consuming plants;

- Residents know well the location, wells and roads’ condition

- Residents envision potential in developing of cultivation with utilization of sprayless and dripping irrigation systems and in sheep breeding

- Provision of gas and electricity allows potential development of industrial processing

- Village suffers from lack of vegetables and other plants production.  Part of villagers possess melleks (land plots), where they grow plants for own consumption that do not require lots of water (melons, watermelons) and grapes.  There was fruit garden near (around 200 years ago).  Today there are few trees left there, one of them is 100 years old and its harvest yield is 1000 kg of fruits (it is well adapted to the local conditions).  Rejep Nazarov, activist of community, tried to plant fig trees and various apple sorts’ trees.  He uses water for irrigation from the well he dug himself on the territory of his garden.

Local residents would like to grow vegetables, tomatoes and cucumbers, but they need water and knowledge for this.  Positive cultivation experience examples are absent (lack of experience).

Problems:

- Lack of water for drinking purposes, irrigation and cattle

- Infestation of the village’s territory

- Existing medical care post does not meet population’s demand for medical service

- Absence of heating in the school

- Absence of social leisure places for young people

- Wells need repair

Local population’s values:

- Residents prefer fishing in the sea and in Atrek River as occupation, because they want quick and big profit.

- They live in line with the following principle: “the sea provides quick profit (it will always feed us); it is not possible to become wealthy by it”

- They love visitors and do not assume they can get any profit from them.

Treatment of tourism:

Chekishlyar is located in border zone; therefore tourism development is practically impossible.  There are tourists coming here in summer time.  Local residents assume they are guests (friends, friends of friends).  They are warmly welcomed in peoples’ homes and they are not charged for anything.  Residents do not assume possible income sources from tourists.

Group of people interested in learning technologies of aquaculture cultivation:

- Nazarov Tagandurdy Kotdurdyevitch, house 5 (teacher)

- Khomujanov Bazar

- Nazarov Rejep. (Only person in the village who grows figs)

- Rowshan

Preferences:

- Fish breeding in small pools (sturgeon, sea-roach, and vobla)

- Cultivation (fruit trees gardening)

- Treatment of crayfish breeding: local residents do not eat crayfish, but they are ready to breed it in pools if guaranteed wholesale will be established.

## Attachment 5.  Cause and effect tree

## Attachment 6

## List of members of Acton Plan Execution Committee, village Chekishlyar

- Archin Yakubov J.,

- Imam Nurmamedow G.,

- Elders Counsel Representative Yakubov

- Gurbanniyazov Annaberdy,

- Saparglyjowa R.,

- Khotjanowa A.,

- Gurbanmamedow N.

Monitoring Group members list

- Imam Nurmamedow G. (execution monitoring)

- Elders Counsel Representative Yakubov (finance control)

## Notes

# Endnotes

Turkmenistan.  National Coast Profile, Report, Caspian Ecological Program, Ashgabat, 2000

Turkmen SSR, Materials about regions’ economies.  Published by Institute of Economical Research for State Development Plan of Turkmen SSR, SDP TSSR, Institute of Economical Research, Moscow, 1937

Further only Chekishlyar name will be used to cover both Chekishlyar and Aulbazar villages.

There is opinion among local social specialists, that refusal to let girls leave for education is pretext; real reason is absence of funds required for education.

Public discussions of the action plan in Chekishlyar village with participation of local activists, community’s leaders and representatives of local authorities, July 21, 2005, Chekishlyar village, Esenguly etrap.

# Text boxes

Enclosure 1

Village name (Chekishlyar) history

There are few versions for village’s name origin.  Most popular legend provides that this village was famous for boat craftsmen, whose hammer knocking sound was heard far beyond village’s bounds.  This is where the village’s name (Çikiç işleýär) from, which means ‘the hammer is working’.

Other version provides that in the village’s port which existed until 20th century, there was waterway channel, along which haulers were pulling boats, and berth overseer was shouting ‘Çek!’ (pull).

Diagram 1:  Age by population index

0%

20%

40%

60%

80%

0-16

16-62

62+

Age group

Population percentage

Chekishlyar village

Aulbazar village

Diagram 2: Population’s employment

Officially employed

(salary)

19%

37%

Pensioners

7%

Residents under employment age

37%

Fishers and other unofficially working people and jobless people

Enclosure 2

Dependence on sea resources

Evaluation of people occupied by fishing varies depending on the source of information.  According to official information, only 90 residents are fishers, most likely those who worked for closed fishery farm on large vessels.  Quantity of fishers defined as at least 350 men, i.e. in average one man from each family.

Women consider that fishing provides from 50 to 70% of family income.  In average, each fisher spends 250 days year fishing.  Largest catch is taken in winter months.  Sturgeon is fish, considered as providing mainly income; it is catch by fishing nets and hooks. Fine-mesh coastal fishing is also popular, but it is used mostly as direct food source. Catches are from 10 to 100 kg per day, achieving highest level in winter and spring time.

Other sea related income source is wild waterfowl, basically migrating and wintering birds; hunting is done only in period from October to March.  Practically all fishers hunt also and spent around 35 day a year for it.  Residents consider income from hunting as in significant and use birds for food.

Enclosure 3

Water and cultivation in Chekishlyar

Sweet water aquifers presence is recorded even in the middle 19th century.  At that time, population of Chekishlyar and Esenguly utilized water from wells in Chekishlyar.  When Russian troops disembarked in the end of 19th century, lack of water provision for them has occurred and soon this water source became salty and useless.

In 30-50th of the last century, there was water purification facility built and put in operation in the regional center Esenguly, and used steam condensing method for sea water desalting.  Water was delivered to Chekishlyar from Esenguly and sold by coupons (10 Soviet Kopek (cent) in exchange for 1 coupon; 1 coupon served to purchase 3 buckets (30 liters) of water).  In the beginning of 90th there was sea water purification facility built which used return osmonic method for water purification.

It is discovered that fresh water aquifers are located along the whole Turkmenistan part of the Caspian Sea coast, including part from Esenguly to Okarem, Cheleken peninsula, Gyzylsuw island, from the North Gyianly to Karsy village.  Aquifers’ depth is defined as 1.5 to 2 meters.  There is clay layer located at this depth 20 centimeters thick, which suppresses deeper aquifer’s water evaporation.  Water in dug wells is of small capacity and soon becomes salty.

Local residents use sprayless technology for growing, with utilization of fresh water aquifers for watering.  Technology described as following: in large fields, soil is excavated down to 2 meters deep, for loosening clay layer; then it is filled with manure and covered with watered sand, into which the seeds planted.  By utilization of this method, grapes, olive, melons, fig and other fruit trees are grown.  Vegetables’ (tomatoes, cucumbers etc.) growing is possible but requires additional watering from wells.

At present moment there are 25 fields for cultivation located on territory of Esenguly part of the Khazar Preserve, each from few hundred to few thousand square meters large.  Provision of technical assistance for such income source was impossible until recent time because of the Preserve Zone status, but there was official permission for cultivation on these fields.

Enclosure 4.  Priority problems in Chekishlyar village

All residents consider problem of drinking water supply as most urgent and pressing, which must be solved as soon as possible.   Further on details, opinions of members are divided.

Women consider that unemployment, absence of adequate medicinal service and absence of heating system in the school are core problems of the village residents.

Men envision problems related to fishing as most important; as for village’s general social life conditions, problem of waste is called a priority problem.

Young women consider absence of sewing workshop as most important, followed by unemployment and lack of bakery.  Young men point out unemployment and lack of water for cattle.

Diagram 3:  Chekishlyar Action Plan implementation structure

Action Plan

Execution Committee:

Execution Committee

monitoring group:

Action

Plan

Project 3

(responsible person 3)

Chekishlyar Community

control

Implementation

Support

Project 1

(responsible person 1)

Project 2

(responsible person 2)

Local authorities

(Archin, Hyakimlik

Esenguly

etrap)

International

Donors

Local donors

(oil companies etc.)

Finance

and other support

fishing

Carpet

waving

mellek

salary

Carpet

waving

## Seasonal fishing diagram

## Seasonal hunting diagram

Lack of water

Insufficient provision

of water from

purification

facilities in Esenguly

Lack of

Natural sources

Of water (wells)

Lack of transportation

For water delivery

Insufficient

productivity

Absence of

Distribution

system

Absence of

Private vehicles

For water

delivery

Absence of

Water purification

facilities

Lack of own

funds

Community’s

Weak

organization

Lack of mains

Absence of waste

Management system

Lack of support

(maintenance) for

equipment

Insufficient

Knowledge of

aquifers

Technology

Primitivism

Lack of technical

Support for

Aquifers’ study

Lack of funds

For purchase

Absence of

Local budget

Insufficient

Specialists’

Training

Spare parts’

bad provision

Infestation of the village

Absence of hard waste

Management system

Absence of liquid waste

Management system

Population’s

Weak

organization

Lack of

funding

Lack of

Funds collection

system

Absence of

Vehicle/tractor

For waste collection

And transportation

Management

Structure

absence

Lack of

Information

For residents

Lack of special

Truck

For waste collection

Fishing Resources Decline

Fine-mesh fish resources

decline

Lack of

Water in

Atrek River

Sturgeon fish resources

decline

Atrek River water

Resources’ share with

Iran is not defined

Absence of technologies

And knowledge for

Breeding fine-mesh

fish

Lack of funds

For organizing

Absence of fish breeding

base

General problems

Of the Caspian Sea

Unemployment

Undeveloped

business

Low professional

Skills level

Lack of funds

For starting

The commerce

business

Undeveloped

Loan service

From banks

Community’s

Weak

Organization

Small number

Of population

Lack of

Professional

Training in

The school

Financial aid

lack

Girls are not

Allowed to leave

For education

Absence of

population

owned Funds

Strong traditional

Mentality

Lack of

Knowledge about

Establishing small

businesses

Lack of

Professional

Training

institutions

Decline of income from fishing

Fishers’ service

weak

infrastructure

Absence of

Fish

processing

Absence of

Proper

technologies

Absence of proper

Marketing network

Lack of

knowledge

Lack of knowledge

About packing and

sale

Absence of processing

equipment

Decline of

Fish resources

(see diagram 2)

Absence of

Boat spare parts

Shop

Lack of funds

For small

business

Absence of

Boat repair

workshop

Absence of spare

Parts provision

System

Small number of

Clients for

Establishing

business

Lack of

specialists

Population’s

Weak

organization

Absence of

refrigerator

Lack of

Smoking

equipment

Absence of aluminum

Welding machine

For boat repairs

Lack of knowledge

About modern processing

methods