| ## Project Title | # Caspian Environment Programme: # Sustainable Management of Caspian Fisheries Project |
| --- | --- |
| ## Project number | ## EuropeAid/115111/C/SV/Multi |
| ## Countries | ## Azerbaijan, Kazakhstan, Russian Federation, in collaboration with Iran |
| ## Azerbaijan HQ ## Address: ## Tel: ## Fax: ## Email: ## Contact Person ## Signature: | ## Government House (Room 108) Az 1016 40, Uzeir Hajbayev Street, Baku, Azerbaijan +99412-4971-785; +99412-4938-003 +99412-4971-786 nwilloughby@caspian.in-baku.com Dr Nick Willoughby |
| ## EC Consultant ## Name: ## Address: ## Tel: ## Fax: ## Email: ## Contact Person ## Signature: | ## Landell Mills Limited Bryer Ash Business Park Bradford Road Trowbridge BA14 8HE United Kingdom +44-1225-763-777 +44-1225-753-678 Email: danil.samoilenko@landell-mills.com ## Mr Danil Samoilenko, Project Director ## _____________________________________ |

## Date of Report	30th September 2005

## Reporting Period	8 March  – 30 September 2005

## Authors of Report	Nick Willoughby

| Mauro di-Veroli ## ______________________ (Task Manager) [name] | ## ______________________ [signature] | ## ______________ [date] |
| --- | --- | --- |

CONTENTS

| SECTION | REPORT ELEMENT | PAGE |
| --- | --- | --- |
| Section 1 | Project synopsis | 1 |
| Section 2. | Project analysis Mar – Sep 2005 Descriptive summary of activities and events | 3 |
| Section 3. | Progress measured against log-frame anticipated results | 12 |
| Section 4. | Progress measured against log-frame anticipated activities | 17 |
| Section 5. | Future plans | 19 |
| Annexes | Annexe 1: Key project Documents |  |
|  | 1a. Project analysis |  |
|  | 1b. Specific activity components |  |
|  | 1c. Revised logical framework |  |
|  | 1d. Revised work plan |  |
|  | Annexe 2: National Population Dynamics Workshops |  |
|  | 2a. Agenda |  |
|  | 2b. Participants |  |
|  | Annexe 3: Russian e-mail confirming participation in project |  |
|  | Annexe 4: October Workshop Plans (Iran) |  |
|  | 4a. Plans and Draft Agenda for Regional Workshop, Ramsar |  |
|  | 4b. Draft Agenda for FRAG, Tehran |  |

List of Abbreviations

| AzerNIKH | Fisheries Research Institute, Azerbaijan |
| --- | --- |
| BISRAG | Biodiversity and Invasive Species Regional Advisory Group of CEP |
| CAB | Commission for Aquatic Bio-resources |
| CaspNIRKH | Caspian Fisheries Research Institute (Astrakhan, Russia) |
| CCP | Sustainable Development of Caspian Coastal Communities Project |
| CEP | Caspian Environment Programme |
| CEFAS | Centre for Environment, Fisheries & Aquaculture Science |
| CIS | Commonwealth of Independent States |
| CITES | Convention for International Trade in Endangered Species of Wild Fauna & Flora |
| EBRD | European Bank for Reconstruction and Development |
| FRAG | Fisheries Regional Advisory Group of the CEP |
| FRE | Fisheries Research Expert (Georgi Daskalov) |
| FSU | Former Soviet Union |
| FAO | Food and Agriculture Organisation |
| GEF | Global Environment Facility |
| GIS | Geographic Information System |
| IFRO | Iranian Fisheries Research Organisation |
| IOA | Indicators of achievement |
| IUCN | International Union for the Conservation of Nature |
| LML | Landell Mills Ltd |
| NCU | National Coordinating Unit |
| NGO | Non-governmental organisation |
| PCU | Project Coordination Unit |
| PD | Project Director (Danil Samoilenko) |
| PS | Procurement Specialist (Peter Harding) |
| RAG | Regional Advisory Group (of the Caspian Environmental Programme) |
| RFME | Regional Fisheries Management Expert (Andrew Payne) |
| RMT | Regional Management & Technical (workshop) |
| RTR | Regional Training (workshop) |
| SAPIC | Strategic Action Plan Implementation Coordinator |
| SE | Senior Economist (Andrew Palfreman) |
| SMCFP | Sustainable Management of Caspian Fisheries Project (this project) |
| TCP | Technical Cooperation Programme |
| TAC | Total Allowable Catch |
| TAG | Thematic Advisory Group (of the CEP) |
| Tacis | EU Technical Assistance Programme for the CIS and Mongolia |
| TCP | Technical Cooperation Project (FAO) |
| TD | Technical Director (Nigel Peacock) |
| TL | Team Leader (Christopher Mathews until June 05, then Nick Willoughby) |
| ToR | Terms of Reference |
| TP | Technical Proposals by Landell Mills |
| WWF | World Wide Fund for Nature |