Caspian Environment Programme

# CEP-SAP Project

Development of Caspian Coastal Sites Inventory (CCSI) and identification of areas of special importance and/or sensitivity within an ecosystem approach and framework

Inception Report

Almaty – Ashghabat – Baku – St. Petersburg –Tehran

2006

Contents

| Summary | 4 |
| --- | --- |
| Introduction | 5 |
| Background | 5 |
| Objectives | 6 |
| Implementation Strategy | 6 |
| Major Activities and Timeline | 7 |
| Project Implementation | 8 |
| Implementation Arrangement | 8 |
| Methodology of the CCS Mapping | 8 |
| Methodology of the Human Impact Assessment | 13 |
| Biodiversity Monitoring Programme | 15 |
| Expected Results | 22 |
| Interaction of CCSI and other CEP projects | 23 |
| References | 24 |
| Annex 1 List of maps recommended for construction and usage in reports of the CCSI Project | 25 |
| Annex 2 Questionnaire for local experts considering his/her opinion on the environmental state of the coastal site and biodiversity of the coast under the study | 27 |
| Annex 3 Report on the CCSI Inception Meeting (Baku, Azerbaijan, 12-13th January, 2006) | 36 |

List of Tables

| Section 2 | Project Implementation |
| --- | --- |
| Chapter | 2.2 Methodology of the CCS Mapping |
| Table 1 | Main types of the Caspian Sea coasts and human impacts on them in the five littoral states |
| Table 2 | Invented example: List of animals included into the Red Books in the Republic Azerbaijan |
| Table 3 | Invented example: Record of plant and animal species of the coast (or segment of coast) of I.R. Iran |
| Chapter | 2.3 Methodology of the Human Impact Assessment |
| Table 4 | Human impacts on marine and coastal biotope complexes and their abbreviations (HELCOM, 1998) |
| Table 5 | Criteria system for assessing the degree to which a certain biotope is under threat within the survey area (HELCOM, 1998) |

List of Abbreviations

| ACEP | - | Azerbaijan Centre of Ecological Projects (Baku, Azerbaijan) |
| --- | --- | --- |
| BIS | - | Biodiversity Information System |
| BMP | - | Biodiversity Monitoring Programmes |
| CCSI | - | Caspian Coastal Sites Inventory |
| CEP | - | Caspian Environment Programme |
| DOE | - | Department of Environment, I.R.Iran |
| ECOPRO | - | Environmental Consulting and Nature Protection Design Agency “ECOPROJECT”, St. Petersburg, Russia |
| ECS | - | Ecological Consulting Services |
| EUCC | - | European Union for Coastal Conservation |
| GT | - | Ground-Truthing |
| HELCOM | - | Helsinki Commission |
| IMAPS | - | Interactive Mapping Tools |
| KAAE | - | Kazakh Agency of Applied Ecology, Almaty, Kazakhstan |
| NC | - | National Coordinator |
| NIDFF | - | National Institute for Deserts, Flora and Fauna, Ashghabat, Turmenistan |
| PCU | - | Project Coordination Unit |
| RB | - | Red Book |
| RC | - | Regional Coordinator |
| SAP | - | Strategic Action Programme |
| TDA | - | Transboundary Diagnostic Analysis |
| TOR | - | Terms of Reference |
| UNEP | - | United Nations Environment Programme |
| UNOPS | - | United Nations Office for Project Services, Geneva, Switzerland |
| WCMC | - | World Conservation Monitoring Centre |

SUMMARY

This report summarises the results of activity and plans of work on the Project “Development of Caspian Coastal Sites Inventory (CCSI) and identification of areas of special importance and/or sensitivity within an ecosystem approach and framework” from its beginning in early December, 2005 till the end of Inception Meeting held in Baku on 12-13 January 2006.

1	Introduction

1.1	Background

The Caspian Environment Programme (CEP) represents a partnership between the five littoral states, Azerbaijan, Islamic Republic of Iran, Kazakhstan, Russian Federation, and Turkmenistan. The overall goal of the CEP is to promote the sustainable development and management of the Caspian environment in order to obtain the optimal long-term benefits for the human population of the region.

During the first phase of the GEF-supported project under the CEP a Transboundary Diagnostic Analysis (TDA) and a Strategic Action Programme (SAP) were formulated through elaborate consultations within the region. The SAP identified four regional environmental concerns, one of which was threats to biodiversity. Based on these concerns, five environmental quality objectives (EQO) were formulated. In relation to biodiversity threats, the EQO is: “Conservation of Caspian Biodiversity”.

Also during phase one, a number of activities were carried out with the aim to increase the knowledge-base on biodiversity in the Caspian region. A biodiversity database was developed based on existing information. Although this database is incomplete and limited in scope, it represents the first time that regional biodiversity information has been compiled into one single entity. In addition, national reports were prepared on habitat diversity and species biodiversity in each of the five Caspian countries based on existing data and information.

The second phase of the project started implementation in June 2004. The main focus of the projects is on implementation of activities related to the SAP objectives: biodiversity conservation, invasive species and pollution. The project work-plan is divided into nine different Outcomes. Under Outcome A, the main objective is to improve the information base on which the formulation of future biodiversity management plans can be based. Under this outcome, several activities have already been initiated:

- The development of interactive mapping tools (ImapS) for the entire Caspian basin is being implemented together with the UNEP World Conservation Monitoring Centre (WCMC).

- The development of a biodiversity database, a biodiversity monitoring programme and associated training has been combined into one sub-project, which is currently being implemented by Ecological Consulting Services (ECS).

One of the remaining key activities under Outcome A is the development of a Caspian Coastal Sites Inventory (CCSI). This activity will be implemented through the TOR below. The outputs of this activity will in turn be integrated with the biodiversity database developed by ECS and the ImapS tool developed by WCMC. Furthermore, based on the final CCSI, sites of particular importance and/or sensitivity will be identified, which will need special conservation measures at local, national and regional level.

A preliminary CCSI will be completed as part of the ECS sub-project. This preliminary CCSI will be the starting point for the TOR.

1.2	Objectives

The main objective of the TOR is to develop a coastal sites inventory of the Caspian region with the aim to identify sensitive areas in need of future protection.

Additional objectives are:

- To introduce/strengthen the ecosystem approach as a framework for biodiversity monitoring and conservation

- To improve the knowledge base on biodiversity in the Caspian Sea

1.3	Implementation Strategy

The CCSI will be developed within an overall ecosystem framework that encompasses the entire Caspian region. The Ecosystem Approach is increasingly being applied at a global scale in the management of natural resources and biodiversity conservation. The approach emphasizes ecosystem processes rather than ecosystem components only. Ecosystem processes include various types of species interactions, species-environment interactions, seasonal variations in the physical environments and ecological adaptations to those variations.

The ecosystem approach implies that coastal sites, apart from their intrinsic biodiversity values, also are valuable as parts of the larger-scale ecosystem. Applying the approach to the CCSI will thus involve describing ecosystem linkages and processes between different coastal sites and the larger-scale ecosystem of the Caspian Sea, as well as the more conventional description of biodiversity components within each site.

The core of the TOR will be two separate field activities, a ground-truthing exercise and initiation of a one-year monitoring programme.

- The ground-truthing will be carried out at five selected coastal sites of each country, participating in the CCSI project, with the aim to verify and document key characteristics of those sites. This will be done through photo-documentation and description of key habitats and species communities (it seems worthwhile to base on the local specialists data).

- The monitoring programme will be initiated with the aim to obtain key biodiversity data from five selected sites of each country over one full seasonal cycle. The detailed protocol for the programme (e.g., identification of key parameters and indicators for monitoring, frequency & methods of monitoring) will be developed as part of the TOR.

1.4	Major Activities and Timeline

- Review of existing situation and formulation of work-plan (Month 1)

- Recruit RC and NCs (Month 1)

- Inception Meeting with the aim to define scope of Ground-Truthing (GT) exercises, discuss and agree on the key elements of the biodiversity monitoring programme (Month 1)

- National coordination meetings, by NCs (Month 1-2)

- GT exercises conducted by NCs (Months 2-5)

- Supply of monitoring equipment to the monitoring agencies in the littoral countries under separate arrangement (Months 2-3)

- Initiation/strengthening of Biodiversity Monitoring Programmes (BMP) in each country (Months 3-14)

- Integration of national GT reports into regional CCSI (Month 6)

- Regional Meeting to review monitoring results and suggest selected sites for protection based on agreed criteria as developed by RC in consultation with the NCs (Month 7)

- Completion of national BMP reports (Month 13)

- Integration of national BMP reports into a regional BMP report (Month 15)

2	Project Implementation

2.1	Implementation Arrangements on the Project

In order to ensure consistency, and to ensure that the final output of the TOR incorporates all the outputs from all sub-contractors in a systematic and integrated manner, the entire TOR was contracted out to a single entity, i.e. The Consultant (ACEP). The Consultant was recruited through UNOPS and will directly report to the CTA.

For the implementation of the overall TOR, one regional coordinator (RC) and five national coordinators (NC) were required by ACEP, which will provide the services of the following key personnel:

| Name | Specialization | Nationality | Period of Service |
| --- | --- | --- | --- |
| Vladimir Pogrebov | Regional Coordinator | Russian Federation | 12/2005-02/2007 |
| Tofik Hasanov | National Coordinator | Azerbaijan | 12/2005-02/2007 |
| Vladimir Uvarov | National Coordinator | Kazakhstan | 12/2005-02/2007 |
| Omid Sedighi | National Coordinator | I.R. Iran | 12/2005-02/2007 |
| Andrey Filippov | National Coordinator | Russian Federation | 12/2005-02/2007 |
| Amanklych Babayev | National Coordinator | Turkmenistan | 12/2005-02/2007 |

The RC coordinated the work of the NCs and liaised with CEP/PCU. The five NCs coordinated the work at national level in each of the five Caspian countries. They reported to the RC.

2.2	Methodology of the CCS Mapping

At the Inception Phase of the Project Implementation, team of the JSC ECOPROJECT (Russian Environmental Agency, St. Petersburg) prepared GIS-based maps (MapInfo 6.0) of coastline for both entire Caspian Sea and coastline of all the five littoral states (Azerbaijan, Islamic Republic of Iran, Kazakhstan, Russian Federation – RF, and Turkmenistan) participating in the Project. Topographic base maps were delivered to all NCs.

According to the plan proposed by RC, each littoral state should construct a map of its coasts using as an analogue a map of The Coastal Systems of Europe, which was done within a framework of project implemented by The European Union for Coastal Conservation – EUCC in 1998 (see examples below). Explanations necessary for the map construction are presented at a site: http://www.coastalguide.org/typology/typrcol.html. However, it seemed worthwhile to use more detailed classification represented in a Table 1 (Section “Catchment area” was deleted from the Legend). Detailed elaboration of map was proposed to do by use of three-letter abbreviations given in Table 1.

At the beginning of work, it was considered desirable to construct more maps able to characterize environment of the Caspian Sea coastline in a way that is more detailed. Their approximate list is given in Annex 1 and was discussed at the Inception Meeting, which took place in Baku on 12-13th January 2006 (see Annex 3). However, taking into account the Project Timeline, it was concluded that this work is labour consuming and not all littoral states will be able to finish it in time.

Existence of a certain types of coastline within the boundaries of each littoral state we agreed to designate by a sign «+» in appropriate cells of table (see Table 1). Dashes in Table 1 show that this type of coastline is absent in the country. We agreed also that it would be good to present examples of various types of coastline in each littoral state (photo were welcomed). Besides, we agreed to characterize human impacts in this table taking, as a basis an approach used in a similar project carried out for the Baltic Sea (HELCOM, 1998). Complete text of this publication is represented at site: http://www.helcom.fi/publications/bsep/en_GB/bseplist/ (Baltic Sea Environment Proceedings, No. 75 - BSEP 75). Characterizing human impacts on the coastline (see below; Table 4) we decided to use not the classification of biotopes as it is extremely complicated but to take the classification similar to the classification of biotope complexes (see Table 1).

Table 1	Main types of the Caspian Sea coasts and human impacts on them in the five littoral states

| Code | Coastal site type | Azerbaijan | Iran | Kazakhstan | Russia | Turkmenistan |
| --- | --- | --- | --- | --- | --- | --- |
| HRC | Hard rock cliffed coasts | + | - |  | CG | - |
| HRP | Hard rock coastal plains | СА | - | + |  | - |
| SRC | Soft rock cliffed coasts |  |  |  |  | + |
| SRP | Soft rock coastal plains |  |  |  |  | + |
| SKC | Skerry coasts |  |  |  |  |  |
| SGS | Shingle / sandy spits | DR |  | DR | DR |  |

Table 1 (continuation)

| Code | Coastal site type | Azerbaijan | Iran | Kazakhstan | Russia | Turkmenistan |
| --- | --- | --- | --- | --- | --- | --- |
| SSB | Shingle / sandy beaches | CA |  |  |  |  |
| COD | Coastal dunes |  |  |  |  |  |
| RRT | Reed & rush thickets |  |  | CN |  |  |
| MUF | Mud flats |  |  |  |  |  |
| WET | Wetlands |  |  |  |  |  |
| SAM | Salt marshes |  |  |  |  |  |
| OBA | Open bays |  |  |  |  |  |
| SCB | Semi-closed bays |  |  |  |  |  |
| LAG | Lagoons |  |  |  |  |  |
| COL | Coastal lakes |  |  |  |  |  |
| RID | River deltas |  | CW, CP |  | CN, CP | CA |
| EST | Estuaries | CP |  |  |  | CP |
| SOI | Solitary islands |  |  |  |  |  |
| ARC | Archipelagos |  |  |  |  |  |

Characteristics of the Caspian coasts biodiversity are essential for the CCSI. As a first step, we decided to characterize biodiversity of comparatively large taxonomic groups of plants and animals using two main indices: (1) total number of species recorded in the study area, and (2) number of species included into Red Books (RB) of various levels (the latter was considered to be priority-driven). Therefore, it was agreed that biodiversity of each coastal site studied in any of the littoral state participating in the Project will be characterized by somewhat like a record card (see Table 2). It was decided to produce such tables with indices 2а, 2в, 2с, etc., as many as possible (according to the data available in each of the littoral state participating in the Project).

Table 2	Invented example: Record of plant and animal species of the coast (or segment of coast) of I.R. Iran

| Group | Species total | Included into RB* | Species dynamics | RB species dynamics** | Comments |
| --- | --- | --- | --- | --- | --- |
| Algae | 78 | 7 (0-5) | ( | ( |  |
| Lichens | 89 | 5 (1-4) | ( | ( |  |
| Mosses | 12 | 4 (2-5) | ( | ( |  |
| Vascular plants | 222 | 12 (0-5) | ( | ( |  |
| Plants total: | 401 | 28 (0-5) | ( | ( |  |
| Invertebrates | 99 | 5 (2-5) | ( | ( |  |
| Fishes | 68 | 5 (0-4) | ( | ( |  |
| Amphibians | 22 | 7 (2-3) | ( | ( |  |

Table 2 (continuation)

| Group | Species total | Included into RB | Species dynamics | RB species dynamics* | Comments |
| --- | --- | --- | --- | --- | --- |
| Reptiles | 45 | 4 (0-4) | ( | ( |  |
| Birds | 124 | 24 (3-4) | ( | ( |  |
| Mammals | 44 | 8 (1-3) | ( | ( |  |
| Animals total: | 402 | 53 (0-5) | ( | ( |  |
| Species total: | 803 | 81 (0-5) | ( | ( |  |

*	IUCN category should be shown

**	Biodiversity decreases: ( (-n), where n is a number of disappeared species; biodiversity is stable: - (; biodiversity increases - ( (+n), where n is a number of appeared species

Maps, which should be constructed, basing on such table data on species included into the Red Books, should contain coloured circles for each species with a figure inside the circle showing its number in the table. Initially numeration should be individual for each littoral state. Later on, data will be summarized and one common numeration will be used. Therefore, it was agreed to make provision for a special column in the preparing table named “Number for the entire Caspian coastline” besides the column named “Number for [name of littoral state]. PC recommended preparing tables according to the invented example, showing situation with animals for the Republic Azerbaijan (see Table 3). It was approved that presence of the Latin name of species is an obligatory condition of the table filling in.

Table 3	Invented example: List of animals included into the Red Books in the Republic Azerbaijan

| Groups and species | IUCN category* | No for Azerbaijan | All-Caspian number |
| --- | --- | --- | --- |
| Invertebrates |  |  | To be |
| Species A | 3 | 1 | filled in |
| Species B | 2 | 2 | later |
| Fishes |  |  | by RC |
| Species C | 2 | 3 | staff |
| Species D | 2 | 4 |  |
| Amphibians |  |  |  |
| Species E | 2 | 5 |  |
| Reptiles |  |  |  |
| Species F | 1 | 6 |  |
| Birds |  |  |  |
| Species G | 0 | 7 |  |
| Species H | 4 | 8 |  |
| Mammals |  |  |  |
| Species I | 5 | 9 |  |
| Species G | 4 | 10 |  |
| Species K | 4 | 11 |  |
| Total |  | 11 |  |

*	0 – probably extinct; 1 – endangered; 2 – vulnerable; 3 – rare; 4 – indeterminate; 5 – recoverable and recovering.

Table on plants should be prepared in the same manner.

Designating various groups of plants on map, we agreed to use circles of the following colours:

- Algae – chlorine (;

- Fungi – murrey ( (in RF – 1);

- Lichens – turquoise ( (in RF – 1);

- Mosses – cyan ( (in RF – 1);

- Vascular plants – green ( (in RF – 39).

Designating various groups of animals on map, we agreed to use circles of the following colours:

- Invertebrates – grey ( (in RF – 20);

- Fishes – yellow ( (in RF – 6);

- Amphibians – green-brown ( (in RF – 2);

- Reptiles – purple ( (in RF – 5);

- Birds – orange ( (in RF – 40);

- Mammals – red ( (in RF – 12).

It was considered worthwhile in the beginning of the mapping process to construct maps separately for each group. Later on, the maps constructed should be combined according to the number of rare species within the taxonomic groups chosen. For example, for the Russian coastline of the Caspian Sea, among the plants included into the Red Book of RF, we have the following number of species per each group: fungi – 1; lichens – 1; mosses – 1; vascular plants – 39. Hence, we consider that for these figures it will be convenient to have separate maps for (1) fungi, lichens, and mosses; and (2) vascular plants. Among the animals included into the Red Book of RF, we have for the Russian coastline of the Caspian Sea, the following number of species per each group: invertebrates – 20; fishes – 6; amphibians – 2; reptiles – 5; birds – 40; and mammals – 12. Hence, we consider that for these figures it will be convenient to have separate maps for (1) invertebrates; (2) fishes, amphibians and reptiles; (3) birds; and (4) mammals.

The described above stage of work will be based on a paper method and will need ground-truthing in the course of fieldwork (specifically, at least five coastal sites should be studied by the Project team members of each littoral state). We agreed that it would be worthwhile to fulfil two independent studies:

- Questioning of local experts, and

- Implementation of own observations.

Both types of studies should be carried out in a similar way (see Annex 2) but own observations should include semi-quantitative assessment of the environmental state of coast in a way described below (see Table 5).

2.3	Methodology of the Human Impact Assessment

Assessment of main human impacts on coastal habitats and, as a result, on biodiversity, is considered to be an obligatory stage despite the limited time of the GT stage of work. It is intended to use an approach, which was successfully used for the same purposes on the Baltic Sea (HELCOM, 1998). Necessary details of this approach one may find in the Baltic Sea Environment Proceedings, No. 75 (http://www.helcom.fi/publications/bsep/en_GB/bseplist/; see BSEP 75).

List of human impacts on marine and coastal biotopes, presented on page 13 of mentioned publication, should be supplement with impacts caused by oil production and transportation (construction of oil infrastructure objects inclusive) since it is more than topical for the Caspian Sea. We assume that it will be excusable not to use semi-quantitative evaluation of the coast environmental status at the first (office) stage of study because of its high subjectivity; and to show only the types of human impact. The first draft of such a table is presented in Table 4. The data collected should be put on map of each littoral state participating in the Project.

Table 4	Human impacts on marine and coastal biotope complexes and their abbreviations (HELCOM, 1998)

| (С) – biotope loss or change (irreversible or reversible) |
| --- |
| CA | - | Agriculture (intensive, changing, land reclamation, stop of traditional farming) |
| CB | - | Construction, dredging, dumping of dredged material |
| CD | - | Coastal defense, e.g., dyking, stabilization of sand |
| CE | - | Eutrophication (fertilization, sewage, combustion) |
| CF | - | Overfishing, bottom trawling, mariculture (fishfarming or mariculture is indicated with an additional F: СFF) |
| CH | - | Building activities fir recreation purposes, e.g., summer houses, marinas |
| CG | - | Wear (traffic, tourism) |
| CM | - | Mineral extraction (prospecting, mining, dredging) |
| CN | - | Oil production and transportation (construction of oil infrastructure objects inclusive) |
| CP | - | Pollution (non-eutrophication) of air, earth and water (pesticides, waste disposal, sewage, combustion, oil) |
| CT | - | Forestry (deforestration, plantations, changes) |
| CW | - | Water regulation (drainage rerouting, extraction/desiccation land reclamation) |
| CY | - | Military activities (shooting, bombing, etc.) |

Table 4 (continuation)

| (D) – Biotope disturbance (temporary) |
| --- |
| DA | - | Agriculture, forestry |
| DB | - | Construction, dredging, dumping of dredged material, mineral extraction |
| DF | - | Fishing, hunting |
| DY | - | Military activities (shooting, bombing, etc.) |
| DR | - | Recreational activities |

Second stage of the Ground-Truthing will include assessment, which will be result of own field observations, carried out by the team members of each littoral state. This assessment will be based on the already mentioned approach (HELCOM, 1998; see Table 5). Each segment of the coast studied will get literal expression, showing its environmental status.

Table 5	Criteria system for assessing the degree to which a certain biotope is under threat within the survey area (HELCOM, 1998)

| CRITERION 1 «loss of area» Threatened by direct destruction (DE) | CRITERION 2 «loss of quality» Threatened by qualitative changes (QU) | OVERALL ASSESSMENT (() |
| --- | --- | --- |
| 0 – Completely destroyed (total loss of area) | 0 - Completely destroyed (completely changed) | 0 - Completely destroyed |
| Biotope which was previously present in the survey area but today can no longer be proven to exist. | Biotope whose quality is affected so severely that its natural variants are completely destroyed. |  |
| 1 – Immediately threatened (immediate danger of total loss of area) | 1 - Immediately threatened (immediate danger of becoming completely changed) | 1 - Immediately threatened |
| Biotope of which only little portions in the former area of distribution still exist. If impacts continue and no protection or management measures are taken a complete destruction has to be suspected. | Biotope whose quality is negatively affected in the entire area so that typical or natural variants can only be found in one or very few sub-regions. |  |
| 2 – Heavily endangered (heavy danger of severe loss of area) | 2 - Heavily endangered (heavy danger of becoming severely changed) | 2 - Heavily endangered |
| Biotope that shows a heavy decline of area in almost the entire region or that is already extinct in several sub-regions. | Biotope whose quality is negatively affected in a way that a decline of typical variants can be stated in almost the entire area or that typical variants already became extinct in several sub-regions. |  |
| 3 – Endangered (danger of loss of area) | 3 - Endangered (danger of becoming decisively changed) | 3 - Endangered |
| Biotope that shows a negative development of area extends over a broad range of the region or that is locally extinct at many sites. | Biotope whose quality is negatively affected in a way that a decline of typical variants in several sub-regions can be stated or typical variants already became locally extinct at numerous sites. |  |

Table 5 (continuation)

| CRITERION 1 «loss of area» Threatened by direct destruction (DE) | CRITERION 2 «loss of quality» Threatened by qualitative changes (QU) | OVERALL ASSESSMENT (() |
| --- | --- | --- |
| P – Potentially endangered |
| This category does not represent a category of actual threat according to categories 1-3. Biotopes potentially threatened are those which have been always rare or which exist only in a small area but which might easily qualify for even category “0” if their small area of distribution is affected by adverse impacts. |
| «*» - Presumably not endangered at present |
| «?» - No data available |
| «-» - Does not occur in the survey area |
| «(» - Classification not meaningful |
| Categories for assessment of regeneration ability (RE): |
| N – Regeneration impossible |
| K - Regeneration hardly possible |
| S - Regeneration difficult |
| B - Regeneration conditionally possible |
| «*» - Presumably not endangered at present |
| «?» - No data available |
| «-» - Does not occur in the survey area |
| «(» - Classification not meaningful |

The data collected in the course of this study should be presented on maps of each littoral state using designations shown in the table.

2.4	Biodiversity Monitoring Programme

Biodiversity Monitoring Programmes (BMP) will be initiated in each littoral state simultaneously with the observations, which will be carried out in the course of the Ground-Truthing. Number of coastal sites, where the monitoring observations will be carried out, as well as the scope of work at each of them was discussed in the course of Inception Meeting (see Annex 3). It was decided that their number may be the same as the number of sites for ground-truthing and should be equal five. It was decided that the coastal sites for monitoring should be selected using the following criteria:

- It should be sites of particular importance and/or sensitivity, which will need special conservation measures at local, national or regional level;

- It should be sites of particular importance for the Caspian Sea ecosystem as a whole;

- Rare, threatened, vulnerable and/or endangered species occurrence in this particular location should be taken into consideration;

- Rare, threatened, vulnerable and/or endangered ecosystems existence at this particular site should be also taken into account;

- The biotopes, which are playing crucial role in inter-species or species-environment or inter-ecosystem interrelations, should be considered first.

It was approved by all the project participants that the above listed requirements are met to a great extent at the coastal sites with the already existing observation net, e.g., at the Protected Areas of various level, standard sites of bird migration observations, and sites of seal observations in winter time and so on.

The biodiversity and environmental data, which could realistically be obtained in the course of monitoring observations, will comprise the following.

- Biotic characteristics, in particular species composition of main ecological groups including

- Plants (algae, fungi, lichens, mosses, and vascular plants)

- Animals (shallow water bottom dwellers and fishes, amphibians, reptiles, birds and mammals)

- Seasonal variations in flora and fauna

- Abiotic characteristics including

- Air and water temperature

- Air humidity

- Wind velocity and direction

- Degree of cloudiness

- Precipitations

- Soil type (optionally)

- Water salinity

- Water transparency

- Water pH

- Oxygen content in water

- Visual observations on oil slicks, drifting algae, areas with roiled or frothed water, etc.

As well, following observations should be carried out and dated in the seasonal aspect:

- Arriving of animals after hibernation;

- Beginning, height and end of blossoming for main plant species;

- Beginning, height and end of the spring and the autumn migration for migrating birds, mammals and other animals (if any);

- Beginning, height and end of coupling and breeding;

- Beginning, height and end of nesting for birds;

- Beginning, height and end of moulting for birds and mammals;

- Seasonal changes in behaviour of birds, mammals and other animals (if any);

- Beginning, height and end of fructification for main plant species;

- Beginning, height and end of natural defoliation of trees and shrubs;

- Disappearance of animals for hibernation; and so on.

Besides that, observations should include assessment of the human impact changes in the seasonal aspect (firing of grass in the springtime, illegal fishing and hunting, usage of fertilizers or pesticides, overexploitation of resources, e.g., over-pasturing, intensive coastal tourism, collecting of berries and fungi, etc.).

All observations should be provided by digital photo documentation of the processes and phenomena observed, which should be carried out on a high professional level.

Detailed elaboration of the monitoring programme was discussed during the Inception Meeting (see Annex 3). Generally the approach was approved (see Annex 3) while some problems and unclear issues were thoroughly debated.

The lists of sensitive sites for BMP as well as proposals on the ecosystems, objects and methods of monitoring for each littoral country are as follows (observations will be carried in all seasons – all-the-year-round).

Azerbaijan

Sensitive sites:

- Samur-Yalama – forests (forest flora and fauna) and freshwater ecosystems

- Divichinskiy Estuary – wetland ecosystems (birds)

- The Kura River Delta– freshwater ecosystems (flora, fishes, birds)

- Gyzyl-Agachsky Protected Area – marine ecosystems (Big and Small Gyzyl-Agachsky Bays) and wetland ecosystems (flora, fishes, birds)

- National Park «Girkan» - forest ecosystems (flora and fauna)

Ecosystems for monitoring:

- Marine (bays and estuaries)

- Freshwater (rivers and lakes)

- Wetland

- Forest (relic and coastal)

Objects for monitoring:

- Wetland vascular plants (grass, bush and tree species)

- Coastal vascular plants (grass, bush and tree species)

- Fishes

- Amphibians

- Reptiles

- Birds

- Mammals

Monitoring methods:

- Standard route botanical and zoological field studies will be planned in such a way that main communities will be covered and Red Data Book species will be included

- Correction of thematic maps (vegetation, landscapes, etc.) constructed in the course of office studies will be done by the indices of ecosystem boundaries, environmental state of key biotopes and species populations, state and geographical location of rare plant and animal communities, priority of habitats and species for protection, etc.

- Vegetation types will be described in connection with their habitats; succession (renewal) phase, age structure, growth class (for forest communities), human impact, degradation degree, etc.

- Zoological studies will be accomplished according to the methods accepted in Azerbaijan

- Birds will be observed by means of binoculars and telescope on tripod

- Animals will be detected by direct visual observations as well as registered by their burrows, footprints, skeleton remnants droppings, etc.

- Changes in the state of animal populations will be studied in connection with possible changes in their habitats and еру human impact level

- Protected areas will be studied from the viewpoint of their territory representativeness, effectiveness of nature protection measures and ability for rehabilitation

Iran

Sensitive sites:

- International Wetlands of Alagol, Agigol and Almagol (flora, fishes, amphibians and reptiles, birds, mammals)

- Wildlife Refuge of Miankale Wetland and Gorgan Bay (flora and fauna)

- Wildlife Refuge of Fereidoonkenar (flora and fauna)

- International Wetland and National Natural Park of Boojagh (flora and fauna)

- International Wetland of Anzali (flora and fauna)

Ecosystems for monitoring:

- Marine (gulf, bays and estuaries)

- Freshwater (rivers)

- Wetlands (coastal)

- Forest

Objects for monitoring:

- Algae (phytoplankton)

- Vascular plants

- Invertebrates (zooplankton)

- Fishes

- Amphibians

- Reptiles

- Birds

- Mammals

Monitoring methods:

In addition to methods of terrestrial field surveys, methods of marine sampling will be used.

- Location of marine stations will be determined by means of GPS

- Sampling of plankton (3 replicates) will be carried out by Bongo-net (Ø = 45 cm). Nets with mesh sizes of 64 μ for phytoplankton, 110 μ for zooplankton and 335 μ for ichthyoplankton will be used. Samples will be preserved in 4% formaldehyde and kept in the labeled and coded containers

- Samples will be surveyed under an invert microscope. In order to count the planktons, the plankton chamber with a volume of 1 cc will be used

- Macrobenthos samples (3 replicates) will be taken using the Van Veen Grab (0.025 m2). Samples will be washed in the field using sieves of 0.5 mm mesh size, transferred to plastic containers and fixed with 4% formaldehyde

- In the laboratory the macrofauna samples after addition of ethanol will be coloured by Bengal Rosa. To identify some invertebrate groups, microscopic photography will be utilized

- Diversity index of Shannon (H’), Simpson Index (λ) and evenness index (E) will be calculated for data analysis and presentation.

Kazakhstan

Sensitive sites:

- Novinsky Reserve - wetland ecosystems (flora, birds)

- Ural River Delta - wetland ecosystems (flora, birds, fishes)

- Komsomolets Bay - marine ecosystems (birds)

- Aktau-Buzachi Reserve – desert ecosystems (fauna)

- Karakiya-Karakol Reserve – freshwater ecosystems (fauna)

Ecosystems for monitoring:

- Marine

- Freshwater

- Wetland

- Desert

Objects for monitoring:

- Wetland vascular plants (grass, bush and tree species)

- Coastal vascular plants (grass, bush and tree species)

- Invertebrates

- Fishes

- Amphibians

- Reptiles

- Birds

- Mammals

Monitoring methods:

- Composition of flora and fauna as well as quantitative studies will be carried out by both route observations and grid sampling

- Route and grid sampling will be accomplished taking into account all environmental and landscape types, impacted areas inclusive

- Field studies will be organised in a way, which will provide a possibility for recording of maximum possible number of plant and animal groups inhabiting the study area

- Meteorological characteristics such as air temperature, wind velocity and direction, precipitations, degree of cloudiness, etc. will be recorded in all monitoring observations

- In the course of marine and freshwater monitoring studies, water temperature, water salinity water transparency (NTU), pH, oxygen content, etc. will be measured; visual observations on oil slicks, drifting algae, areas with roiled or frothed water, etc. will be fulfilled in parallel with instrument measurements

Russia

Sensitive sites:

- Sub-aqueous part of the Volga River Delta (avandelta; marine and wetland ecosystems: vascular plants, birds and mammals)

- Area of former river-beds and hillocks adjacent to the Volga River Delta (“Il’menno-bugrovye” sites: wetland ecosystems: birds and mammals)

- Small Zhemchuzhny Island (marine and wetland ecosystems: birds)

- Kizlyarsky Bay (marine and wetland ecosystems: vascular plants, birds and mammals)

- Agrakhansky Reserve (marine and wetland ecosystems: birds)

Ecosystems for monitoring:

- Marine

- Wetland

Objects for monitoring:

- Wetland vascular plants

- Coastal vascular plants (grass, bush and tree species)

- Birds

- Mammals

Monitoring methods:

- Considering the shortage of funds, Russian BMP team inclines to perform terrestrial monitoring only with emphasis on bird observations. Data on mammals and vegetation will be collected as optional on some monitoring sites.

- At all terrestrial monitoring locations, fixed photographic points will be established for routine recording of digital images. These images will assist users to visualise general comparative characteristics of each habitat for tracking seasonal and long-term changes in soil and floral community characteristics

- The transect approach will be used for mammal studies with checklists for observation of tracks, droppings, burrows, direct sightings, etc. The same transects will be used for floral and faunal surveys.

- For some key species of mammals, specific methods will be used to quantify their population size and structure

- Monitoring of local (resident) birds will take place in co-ordination with floral and faunal surveys. Visual records as well as photography will be provided.

- Registration of bird fauna composition, presence, and abundance of resident, migratory and wintering birds, number of breeding pairs, etc. will be accomplished

- Ecological state of local (resident) birds as well as status of migratory and wintering populations will be assessed, especially where they have regional or global significance

- Meteorological characteristics such as air and water temperature, air humidity, wind velocity and direction, precipitations, degree of cloudiness, etc. will be recorded in all monitoring observations

Turkmenistan

Sensitive sites:

- Atrek River Delta and Gasankuli part of the State Nature Reserve “Khazar”

- Ogurchinsky Island (area of the State Nature Reserve “Khazar”)

- South-Cheleken Bay

- Krasnovodsky, Balkhansky, North-Cheleken and Mikhailovsky Bays (northern part of the State Nature Reserve “Khazar”)

- Kiyanly Bay

Ecosystems for monitoring:

- Marine (the Atrek River delta)

- Wetland

- Desert (sandy, clayey and brackish)

Objects for monitoring:

- Wetland vascular plants

- Coastal vascular plants (grass and bush species)

- Fishes

- Reptiles

- Birds

- Mammals (Caspian seal, true otter, goitered gazelle)

Monitoring methods:

- In general, landscape-geographical-botanical methods will be applied

- Remotely sensed observations such as satellite images will be used too (mainly for the coastline and coastal ecosystem study)

- Besides that cartographic data (thematic maps, as well as topographic maps) will be used for coastal sites inventory, assessment of possible ecosystem changes and human impacts

- During the fieldwork, visual transport and on-foot traverses will be made over the entire study area

- Key sites will be thoroughly studied by means of environmental profiling at various distances; all landscape components will be described along the profiles (transects)

- Observations on animals will be carried out at some sites chosen by the specialists of Protected Areas

- Meteorological characteristics such as air and water temperature and air humidity, will be recorded in all monitoring observations

- Soil type will be studied optionally

3	Expected Results

Development of a coastal sites inventory of the Caspian region with identification of sensitive areas in need of future protection is considered to be the main result of the project implementation.

The ecosystem approach as a framework for biodiversity monitoring and conservation will be strengthen by basing on both abiotic and biotic data as well as by assessment of main human impacts on coastal habitats and the degree to which a certain biotope is under threat within the survey area. Due to such an approach, the knowledge base on biodiversity in the Caspian Sea will be improved while the practical results achieved could be applied to solution of the most urgent nature protection problems in the Caspian region.

Deliverables of the Project are expected to be as follows (see also Annex 3):

- Work-plan (Month 1)

- Inception Report (Month 1)

- National GT Reports (Month 5)

- Regional CCSI (Month 6)

- National BMP Reports (Month 13)

- Final BMP Report (Month 15)

The minimum number of maps, which will be produced by each of littoral states participating in the Project after the end of the Ground-Truthing stage, is five. They will be:

- Coastal landscapes (types of vegetation and Protected Areas should be shown) in the boundaries of [name of the littoral state, e.g., Azerbaijan];

- Coastal systems of the Caspian Sea in the boundaries of [name of the littoral state, e.g., Turkmenistan] (see Table 1);

- Distribution of plant species included into the Red Book along the coasts of [name of the littoral state, e.g., I.R. Iran] (see Tables 2 and 3); if the number of rare species is too much (e.g., more than 12), separate maps will be presented;

- Distribution of animal species included into the Red Book along the coasts of [name of the littoral state, e.g., Russia] (see Tables 2 and 3); if the number of rare species is too much (e.g., more than 12), separate maps will be presented;

- Human impacts on the coastal systems and the degree to which a certain segments of coast are under threat within the boundaries of [name of the littoral state, e.g., Kazakhstan Russia] [name of the littoral state, e.g.,] (see Tables 4 and 5).

National BMP Reports as well as Final BMP Report will include results of monitoring in a form of tables, graphs and diagrams, which will be analyzed, interpreted and discussed in the text.

4	Interaction of CCSI and other CEP projects

Interaction of CCSI and other CEP projects, such as BIS, ECS, IMAPS (see List of Abbreviations above) and others is implied from the very beginning and is stated in the Background section of the this Report (see above). Discussion on coordination between Consortium and other CEP projects was initiated by CEP expert Lev Neretin and was discussed in details during the Inception Meeting held in Baku on 12-13 January 2006 (see Annex 3 below). As a result, it was concluded that this coordination would take place during the entire period of the CCSI Project implementation. Coordination will be based on correspondence via e-mail (see e-mail addresses of the CCSI Inception Meeting participants in Annex 3 below), phone calls and personal meetings of CEP participants at planned workshops (April and September 2006; see Annex 3 below). Besides that, Consortium had arranged already an FTP folder at the ECOPROJECT server to put there files for use of all persons involved into CCSI activity. Both login and password are given to all team members. Therefore, the arranged folder “CCSI” containing all the most important documents related to the project is open for acquaintance and any purposes needed. Any comments on the documents placed at the FTP server may be freely sent to any NC, RC, or Project Manager. FTP connection is tested and is assessed by the team as capable of working.

At the Inception Meeting, it was also agreed (discussion with Vladimir Belokopytov) that monitoring data will be transferred to ECS team for loading into BIS by means of FTP organised at the ECOPROJECT server. National teams should upload first monitoring data there by 1 April 2006 as the latest. At first, the formats used will not be unified but later on unification will be made according to the type of data collected. In any case it is recommended to use the first page of the Questionnaire given in Annex 2 below as a cover page for the Monitoring Protocol.

It was also stated (discussion with Vladimir Belokopytov) that monitoring data outlined for observations are compatible with BIS formats. In particular, it was accepted that such data as periods of blossoming, arriving of animals after hibernation, migration, breeding, moulting, etc. will include information on species (Latin name of species is obligatory) and calendar dates of the event (with indication of its beginning, height and end, where possible).

At the Inception Meeting, it was accepted that the GIS-based environmental maps will be reported (in addition to hard copies) in electronic form in coordinated formats in order to be incorporated with IMAPS. Their final versions will be placed at the ECOPROJECT FTP server (see above). Vladimir Uvarov (representative of Consortium and NC in Kazakhstan) provided national teams with recommendations on the range of formats acceptable for the GIS-based map construction. Main requirements are as follows:

- Data should be presented in coordinates GK Pulkovo 42 or WGS 84;

- GPS positioning during monitoring should be carried out in the coordinates mentioned above;

- Vector data should be presented using formats ESRI (*.SHP), MapInfo (MIG/MID), AutoDesk (DXF/DWG), Microsation (*.DGN);

- Raster data should be presented using formats BIL, BMP, GeoTIFF, TIFF, GeoGIF, JPEG, MrSID.

At the Inception Meeting, it was highlighted that monitoring guidelines received from ECS (they were sent to the CCSI Project Manager and RC in the course of pre-meeting correspondence by Lev Neretin and were incorporated into the CCSI Work-plan) should be obligatory taken into consideration while planning and implementing monitoring activities.

5	References

|  | Coastal Systems of Europe, 1998. On-line: http://www.coastalguide.org/typology/typrcol.html |
| --- | --- |
|  | HELCOM, 1998. Red List of Marine and Coastal Biotopes and Biotope Complexes of the Baltic Sea, Belt Sea and Kattegat - including a comprehensive description and classification system for all Baltic marine and coastal biotopes - Baltic Sea Environment. Proceeding No. 75. 120 p. On-line: http://www.helcom.fi/publications/bsep/en_GB/bseplist/; |

Annex 1

List of maps recommended for construction and usage in reports of the CCSI Project

| Figure 1 | Physical map (state and region frontiers, rivers, lakes, roads, settlements) |
| --- | --- |
| Figure 2 | Chart of the Quaternary sediments |
| Figure 3 | Geomorphology of the coastal zone |
| Figure 4 ( | Coastal landscapes (types of vegetation and Protected Areas should be shown – accepted at the Inception Meeting in Baku) |
| Figure 5 ( | Coastal systems |
| Figure 6 | Climatic division of the region into districts |
| Figure 7 | Seasonal dynamics of the average monthly temperature (columns with average temperature by months) |
| Figure 8 | Seasonal dynamics of the average monthly rate of precipitation (columns with average rate of precipitation by months) |
| Figure 9 | Number of days with a blanket of snow |
| Figure 10 | Seasonal dynamics of the wind speed (and wind direction?) (columns with average wind speed by months or wind roses?) |
| Figure 11 | Seasonal dynamics of the sea roughness (columns with average indices of sea roughness by months) |
| Figure 12 | Seasonal dynamics of the sea-surface temperature (columns with average sea-surface temperature by months) |
| Figure 13 | Seasonal dynamics of the sea-surface salinity (columns with average sea-surface salinity by months) |
| Figure 14 | Seasonal dynamics of the sea-surface currents (columns with average sea-surface currents by months) |
| Figure 15 | Flooding of the coast by the sea surges according to the long-term data |
| Figure 16 | Dates of the fast ice appearance and disappearance (e.g., 20.11-10.01) and average duration of the freezing-over period (by columns) |
| Figure 17 | Coastal soils |
| Figure 18 | Coastal vegetation (with total number of recorded species by columns) |
| Figure 19 ( | Distribution of plant species included into the Red Book along the coasts (by groups: algae, fungi, lichens, mosses, vascular plants) |
| Figure 20 | Number of plants included into Red Books of various levels (by groups: algae, fungi, lichens, mosses, vascular plants; columns with maximum coverage of the coastline) |

| Figure 21 | Complexes of fauna (with total number of recorded animals by columns) |
| --- | --- |
| Figure 22 ( | Distribution of animal species included into the Red Book along the coasts (by groups: invertebrates, fishes, amphibians, reptiles, birds, mammals) |
| Figure 23 | Number of animals included into Red Books of various levels (by groups: invertebrates, fishes, amphibians, reptiles, birds, mammals; columns with maximum coverage of the coastline) |
| Figure 24 ( | Human impacts on the coastal systems and the degree to which a certain segments of coast are under threat |

(	types of maps that were considered to be obligatory ones for construction during the Inception Meeting

Annex 2

Questionnaire No. ______ *

for local expert considering his/her opinion on the environmental state of the coastal site and biodiversity of the coast under the study

Date: _______________________________________	Time: _________________________

Site where the questioning takes place (if it is coastal site – GPS co-ordinates): ___________

______________________________________________________________________________

Family name, name, and patronymic name of expert: ________________________________

______________________________________________________________________________

Organisation: _________________________________________________________________

Position, academic status: _______________________________________________________

Address: ______________________________________________________________________

Office phone: __________________________ Home phone ____________________________

Mobile phone: _________________________ E-mail: ________________________________

Family name, name, and patronymic name of the questioning person: __________________

______________________________________________________________________________

Organisation: _________________________________________________________________

Address: ______________________________________________________________________

Office phone: __________________________ Home phone ____________________________

Mobile phone: _________________________ E-mail: ________________________________

*	Please, feel free to use additional sheets of paper if necessary, numbering your answers respectively to the numbers of questions

Assessment of the biodiversity dynamics during the last several years by the expert

1. What plant species are common on the study coast? __________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

2. What plant species decreased in abundance during the last several years? (If it is possible, please, assess these changes quantitatively) ___________________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

3. What do you think are the causes of these changes? __________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

4. What plant species increased in abundance during the last several years? (If it is possible, please, assess these changes quantitatively) ___________________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

5. What do you think are the causes of these changes? __________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

6. What plant species included into the Red Books, are common on the study coast? __________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

7. What plant species included into the Red Books decreased in abundance during the last several years? (If it is possible, please, assess these changes quantitatively) _________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

8. What do you think are the causes of these changes? __________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

9. What plant species included into the Red Books increased in abundance during the last several years? (If it is possible, please, assess these changes quantitatively) _______________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

10. What do you think are the causes of these changes? _________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

11. Is there human impact on the vegetation and of what kind it is (biotope changes, tree cutting, mowing, and burning of grass, pasturing of cattle, etc.)? (If it is possible, please, rank these human impacts from more dangerous to less dangerous) ________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

12. To what extent do these human impacts reduce the plant abundance and biodiversity? (If it is possible, please, assess quantitatively) _______________________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

13. What animal species are common on the study coast? _______________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

14. What animal species decreased in abundance during the last several years? (If it is possible, please, assess these changes quantitatively) ___________________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

15. What do you think are the causes of these changes? _________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

16. What animal species increased in abundance during the last several years? (If it is possible, please, assess these changes quantitatively) ___________________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

17. What do you think are the causes of these changes? _________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

18. What animal species included into the Red Books, are common on the study coast? _______

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

19. What animal species included into the Red Books, decreased in abundance during the last several years? (If it is possible, please, assess these changes quantitatively) _________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

20. What do you think are the causes of these changes? _________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

21. What animal species included into the Red Books, increased in abundance during the last several years? (If it is possible, please, assess these changes quantitatively) _________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

22. What do you think are the causes of these changes? _________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

23. Is there human impact on animals and of what kind it is (biotope changes, illegal hunting, poisoning by pesticides, etc.)? (If it is possible, please, rank these human impacts from more dangerous to less dangerous) ______________________________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

24. To what extent do these human impacts reduce the animal abundance and biodiversity? (If it is possible, please, assess quantitatively) _____________________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

25. Do seasonal (daily) migrations of animals (except birds) exist on the segment of coast under consideration? _________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

26. At what time do they take place (beginning, height, and end)? _________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

27. How many individuals migrate through the coastal site under consideration? _____________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

28. Do migrations of animals (except birds) reduce or change in time? (If it is possible, please, assess these changes quantitatively) _________________________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

29. What do you think are the causes of these changes? _________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

30. Do migrations of animals (except birds) grow or change in time? (If it is possible, please, assess these changes quantitatively) _________________________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

31. What do you think are the causes of these changes? _________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

32. Are there any changes in the behaviour of animals? _________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

33. What do you think are the causes of these changes? _________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

34. To what extent is developed illegal hunting on mammals? What are the species most popular for such hunting? (If it is possible, please, assess impact of hunting quantitatively) ___________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

35. What is the dynamics of human impact on animals? Does it grow, reduce or is it stable? (If it is possible, please, assess these changes quantitatively) _________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

36. Were there cases of mass death of some animal species during the last several years? (If it is possible, please, assess these changes quantitatively) ___________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

37. What do you think are the causes of these changes? _________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

38. At what time do the bird migrations in spring and autumn take place (beginning, height, and end)? _________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

39. How many individuals migrate through the coastal site under consideration? _____________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

40. Do migrations of birds reduce or change in time? (If it is possible, please, assess these changes quantitatively) ___________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

41. What do you think are the causes of these changes? _________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

42. Do migrations of birds grow or change in time? (If it is possible, please, assess these changes quantitatively) __________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

43. What do you think are the causes of these changes? _________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

44. Is there human impact on birds and of what kind it is (biotope changes, hunting, catching of singing and hunting birds, etc.)? (If it is possible, please, rank these human impacts from more dangerous to less dangerous) ______________________________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

45. To what extent these human impacts reduce the bird abundance and biodiversity. (If it is possible, please, assess quantitatively) _______________________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

46. Do these human impacts grow, reduce or are they stable? (If it is possible, please, assess these changes quantitatively) ______________________________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

47. To what extent is developed illegal fishery (in particular of sturgeon fishes)? _____________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

48. How can you assess the share of illegal fishery as compared to official data (state fishery, fishing cooperative associations, etc.)? ______________________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

49. What kinds of human impacts in general you consider the most dangerous for the segment of coast under consideration? (If it is possible, please, rank these human impacts from more dangerous to less dangerous) ______________________________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

50. What measures you consider the most important for improvement of the environmental state of the segment of coast under consideration? _________________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

51. What important questions are absent in this Questionnaire? Would you like to name them and to answer on them? ______________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

______________________________________________________________________________

Annex 3

Report on the CCSI Inception Meeting
(Baku, Azerbaijan, 12-13th January, 2006; see List of Abbreviations
in the beginning of the Report)

CCSI Inception Meeting was organised by ACEP in Baku (Azerbaijan) and took place on 12-13th of January 2006 in the House of Government (see photos below). List of the Inception Meeting Participants is presented in Table A-1 while the Meeting Agenda is given in Table A-2. Full text of the Inception Meeting Minutes (11 pages) will be sent upon a request. Main agreements on the implementation of the CCSI Project as well as the plan on major activities, responsibility, milestones, and general timeline (see Table A-3) are presented below.

Table A-1	List of the Inception Meeting Participants

| Name | Organisation | Position in CCSI Project | Contact information |
| --- | --- | --- | --- |
| Lev Neretin | CEP | - | lev.neretin@undp.org |
| Bakhtiyar Muradov | CEP | - | BMuradov@Caspian.in-Baku.com |
| Ziyafet Kerimov | CEP | - | caspian@caspian.in-baku.com |
| Vladimir Belokopytov | ECS | - | v.belokopytov@gmail.com |
| Elchin Iskenderov | ACEP | Project Manager | Phone: (+7 10 994 12) 92-30-39; E.Iskenderov@acep.in-baku.com |
| Vladimir Pogrebov | ECOPRO | Regional Coordinator | Phone/fax: (+7 812) 740-57-03; pogrebov@ecopro.spb.ru |
| Tofik Hasanov | ACEP | National Coordinator in Azerbaijan | t.hasanov@acep.in-baku.com |
| Vladimir Uvarov | KAAE | National Coordinator in Kazakhstan | uvarov@kape.kz |
| Omid Sedighi | DOE | National Coordinator in Iran | osedighi@gmail.com |
| Andrew Filippov | ECOPRO | National Coordinator in Russia | Phone/fax: +7 812 740-57-03; filippov@ecopro.spb.ru |
| Aman Babayev | NIDFF | National Coordinator in Turkmenistan | babayevICC@online.tm |
| Manaf Suleymanov | ACEP | Azerbaijan Expert | office@acep.in-baku.com |
| Natalie Nazarova | ACEP | Azerbaijan Expert | office@acep.in-baku.com |
| Serik Timirkhanov | KAAE | Kazakhstan Expert | serik@kape.kz |
| Valery Svetlakov | KAAE | Kazakhstan Expert | valery@kape.kz |

Table A-2	Inception Meeting Agenda

| Time | Event |
| --- | --- |
| 12th January 2006 |
| 900-930 | Registration of Inception Meeting participants |
| 930-1000 | Greetings of participants by CEP representative in Baku (Bakhtiyar Muradov), election of Chairman and acceptance of Agenda |
| 1000-1020 | CEP activities in the Caspian Region (Lev Neretin) |
| 1020-1040 | Coffee break |
| 1040-1100 | ECS Project and it possible links with the CCSI Project (Vladimir Belokopytov) |
| 1100-1230 | CCSI implementation: aims and milestones (Vladimir Pogrebov) |
| 1230-1330 | Lunch |
| 1330-1530 | Statements of National Coordinators |
| 1530-1600 | Coffee break |
| 1600-1730 | Questions and answers, discussion, acceptance of Agenda for 13th January 2006 |
| 1900 | Joint Dinner |
| 13th January 2006 |
| 930-1030 | CCSI management and interaction of participants (Elchin Iskenderov) |
| 1030-1100 | Coffee break |
| 1100-1230 | Questions and answers, discussion |
| 1230-1330 | Lunch |
| 1330-1730 | Cultural Programme / Sightseeing |

Main agreements on the implementation of the CCSI Project are as follows:

- An approach proposed by RC - Vladimir Pogrebov is approved in general.

- Possibilities of constructing all maps that are considered to be desirable in order to characterize environment of the Caspian Sea coastline in a most detailed way (see Annex 1) were discussed. However, taking into account the Project timeline it was concluded that this work is labour consuming and not all littoral states will be able to finish it in time. Five main types of maps (they are ticked off in Annex 1) were considered to be obligatory ones.

- It is agreed that all CCSI NCs should prepare and deliver to RC Biodiversity Monitoring Programmes, which should contain information on the type of ecosystem selected for monitoring, selected period of monitoring observations and belonging of their objects to a specific group of monitored objects.

Deadline for National BMPs delivering is 20 January 2006.

Following classification of ecosystems, objects, and seasons will be used:

Ecosystems:

- Marine

- Freshwater

- Wetland

- Forest

- Desert (are added by Turkmenistan NC)

- Mountain (not to be studied within the CCSI Project)

Seasons (fieldwork programme should be worked out in details):

- Spring

- Summer

- Autumn

- Winter

Groups of plants and animals to be studied:

Plants

- Algae

- Fungi

- Lichens

- Mosses

- Vascular plants

Animals

- Invertebrates

- Fishes

- Amphibians

- Reptiles

- Birds

- Mammals

- It is accepted that species included into IUCN Red List are priority-driven; their categories should be shown in all tables prepared.

- CCSI Project participants approved to organize:

- The second meeting (for discussion of the GT results; late April – early May, 2006) in Iran (Omid Sedighi proposed to have it in Ramsar); and

- The third meeting (for discussion of the BMP interim results; late September) in Kazakhstan (Kazakhstan delegation proposed to have it in Aktau).

- Correction of the up-to-date coastline location will be fulfilled on the basis of the latest satellite image available, which will be used by all National Teams (Kazakhstan team is responsible for over-all activity; instructions on formats were given by Kazakhstan experts to all NCs). Deadline – 16 February 2006.

- Budget proposals for fieldwork should be sent by NCs to the Project Manager Elchin Iskenderov not later than 20 January 2006.

Major activities, responsibility, milestones, general timeline and related issues are presented in Table A-3.

Table A-3	Work-plan on major activities, responsibility, milestones, and general timeline

| What | Who | When | Payment |
| --- | --- | --- | --- |
| Contract signing | UNOPS / ACEP | 01 December 2006 | $30,000 |
| Inception Meeting (Baku) | RC / NCs | 12-13 January 2006 |  |
| Work-plan | RC / NCs | 20 January 2006 |  |
| Inception Report | RC / NCs | 20 January 2006 | $50,000 |
| National Ground-Truthing Studies | NCs | 16 January – 31 March 2006 |  |
| National GT Reports | NCs | 21 April 2006 |  |
| Regional Meeting (Ramsar, Iran) | RC / NCs | 26-27 April 2006 |  |
| Regional CCSI Report | RC / NCs | 19 May 2006 | $35,000 |
| BMP Studies | NCs | 16 January 2006 - 5 January 2007 |  |
| Regional BMP Meeting (Aktau, Kazakhstan) | RC / NCs | 27-28 September 2006 |  |
| National BMP Reports | NCs | 5 January 2007 | $35,000 |
| Final BMP Report | RC / NCs | 28 February 2007 | $48,600 |
| Total: |  |  | $198,600 |