Annex 1- Terms of Reference

### Caspian Environment Programme

### Towards a Convention and Action programme for the Protection of the Caspian Sea Environment Project (CEPSAP)

### Terms of Reference for Final Evaluation

# Introduction

The Monitoring and Evaluation (M&E) policy at the project level in UNDP/GEF has four objectives: i) to monitor and evaluate results and impacts; ii) to provide a basis for decision making on necessary amendments and improvements; iii) to promote accountability for resource use; and iii) to document, provide feedback on, and disseminate lessons learned. A mix of tools is used to ensure effective project M&E. These might be applied continuously throughout the lifetime of the project – e.g. periodic monitoring of indicators -, or as specific time-bound exercises such as mid-term reviews, audit reports and final evaluations.

In accordance with UNDP/GEF M&E policies and procedures, all regular and medium-sized projects supported by the GEF should undergo a final evaluation upon completion of implementation. A final evaluation of a GEF-funded project is required before a concept proposal for additional funding can be considered for inclusion in a GEF work program. However, a final evaluation is not an appraisal of the follow-up phase. Final evaluation is intended to assess the relevance, performance and success of the project. It looks at early signs of potential impact and sustainability of results, including the contribution to capacity development and the achievement of global environmental goals. It should also identify/document lessons learned and make recommendations that might improve design and implementation of other UNDP/GEF projects.

##### Project Background

##### The project is a major, and in many ways the leading component of the Caspian Environment Programme  (CEP) which was formally launched in May, 1998, following the successful conclusion of the Ramsar Interim Steering Committee Meeting (SCM). The Ramsar Interim SCM concluded a series of initiatives, meetings, missions, communiqués, declarations starting from 1991 which all had one element in common: they all reflected a strong regional desire for environmental cooperation to safeguard the stressed environment of the Caspian Sea.

CEP reflects the regional decision to collaborate towards the long term protection and sustainable use of the Caspian natural resources for present and future generations. CEP is an inter-governmental umbrella environmental programme of the five Caspian littoral countries namely Azerbaijan, Islamic Republic of Iran, Kazakhstan, Russia and Turkmenistan.  It is envisaged as a set of parallel project pursuing common environmental goals and objectives.

From its inception the CEP has been assisted by the International Partners namely EU through Tacis and the Global Environment Facility (GEF) through the UNEP, UNDP and the World Bank. The international support has moved through two major phases one from 1998 to 2003 (Phase I) when the CEP Programme Coordination Unit (PCU) was based in Baku and from 2004 till now (Phase II) during which the PCU was transferred to Tehran.  During Phase I GEF provided $ 8.5 millions to CEP through project implemented/executed by UNDP, UNEP, World Bank and UNOPS.  EU support during this period reached Euro 5.5 millions.  Noting the considerable progress made under the Phase I the international community continued its support throughout the phase II with some $ 6 millions from GEF and Euro 5.9 Millions from EU. CEP also benefited from support from the private sector .

The CEPSAP project is the management vehicle of the GEF support to the CEP in its Phase II. The project is a key element in support of the CEP in the preliminary implementation of the Strategic Action Programme and continuance of the Convention process.  Implementation of this project is undertaken by UNDP with execution by UNOPS.  The objectives of this project are to:

- Commence implementation of the SAP in three priority areas: Biodiversity, Invasive Species and Persistent Toxic Substances.

- Continue with specific capacity building measures to ensure a regionally owed CEP coordination mechanism capable of full implementation of the SAP and regional coordination of the NCAPs.

- Strengthen the environmental legal and policy frameworks operating at the regional and the national levels and where necessary improve implementation and compliance of those frameworks.

- Achieve tangible environmental improvements in SAP priority areas by implementation of small-scale investments supported by a small matched grants programme

The project office is based in the CEP PCU located in Tehran, I.R. Iran and is executed in close coordination with an EU-Tacis CEP support project targeting fisheries and sustainable coastal development. UNEP’s Regional Office for Europe has assumed responsibility for guiding the Convention process under a Memorandum of Understanding to be signed with UNOPS.

# Objectives and Scope of the Final Evaluation

The objective of the final evaluation is to enable the UNDP-GEF, UNOPS, participating countries and the stakeholders in the Caspian region, namely the five littoral countries, to assess the project outputs, their impact and sustainability, and to take decisions on the future orientation and emphasis of the subsequent phases of the GEF intervention.

The final evaluation should address such issues as:

Project Design

- relevance of project design within the framework of GEF guidelines and global concern regarding the Caspian Sea;

- appropriateness of the project’s concept and design to the current economic, institutional and environmental situation in the target region;

- contribution of the project to the overall development objective as declared in the Project Document; and

- the likely impact of project interventions and sustainability of project outputs.

## Project implementation

- general implementation and management of the UNDP/GEF project by the PCU in terms of quality of inputs and activities, adherence to workplans and budgets, major factors which have facilitated or impeded the progress of project implementation;

- adequacy of management arrangements as well as monitoring and backstopping support given to the project by all parties concerned;

- institutional set-up through the Project Steering Committee and various Expert groups e.g Regional Advisory Groups (RAGs) and the degree to which it has encouraged full involvement of the countries;

- inputs of the Governments of the five countries at national and local levels;

- responsiveness of project management to changes in the environment in which the project operates;

- Collaboration with UNEP Regional Office on Tehran Convention related work

- Relevance , outreach and effectiveness of the Matched Small Grants Programme.

- UNOPS execution;

- co-operation among project partners (UNDP/GEF, UNEP, IAEA , IMO  UNOPS, Project Team, National Governments and international and national organisations and NGOs).

## Project impact

- achievements of the project against the original objectives, outputs and activities as detailed in the project document and the Project Implementation Plan;

- awareness of the participating countries regarding project outputs;

- level of ownership of the project by the participating countries;

- commitment of countries to support the ongoing project;

- likely degree of support from the Countries’ Governments in integrating the project objectives into their national development programmes and other related projects, and how well the project fits into their national development policy;

- impacts on policy and strategy of countries;

- project impact on improving the capacity to prepare and implement collaborative, targeted and effective efforts for the management of the Caspian region ;

- project impact on enhancing inter-agency and inter-ministerial co-operation in each country and on regional cooperation;

- cooperation among and engagement of the international organisations, NGOs and other stakeholders;

- cooperation with sister projects in the GEF IW portfolio, such as the Black Sea Basin, Kura-Arax  basin  and the Volga  Project;

- sustainability of the project’s impact.

# Products Expected from the Evaluation

The end result of this evaluation exercise should be a Final Evaluation Report with findings, assessment of performance, lessons learned, recommendations, description of best practices, and an “action list” in a certain area of particular importance for the project. The evaluation team should also submit a Mission Report, which can be submitted as separate report or combined into the Final Evaluation Report.

Based on the objectives and methodology of the final evaluation, the evaluation team should provide conclusions and recommendations, including:

- general recommendations on the implementation of the project;

- the degree to which the project objectives have been met;

- significant lessons that can be drawn from the experience of the project and its results, particularly those elements that have worked well and those that have not;

- recommendations on further action upon completion of the current project and for the implementation of the subsequent GEF interventions.

The evaluation mission will complete the Project Evaluation Information Sheet (PEIS) according to the existing format and produce a report according to the structure outlined in the UNDP Guideline for Evaluators. In addition, the mission report should contain at least the following annexes:

- Itinerary

- List of meetings attended

- List of persons interviewed

- Summary of field visits

- List of documents reviewed

- Any other relevant material

As the report is the product of an independent evaluation, it is up to the evaluator(s) to make use of the information provided during the mission. However, the evaluator is responsible for reflecting any factual corrections brought to his/her attention prior to the finalisation of the report. Therefore, in order to ensure that the report considers the view of all parties concerned, is properly understood, and is factually accurate, it is necessary for the evaluator to submit draft reports to the project, UNDP/GEF and UNOPS. UNOPS will revert promptly with collective feedback from project partners in order that the evaluator may finalise the report. The final version of the evaluation mission report should be submitted in electronic format (MS Word) and hard copy to UNOPS no later than 31 July 2007.

Methodology

The evaluation will consist of three activities:

- document review;

- field visits; and

- interviews with individuals who are either affiliated to the project in some way or who have or might be expected to be impacted by the project.

## Document Review

The evaluation team shall familiarise itself with the project through a review of relevant documents prior to the field visits. These documents include inter alia:

- Project Document

- Project Implementation Plan

- GEF Project Implementation Review (PIR) for all the years of project implementation

- Minutes of meetings of Steering Committee and RAGs  2004-2007

- UNDP Handbook for Programme Managers: Results-Oriented Monitoring and Evaluation

- Strategic Action Programme and NCAPs

Hard copies of selected documents, which are not available through the internet, shall be made available to the evaluation team by the Programme Coordination Unit.

## Field visits

The evaluation team will visit all five participating countries.

## Interviews

The evaluator(s) will carry out interviews with:

- Project Staff of the Programme  Coordination Unit

- Programme Coordinator, Project Manager s of CEP component projects

- SAP Implementation Coordination Assistants  (SAPICs) and selected National Focal Points (NFPs)

- Leading International Consultants for the Project Components

- Selected members of the Project Steering Committee

- Selected members of the National Expert Groups

- Representatives of relevant international and national NGOs that took active part in the project implementation,

- Other constituencies and stakeholders not directly involved in the project who may have experienced, or may be expected to experience, its impacts.

Although the independent evaluators should feel free to discuss with the authorities concerned all matters relevant to their assignment, they are not authorised to make any commitment on behalf of UNOPS, UNDP or GEF.

Where a field visit is not feasible due to logistical or technical reasons, the Consultant(s) will carry out an interview by other means (i.e. e-mail/phone).

# Evaluation Team

The Evaluation team will consist of two consultants: one responsible for governance issues including institutional settings, Caspian Convention, stakeholder involvement, NGOs participation etc. and second consultant will be responsible for natural resource issues, biodiversity impact, fisheries issues, pollution etc.  The consultants will have considerable knowledge and experience regarding the GEF IW operational programme; and will have in-depth knowledge of international water policy and legislation, including the EU Water Framework Directive. The consultants will possess good knowledge of water basin management issues and relevant scientific understanding and in-depth experience of project evaluation techniques, particularly of those projects which are funded by GEF. The consultants shall not have been directly involved in the design or implementation of the project.

The specific requirements are the following:

- knowledgeable and experienced on international waters related issues, 
- knowledgeable and experienced on GEF/WB/UNDP related issues;
- experienced in the Caspian region;
- experienced in monitoring or evaluations with emphasis on GEF project evaluation;
- no prior involvement in the Caspian Environment Programme.

Implementation Arrangements

Management arrangements: The team of international consultants will be hired through a contract with UNOPS. Local logistical/translation support will be hired by UNOPS through an individual contract directly with the identified individual. The travel of the evaluation team will be organized by UNOPS outside the scope of the contract through direct purchase of ticket and payment of travel allowances or through the involvement of UNDP Country Offices for local travels. The Programme Coordination Unit will provide the required assistance with the arrangement of local travel itinerary and schedule of meetings.

Time frame: The evaluation mission will start by June 2007 from a visit of the international consultant to Tehran, PCU for the recognition and first meeting with the project management team. Following the first visit, the consultant should submit to UNOPS a detailed itinerary of subsequent filed visits for approval and arrangement of the travel. The overall duration of the contract with the international consultant should be no more that 34 working days, and the final version of the evaluation report should be submitted to UNOPS not later than October 31, 2007.

Annex 2.  Conceptual Model for the Evaluation

The Evaluators developed a conceptual model to guide data collection and analysis. This is described below.

Contents of the Conceptual Model

At the planning stage, the Evaluators had to determine the ‘substantive content’ of the evaluation.

This substantive content would later serve to guide and to structure the collection and the analysis of data. The substantive content was initially developed during the planning phase, and it was continually improved during later phases of the evaluation as more information, findings and understanding came to light.

This substantive content had two, complementary components described below.  Combined, they provided a comprehensive set of issues and questions to be addressed through the evaluation.

1)	The logical framework of the Project:

The logical framework (Objectives, Outcomes, Outputs, Activities and Indicators) evolved during the 3 years of project implementation. After reviewing the various logical frameworks, the Evaluators considered that the Outcomes and Indicators in the PIR 2006/07 provided the most relevant, comprehensive and structured framework.

The PIR 2006/07 provide 45 indicators, many of which are actually outputs, many others activities. Collectively, these 45 indicators covered the entire substantive nature of the Project, and therefore provided the basis for most interviews and data collection.

In this connection, the Evaluators set out to determine progress towards each indicator. This led to a large pool of information as to whether the project was successful, based on the initial expectations and design, as set out in the project document.

2)	Other issues

As discussed in the Evaluation report, the project logical framework had some weaknesses and gaps. Complementary questions had to be formulated to address these issues. In addition, during the project, there were unforeseen and unanticipated impacts. Complementary questions had to be formulated to address these issues. Accordingly, the Evaluators prepared a complementary list of questions to address these issues. The origin of these was (i) latest guidance related to International Waters projects from GEF and UNDP (ii) key and cross-cutting issues that arose during the evaluation mission; (iii) guidance from GEF and UNDP-GEF on adaptive management and refinement of indicators since the inception of this project; (iv) latest guidance from GEF on terminal evaluations.

This second layer of issues led to a series of related questions for each stakeholder met.  Most of these issues and related questions were discussed with respect to each Outcome, to related outputs and as applicable to all or some of the indicators described in (1) above.  Of course, the issue and question mix varied depending upon the stakeholder and the time allowed.  These cross-cutting questions are:

- Effectiveness

- Were the outputs produced and/or activities conducted as planned?

- What was the quality of outputs?

- Did the activities have an impact?

- For studies, surveys and reports, this generally translates into were they useful and used?

- For recommendations, this generally translates into were they uptaken and embedded?

- For pilot and demonstration activities, this generally translates into were they disseminated/replicated and did they have measurable impacts?

- What changed as a result of the activity: personal changes or changes in institutional behaviour? What are stakeholders doing differently now, at the end of the project then they were at the beginning?

- Efficiency

- Were the activities conducted on time and on budget?

- Were staff working efficiently?

- Did logistical and administrative support minimize delays and achieve timely work?

- What is it reasonable to expect given the timeframe of the project?

- Is there evidence of project seeking lower cost options?

- Sustainability

- Are the impacts sustainable? What will happen if CEP-SAP stops?

- What governance reforms can be attributed to the project activities?

- What institutional and policy reforms can be attributed to the project activities?

- What budgetary reforms can be attributed to the project activities?

- Relevance

- Is the project still relevant to country priorities?

- Is it relevant to national laws/policies?

- Country ownership/drivenness,

- Does the stakeholder exhibit knowledge of the project?

- How appropriate is stakeholder participation?

- What is the level of cross-sectoral participation?.

6.	Overall views of the project/Other issues and or comments?

- What are the main strengths of the project. What are the project’s main weaknesses?

Application of the Conceptual Model

In line with standard evaluation procedure, the conceptual model was transformed into a framework for inquiry that was used to guide all interviews and data collection but was never used in printed form.

It was used as follows:

- In interviews, the Evaluators used the 45 indicators as a checklist. They ensured that all relevant indicators were discussed in each interview;

- When reviewing documentation, the Evaluators reviewed all outputs associated with the 45 indicators in the PIR 2006/07;

- In interviews, the Evaluators used the ‘cross-cutting’ question list, and discussed all relevant issues in each interview. In many cases, the cross-cutting questions were asked in association with the relevant indicators;

- When reviewing documentation, the findings related to each ‘cross-cutting question’ were noted.

To summarize, the following matrix was used as the conceptual basis for each interview and for all data collection. However, it should be noted that it was not used systematically, but used as a checklist to ensure that all important issues relevant to the interviewee were covered.

|  | Question/Issue 1 | Question/Issue 2 | Question/Issue 3 | Question/Issue 4 | Question/Issue 5 | Question/Issue 6 |
| --- | --- | --- | --- | --- | --- | --- |
| Status of Indicator # 1 |  |  |  |  |  |  |
| Status of Indicator # 2 |  |  |  |  |  |  |
| Status of Indicator # 3 |  |  |  |  |  |  |
| Status of Indicator 4 - 44 |  |  |  |  |  |  |
| Status of Indicator # 45 |  |  |  |  |  |  |

Annex 3.  Mission Itinerary and List of Persons Interviewed

| Date/Time | Name of person | Title/ Institution & Notes |
| --- | --- | --- |
| June 14 – 18 2007 | Islamic Republic of IRAN |  |
|  | Hamid Ghaffarzadeh | CEP-SAP Project Manager ; Project Coordination Unit |
| June 15 | IR Iran |  |
|  | Igor Mitrofanov | CEP-SAP/PCU Biodiversity Expert |
|  | Fritz Schlingeman | UNEP* - Leader of project’s Convention and protocol work. |
|  | Lena Nielsen | EU TACIS* -- Task manager for EU-funded projects in Caspian region. |
| June 16 | IR Iran |  |
|  | Nini Makhzani | CEP-SAP/PCU Public Awareness Expert |
|  | Ali Mohammadi | CEP-SAP/PCU MSGP/MEG Manager |
| June 17 | IR Iran |  |
| 9:00 AM | Mr. Majid Saber Mr. Mahmoud Dibaei | Head, Secretariat for Caspian Sea Affairs, Ministry of Foreign Affairs Expert |
| 11:00 | Dr. S.M.B. Nabavi | Deputy, Department of Environment & General Director of Marine Environment Bureau & CEP Iranian National Focal Point |
|  | Ms. Parvin Farshchi | CEP-SAPIC for Iran |
|  | Mr. Farahani Rad | Management and Planning Organisation |
| 14:30 | Mr. Mohammad Reza Sheikholeslami | CEP-SAP/PCU Pollution Expert |
| 15:30 | Mr. Norouz Tavana | Interim CEP Programme Coordinator |
| 13:00 | Dr. Sh. Nezami Mr. Mojadee Mr. Hossien Negarestan | Vice Minister, Ministry of Agriculture and Jihad, and Head, Iran Fisheries Agency Deputy Head, Iran Fisheries Agency Head of Dept. of Marine Ecology, Iranian Fisheries Research Organization |
| 14:30 | Mr. Knut Ostby Mr. Saeed Ferdows | UNDP Resident Representative UNDP Programme Officer |
| 17:00 | Hamid Gefarzadeh | CEP-SAP Project Manager |
| June 18 | IR Iran |  |
| 9:00 | Yousef Filizadeh | CEP-SAP Anzali Lagoon Pilot Project Manager |
| 10:30 | Mr. Haghshenas | Member of Parliament – Anzali Port |
| 10:30 | Ali Asghar KhaniPour | Aquaculture Institute, Iranian Fisheries Research Organization, Ministry of Jihad Agriculture. |
| 11:00 | Ali Reza Valipour | Fish Nutritionist, Aquaculture Institute, Sefirude Fisheries Research Station |
| 14:00 | Dr. Mohammad Pourkazemi | International Sturgeon Research Institute |
| July 19 - 22 | AZERBAIJAN |  |
| 13:00 | Ms. Eugenie Magomedova | CEP-SAP Baku Sub-office Programme Assistant and Azerbaijan MSGP/MEG manager |
| 16:00 | Mr. Gouseyn Bagirov | Minister of Ecology and Natural Resources & CEP Azerbaijan Focal Point |
| 16:00 | Mr. Rasim Sattarzadeh | Head of Biodiversity Policy Department, Ministry of Ecology and Natural Resources, & CEP-SAPIC |
| June 20 | Azerbaijan |  |
| 10:00 | Mr. Rasim Sattarzadeh | CEP-SAPIC |
| 11:00 | Mr. Talat Tangerli | Director, Chevra NGO Project Manager, MSGP: “Promoting Sustainable Development in local communities of Caspian region through alternative sources of energy” Field visit to MSGP site |
| 11:00 | Ms. Eugenie Magomedova | CEP-Baku Sub-Office Programme Assistant and MSGP/MEG manager |
| June 21 | Azerbaijan |  |
| 10:00 | Ms. Sadagat Mammadova | Head of Division, Ministry of Ecology and Natural Resources & Member of Biodiversity and Invasive Species RAG |
| 11:00 | Ms. Latifa Huseynova | Former Head of Caspian Complex Environmental Monitoring Dept. and Member of Pollution RAG |
| 12:00 | Mr. Mehman Maksud Akhundov | Director, Azerbaijan Fisheries Research Institute and Member of Fisheries RAG |
| 15:00 | Mr. Faiq Askerov | Environmental Manager, BP Azerbaijan |
| 16:00 | Ms. Aytan Shirinova | CEP-SAP MPPA, Azerbaijan |
| June 22 | Azerbaijan |  |
| 10 :00 | Ms. Jamila Ibrahimova | Senior Programme Advisor, UNDP Azerbaijan |
| 11:00 | Mr. Islam Mustafaev | Chairman of NGO “Ruzgar” |
| 12:00 | Mr. Rasim Sattarzadeh | CEP-SAPIC |
| 16:00 | Capt. Shahlar Mammedov & Capt. Vamik Rahimov | Deputy Head, State Maritime Administration, & Head, Maritime Inspection, State Maritime Administration |
| June 21 - 23 | KAZAKHSTAN (Astana & Almaty) |  |
| 9:00 – 11:00 | Mr. Serik Akhmetov | SAPIC for Kazakhstan; Office located in Ministry of Environmental Protection. |
| 11:00 | Mursalnabi Tuyakbaev | Chief of Division, Dept. of International Organizations and Multi-lateral Cooperation. Ministry of Foreign Affairs |
|  | Mr. Rakhat Kuspanov | Referent, Ministry of Foreign Affairs |
| 13:00 | Ms. Janar Mautanova | Ministry of Environmental Protection, Head of Division for International Projects and Conventions. |
| 15:00 | Mr. Kalibenov Bekzhan | Ministry of Economy, Budget and Planning (MEBP); Head of Department of Investment Policy |
|  | Mr. Nurym Ayazbaev | Head, Unit for Internal Resources Investment Planning, MEBP. |
| June 22 | Kazakhstan, Astana |  |
| 9:00 | Mr. Nurakhmet Bizhanov | Chairman, Committee for Government Control of Emergency Situations and Industrial Safety (CGCESIS), Ministry of Emergency Situations. |
|  | Mr. Aitzhan Shagirov | Head of Division; CGCESIS |
| 11:00 | Mr. Yuri Romashov | Committee of Fishery Industry, Ministry of Agriculture (MoA) |
|  | Ms. Elena Ukhova | Main Specialist; Committee of Fishery Industry, MoA |
| 12:00 | Ms. Elvira B. Ibrayeva | Ministry of Environmental Protection; Deputy Director of Legal Policy and International Cooperation Department |
| 14:00 | Mr. Khairbek Mussabayev | Deputy Chairman, Forestry and Hunting Committee (FHC), MoA |
|  | Mr. Aidar Daurbaev | Head of Wildlife Management Division, FHC, MoA |
| 16:00 | Mr. Nurlan Sirazhev | Head, Department of Labor Protection and Environment, KazMunaiGaz National Oil Company, Ministry of Energy and Mineral Resources |
|  | Ms. Olga Ongarbaeva | Ministry of Energy and Mineral Resources |
| June 23 | Kazakhstan, Almaty |  |
| 10:30 | Mr. Alexander Bragin | Director -- Law, Policy and International Cooperation Department, MEP |
|  | Anara Kalelova | Chief of Department; KazHydroMet |
|  | Olga ---, Kristina Natalaya | Head of International Cooperation Unit, KazHydroMet. Head of Caspian Problem Division, KazHydroMet |
| 12:00 | Serik Timirkhanov | Dep. Director for Science; Kazakhstan Agency for Applied Ecology (Coastal Sites Survey) |
| 14:00 | Serik Akhmetov | SAPIC, Kazakhstan |
| June 23 - 27 | TURKMENISTAN |  |
|  | Reading Documentation |  |
| June 24 | Turkmenistan |  |
|  | Reviewing notes and planning evaluation report |  |
| June 25 | Turkmenistan |  |
| 10:00 | Ms. Gozel Orazdurdyyeva | CEP-SAPIC |
| 11:00 | Mr. Michael Wilson | Advisor, TACIS Programme, Turkmenistan |
| 12:00 | Ms. Jakhan Annatcharyeva | Biodiversity Expert, NCAP Expert, BDIS RAG member |
| 15:00 | Ms. Shirin Karryeva | Head, International Projects Dept., Ministry of Nature Protection |
| 15:30 | Mr. Vladimir Glazovsky | Head, Environment Dept., Ministry of Nature Protection |
| 16:00 | Ms. Olga Byashimare | Representative of NGO “Lalezar” and MEG beneficiary. |
| 18:00 | Mr. Makhtumkuli Akhmuradov | Minister of Nature Protection and CEP-SAP National Focal Point |
| June 26 | Turkmenistan |  |
| 11:00 | Ms. Galina Ivanova Ms. Nina Nikolayeva | School no. 13, Turkmenbashi and MEG Recipient |
| 12:00 | Ms. Tatiana Tzura Ms. Garayeva Akbike Ms. Gurbanova Nartach | Caspian Ecological Service (Casp Eco-control), Turkmenbashi, Ministry of Nature Protection. |
| 15:00 | Mr. Davran Yavan | Namys Company and MSGP Recipient, Turkmenbashi |
| 16:00 | Mr. Berdi Berdiyev | Deputy Director, Hazar State Reserve, Turkmenbashi |
| 17:00 | Mr. Oleg Voitsekhovich | Pollution Advisor, EU-TACIS Caspian Water Quality Monitoring and Action Plan for Areas of Pollution Project Concern |
| June 27 | Turkmenistan |  |
| 10:00 | Mr. Nikita Barsuk | Deputy Director, Emerol, Turkmenistan |
| 11:00 | Mr. Gijs Kok | Project Manager, EU-TACIS Caspian Water Quality Monitoring and Action Plan for Areas of Pollution Project Concern |
| 12:00 | Mr. Timur Berkeliyev | WWF Representative, Turkmenistan |
| 13:00 | Ms Inessa Pimenova Mr. Vladimir Budnev | MEG Beneficiaries |
| 15:00 | Mr. Kochumov Yagmur | Head of International Legal Department, Ministry of Foreign Affairs, and CEP legal expert |
| 16:00 | Mr. Rovshen Nurmuhamedov | Environment and Energy Portfolio Manager, UNDP |
| June 24 -27 | RUSSIAN FEDERATION |  |
| June 24 | Travel; reading documents |  |
| June 25 | Russian Federation -Moscow |  |
| 12:00 – 17:30 | Tatyana Butylina | SAPIC for Russia; Staff member of Center for International Projects (CIP). |
|  | Anatoly Saveliev | Staff member of CIP. |
| June 26 | Russian Federation -Moscow |  |
| 10:00 – 12:00 | Mr. Sergei Tikhonov | Director of CIP and Head of CEP Project Russia National Coordination Unit |
|  | Ms. Natalya Tretiakova | Ministry of Natural Resources (MNR); Dept of International Cooperation |
|  | Ms. Natalya Kutaeva; | Ministry of Transport, State Marine Rescue Administration |
|  | Mr. Alexander Postnov | Roshydromet |
|  | Mr. Alexander Korshenko | Head of Marine Pollution Monitoring Lab; State Oceanographic Institute of Roshydromet |
|  | Mr. Anatoly Totsky | Dept of International Cooperation; MNR |
| June 27 | Russian Federation -Moscow |  |
|  | Reviewing notes and planning evaluation report |  |
|  | Ms. Irina Bredneva | UNDP-Russia |
| 28 - 30 June | GERMANY | Frankfurt airport hotel; End of Mission Wrap up; Evaluators compare notes and conduct joint telephone interviews of key stakeholders. |
|  | Andrew Hudson* | UNDP-GEF; International Waters |
| 29 June | GERMANY – Frankfurt |  |
|  | Tim Turner* | International Biodiversity CEP-SAP Expert, and lead Expert on TDA-SAP Update |
|  | Simon Goodman* | Seals survey |
|  | Steve de Mora* | IAEA; Pollution assessment and analysis |
|  | Katarina Mogulova * | POPs Expert |
| 30 June | Evaluators return to respective home bases. |  |
| 3 July | Vladimir Mamaev* | UNDP/GEF, IW RTA, Bratislava |
| 12 July | Peter Taylor* | Manager, Oil Spill Regional Preparedness Initiative (Caspian Sea – Black Sea), IPIECA |
| 18 July | Amy Evans* | Consultant, World Bank |

* - telephone interview

Annex 4.  List of Documentation Reviewed

| Title | Date | Author |
| --- | --- | --- |
| CEP and CEP Participating Countries |  |
| Strategic Action Programme for the Caspian Sea | 2002 | CEP Participating Countries |
| Project Document: ‘Towards a Convention and Action Programme for the Protection of the Caspian Sea Environment’ | 2004 | UNDP/GEF and CEP Participating Countries |
| Draft Protocol On “Biodiversity Conservation Protocol To The Framework Convention For The Protection Of The Marine Environment Of The Caspian Sea”. | April 2006 | CEP Participating Countries |
| Draft Protocol On “Environment Impact Assessment In A Transboundary Context To The Framework Convention For The Protection Of The Marine Environment Of The Caspian Sea”. | September 2006 | CEP Participating Countries |
| Draft Protocol On “Concerning Regional Preparedness, Response And Co-Operation In Combating Oil Pollution Incidents” | 2006 | CEP Participating Countries |
| Draft Protocol For The “Protection Of The Caspian Sea Against Pollution From Land-Based Sources [And Activities]”. | 2006 | CEP Participating Countries |
| Strategic Action Programme for the Caspian Sea (Update) | October 2006 | CEP Participating Countries |
| Framework Convention for the Protection of the Marine Environment of the Caspian Sea (the Tehran Convention) | 2006 | CEP Participating Countries |
| RPAP - Regional PTS Action Programme for the Caspian Region. | 2006 | CEP Participating Countries |
| Decisions of the First Meeting of the Conference of the Parties to the Tehran Convention | May 2007 | Tehran Convention Conference of the Parties TC COP 1 |
| Tehran Convention COP Programme of Work, June 2007 – May 2008 | May 2007 | TC COP 1 |
| Tehran Convention: Note by the Interim Secretariat on the Status of Development of Priority Protocols | May 2007 | TC Secretariat |
| Caspian Seal Conservation Action Plan | 2007 | CEP Participating Countries |
| CEP-SAP Project |  |
| Final Evaluation of the UNDP/GEF Caspian Environment Programme, Phase 1 | 2002 | Alexandra Holland |
| Caspian Environment Programme – Institutional Arrangements (Interim) 2003 | 2003 | CEP-SAP |
| Stakeholder Analysis Revisit | 2004 | Mary M Mathews |
| Steering Committee Meeting, November 2004, Topics and Issues Paper | 2004 | CEP-SAP-PCU |
| Steering Committee Meeting, November 2004, Annex 1: Decisions and Recommendations | 2004 | CEP-SAP-PCU |
| Monitoring study of Beroe ovata and Mnemiopsis leidyi the Southern Caspian, Summer-Autumn 2005 - Final Report. | 2005 | CEP-SAP |
| Public Participation Strategy For The Caspian Sea (2005) | 2005 | CEP-SAP |
| UNDP/GEF APR/PIR 2005 | 2005 | CEP-SAP-PCU |
| UNDP/GEF APR/PIR 2006 | 2006 | CEP-SAP-PCU |
| Grants and Public Participation: Progress Report | 2006 | CEP-SAP-PCU |
| Steering Committee Meeting, February 2006, Topics and Issues Paper | 2006 | CEP-SAP-PCU |
| Steering Committee Meeting, February 2006, Annex : Decisions and Recommendations | 2006 | CEP-SAP-PCU |
| Steering Committee Meeting, December 2006, Topics and Issues Paper | 2006 | CEP-SAP-PCU |
| Steering Committee Meeting, December 2006, Conclusions | 2006 | CEP-SAP-PCU |
| Project Implementation Review Meeting Report, December 2006 | 2006 | CEP-SAP-PCU |
| GEF International Waters Annual Project Performance Results Template | 2006 | UNDP/GEF |
| Development of Caspian Coastal Sites Inventory (CCSI) and identification of areas of special importance and/or sensitivity within an ecosystem approach and framework – Inception Report. | 2006 | CEP-SAP |
| Assessment of Shipping Traffic and Ballast Water Movements to and from Caspian Sea, and preliminary appraisal of possible Ballast Water Management Options (Draft) | 2006 | CEP-SAP |
| Terms of Reference for Final Evaluation | 2007 | CEP-SAP-PCU |
| Development of Caspian Coastal Sites Inventory – Ground Truthing report (Executive Summary and various sections, sub-reports, maps, etc.) | 2007 | CEP-SAP |
| Caspian Environment Programme: Future Evolution | 2007 | CEP-SAP-PCU |
| Caspian Strategic Action Programme Implementation: A Regional Review and Assessment | 2007 | CEP-SAP |
| Anzali Lagoon Adaptive Management Pilot Initiative Project, Progress Report III | 2007 | CEP-SAP |
| Caspian Environment Programme Review Of Existing Information Systems |  | CEP-SAP |
| Methods For Sediment Sampling And Analysis |  | CEP-SAP |
| UNDP/GEF APR/PIR 2007 | 2007 | CEP-SAP-PCU |
| National – Iran |  |
| National Caspian Action Plan | 2002 | Government of Iran |
| Project Brief, MSGP-IR05-3. Creation of a sperm bank for sturgeon breeders in the south of Caspian. | 2005 | CEP-SAP |
| Project Brief, MSGP-IR05-04, Artificial spawning of Rutilus frisii kutum (Kamenskii, 1901). | 2005 | CEP-SAP |
| Caspian Environment Programme: SAP/NCAP Implementation Assessment. | 2006 | P. Farschi and H.F. Rad |
| National – Azerbaijan |  |
| National Caspian Action Plan | 2002 | Government of Azerbaijan |
| MSGP-AZ05-04, Oily Soil Clean Up Project, MPPA Interim report | 2005 | CEP-SAP |
| MSGP-AZ05-04, Oily Soil Clean Up Project, MPPA Final report | 2005 | CEP-SAP |
| Study And Survey Project To Determine The Fluxes Of Major Contaminants From The Kura To Caspian Sea (Mingechaur Reservoir To Kura River Delta) | 2006 | Ruzigar NGO/CEP |
| Environmental Awareness material in Azeri. (a MEG for calendar, booklets) | - | Institute of Zoology |
| Project Brief, MSGPV-AZ10-05, Promoting Sustainable Development in local communities of Caspian region through alternative sources of energy. | 2006 | CEP-SAP |
| National – Kazakhstan |  |
| The Kazakhstan SAP Implementation Assessment Report | 2006 |  |
| MSG Summary: Cleaning the bottom of Ural River at the west-Kazakhstan Oblast | 2005 |  |
| MSG Summary: Conservation & Restoration of Caspian Sturgeon Stocks | 2005 |  |
| National Caspian Action Plan - Kazakhstan |  |  |
| National – Russia |  |
| Review and Implementation of SAP for Caspian Sea and NCAP of the Russian Federation in the Field of Nature Use and Environment Protection | 2006 |  |
| MSG Summary: Introduction of innovative technology of marketable fish production in the Tumak village. |  |  |
| MSG Summary: Supplying Sewage Purification Equipment to Floating Hotels in Volga River. |  |  |
| National – Turkmenistan |  |
| National Caspian Action Plan | 2002 | Gov’t of Turkmenistan |
| Various Materials | - | MEGs |
| Project Brief, MSGPV-TK01-05: Gathering, sorting & processing of plastic waste materials in Turkmenbashi city. | 2006 | CEP-SAP |
| Other |  |
| GEF Evaluation Office: Guidelines for Implementing and Executing Agencies to Conduct Terminal Evaluation | 2007 | GEF Evaluation Office |

Annex 5 – Summary of Field Visits

1. Project Visit: Anzali Lagoon Adaptive Management and Planning Project (Project Regional Demonstration Project)

Background

The level of the Caspian Sea has varied significantly in recent decades, and these trends are set to continue due partly to climate change. The Regional Steering Committee determined to undertake a demonstration project to demonstrate how communities can adapt to rapid sea level rise. Anzali lagoon in Iran was selected as the demonstration site. International experts helped design the project activities. Urban and economic areas near the lagoon are at risk from rising sea levels.

The project aim to collect and gather data and information, forecast how the sea level may change in coming decades, forecast the impact this will have on local land-use and spatial development, and identify appropriate management responses.

The project (total value of local subcontractor $186,000) has prepared several good reports, including scenarios and maps, and has undertaken much consultation, awareness raising and lobbying – mostly at district and provincial level, but some actions at national level. The local government provided quality office space for the project team, as an indication of its commitment.

Direct Observation The evaluation team visited the project office and discussed project progress with project manager. Outputs were reviewed. A brief interview was made with the local MP.

Findings/Comments

Relevance

- This project addresses ‘climate change’ and sea-level rise; these are agreed regional priorities.

Trans-Boundary

- This a regional demonstration project addressing an issue relevant at many places around the Caspian. However, little attention has been paid to regional dissemination. Stakeholders in the other four Caspian countries were not significantly aware of the project aims and findings.

Innovative/Pilot nature

- The project is highly challenging, local awareness of these key issues is low, and local priorities are focussed on short-term economic development rather than the sea level rise. It is therefore addressing innovative issues.

Impacts

- The project team seems highly professional;

- The quality of the outputs is high, although perhaps in some cases over-academic or over-theoretical;

- Observed initial evidence of impacts are significant and include:

  - The prevalent level of understanding has improved considerably;

  - The information base, and the tools for presenting the issues (through maps) have improved considerably;

  - The project reports have reportedly ‘shocked’ local decision-makers, many of who are now committed to changing local spatial development plans and procedures;

  - Urban developments have been stopped in some of the areas at risk from sea level rise;

  - The issues identified through the project have been raised to the President of Iran, who requested that an inter-sectoral team work on preparing a land-use plan in light of probable sea level rise, using the data-base prepared by the project;

  - The issues identified through the project were reportedly submitted to the national Parliamentary economic committee.

2. Project visit: Artificial Spawning of Rutilus Kutum (MSGP-IR05-04, Iran)

Background

Kutum is a fish primarily living in the southern Caspian Sea. This fish was once abundant in the Caspian Sea and historically the annual harvest ranged up to 9000 tons. Unfortunately, its natural stocks have declined. This sharp decline is due to the disruption/degradation of the spawning areas and illegal catch. This valuable species has two types of population in the Caspian Sea, the Spring Kutum and the Autumn Kutum. In the past, hatchery programmes have successfully provided Spring Kutum fingerlings for restocking purposes. However, the endangered Autumn type was neglected, and considered too difficult to hatch artificially. Therefore, an emergency research planning was needed to rehabilitate stocks of the Autumn form. This artificial spawning of the Autumn type aims not only to help Iranian fisheries, but also contributes to the fishing sector in neighbouring Caspian states.

Under the project, which received approximately $44,000 from MSGP, 200 Autumn Kutums, equal number of males and females, were captured during their migration season to the rivers. After they reached maturation, the most suitable Kutum fish were selected for egg stripping and fertilization. The eggs were transferred to fish farms. When the fingerings were considered grown up, they were released into the natural environment. The aim through this project is to release up to 2.5 million fingerlings to the Sea.

Direct Observation. The Evaluators visited the Iranian Fisheries Research Organisation (IFRO) in Anzali who are the grant beneficiaries and are responsible implementing the project. We met several project staff during a three-hour meeting and inspected several photos and records.

Findings/Comments

Relevance

- The project addresses two key issues in the Caspian region (i) decline in fish biodiversity and populations (ii) poverty and declining livelihoods in the region.

Transboundary Nature

- The project addresses a regional issue (fish stocks) and actions in the project may have impacts on communities in other countries – by increasing fish populations across the sea;

- There was little evidence of attempts to disseminate project findings or to cooperate with similar actors/initiatives in other countries.

Innovative/Pilot nature

- This GEF MSGP is well integrated into governmental programme. The MSGP research results showed the way on how to reproduce Autumn Kutum. This immediately led to large-scale, follow-up government investments in re-stocking;

- The project is a ‘first’ in that Autumn Kutum had never been successfully bred previously. However, the project is not very innovative. It is led and implemented by scientists, through a largely scientific/research approach. With GEF support, it may have been more appropriate to develop participatory and/or not market-oriented solutions to restocking. For example, future restocking programmes will still require large-scale government investment, as the local fishermen (who are the main, ultimate, beneficiaries) have not been involved in the programme. If government funding is not available, the local communities will not be able to undertake the restocking.

Impacts

- The IFRO has a large staff with seemingly good capacity. This seems like a very appropriate beneficiary;

- The restocking programmes have reportedly had an immediate impact – leading to impressive increases in catch. This leads to benefits to the local (and possibly regional) fishing community;

- The project does not address the root causes of the problem (which are mostly over-fishing in the entrance to the spawning areas and habitat degradation). Hence, the project is ‘plugging a gap’. However, any long term conservation strategy should focus on removing root causes.

3. Project Visit: Creation of a sperm bank for sturgeon breeders in the south of Caspian (MSGPV-IR12-05)

Background

Population levels of all species of sturgeon in the Caspian have declined sharply in recent years. Whereas the long-term solution is to remove the root causes to this decline, over the short-term artificial breeding and restocking programmes are essential. This involves capturing male and female sturgeon and breeding fish at appropriate times in appropriate conditions. An important part of this strategy is to freeze large numbers of sperm in order to (i) ensure a long term supply (ii) ensure sperm are available when female eggs are available (iii) long term storage of a diversity of sperm. In recent years, a short of sperm at critical times has undermined breeding and restocking programmes.

This project intends to collect high quality sperms during the mating season and to keep them frozen in a sperm bank. The good quality sperms are to be transferred under refrigeration conditions to the laboratory at the institute. The sperm samples are studied once again in the lab. They are then mixed with specific substances and gradually frozen through several stages in liquid nitrogen. Samples are then stored in large liquid nitrogen tanks. The stored samples are evaluated qualitatively and quantitatively for six months. As a result, sufficient amounts of good quality sperms from all sturgeon species will be collected. The GEF grant directly contributes to purchasing liquid nitrogen tanks and liquid nitrogen. Eventually, this project should enable all sturgeon hatcheries (government and non-government) to have access to suitable sperms and also provide grounds for international collaboration. By contributing to restocking programmes, this project should have positive impacts for the sturgeon population and diversity, and positive economic impacts for fishing communities in Iran and elsewhere.

Direct Observation. The Evaluators visited the offices, laboratory and hatching sites of the International Sturgeon Research Institute near Rasht in Iran. We met with officials and laboratory technicians.

Findings/Comments

Relevance

- The project addresses two key issues in the Caspian Sea (i) decline in fish biodiversity and populations (ii) poverty and declining livelihoods in the region.

Transboundary Nature

- The project addresses a regional issue (fish stocks) and actions in the project may have impacts on communities in other countries;

- There was little evidence of attempts to disseminate project findings or to cooperate with similar actors/initiatives in other countries.

Innovative/Pilot nature

- The project beneficiaries have ongoing related projects supported by governments and were able to integrate the GEF support into these governmental programmes;

- GEF support has played a critical role here. However the GEF support is small in comparison to the costs of the overall programme. In that connection, the catalytic or innovative nature of this project requires further clarification’

Impacts

- The project beneficiaries have strong capacity and are able to make good use of the GEF support;

- The project does not attempt to address the threats to sturgeon populations (overfishing, disturbance and habitat destruction) nor does it attempt to remove root causes. It is addressing symptoms in what may be a short-term response;

- According to reports, the Institute was unable to collect enough sperm in 2007 - this may suggest a design fault. More cooperation with other countries able to catch males (e.g. Azerbaijan) may be a solution.

4. Project visit: Promoting sustainable development in local communities of Caspian region through alternative sources of energy (MSGPV-AZ10-05, Azerbaijan)

Background

Local communities of the Tazakend Municipality in Azerbaijan suffer from low standards of living, poverty and shortage of energy. The local people tend to poach fish and waterfowls near the Caspian coast and illegally cut wood in order to survive. These practices have a negative impact on the biological diversity, land and other natural resources of the region. Therefore, it is highly important to provide local communities with alternative energy and biological resources.

The project has two components, an agro forestry plantation and an artificial pond. An agro-forestry plantation situated on 6 hectares of sloping, barren municipal land where 20,000 young trees are being planted. An artificial pond constructed in an area of 1 hectare for the breeding of fish with the capacity of 500 kg/year. This project is providing new job opportunities for the local population by employing them in the plantation and artificial breeding of fish. The plantation of fast-growing trees will also provide wood, help prevent desertification and sequestrate carbon. The MSGP grant of approximately $40,000 followed a similar grant provided by CIDA.

Direct observation  The Evaluators visited the project (approx. 2 hours drive from Baku) together with the implementing NGO (Chevra). I saw that most of the trees have been planted and that the fish pond has been constructed and is now filling up. It is expected to be fill within 1 month and immediately stocked with fish. In the long term, through the sale of fish and wood, the project should be profitable.  There are tentative plans to establish a mini resort, with fishing, relaxation, shade and restaurant.

Findings/Comments

Relevance

- The project addresses agreed environmental challenges in the TDA and SAP (ie desertification and erosion). It also aims to address socio-economic challenges;

Transboundary Nature

- Although the project is addressing an issue important across the region, there is little evidence that this project can contribute to actions at any other site.

Innovative/Pilot nature

- The project was initially supported by CIDA before being supported by CEP-SAP MSGP;

- This project is considered innovative for Azerbaijan, as it has both ecological and social objectives. Previous plantation projects were uniquely ecological and all trees were fully protected;

- The involvement of local people and authorities in the project design/implementation was not clearly explained – will they learn from this, will they be able to replicate the successes? This does not seem to have been a concern;

- There was no evidence that national authorities (notably MENR) are interested in this project – given its innovativeness. This lack of interest possibly reduces its potential catalytic value and its dissemination potential.

- Overall, reforestation is an issue with a huge wealth of experience worldwide. Hence, the innovative nature of this project is likely to be limited.

Impacts

- The project draws on a depth of scientific exercise within Chevra and seems well designed from that perspective. I was informed (but could not independently verify) that the survival rate for trees (after 3 years) is approximately 70%. This is high;

- Several sources informed me that it will be possible to sell the wood and the fish to the local people, once available, hence the project should be financially sustainable, even profitable. There is a possibility of replication on a commercial basis;

- This integrated project could provide a model for sustainable rural development;

- The project uses Canadian Poplar tree, a non-indigenous species chosen for its rapid growth and its ability to survive in the area. The trees are planted in an arid area and require year round irrigation. This is currently available, but does increase the risk of future failure;

- A more useful demonstration, if technically feasible, would have been of indigenous species requiring less maintenance and irrigation.

The success of the project will only be clear after several years if (i) fish are being produced commercially without negative environmental impact (ii) wood is produced, sold and trees are replanted and maintained on a totally sustainable basis.

5. Project visit: Gathering, sorting & processing of plastic waste materials in Turkmenbashi city (MSGPV-TK01-05)

Background

The ever-increasing use of plastic materials in the world has resulted in unprecedented amounts of plastic waste.  Their disposal is rather difficult and disintegration takes a long time. An alternative disposal method is burning, but this can release considerable amounts of hazardous substances into the environment. Currently, urban wastes in Turkmenbashi City are either land filled, dumped or burned. Currently, most plastic waste is burnt at low temperatures. The predominant winds carry the hazardous fumes toward the city and the sea shores. As a result, the population of Turkmenbashi City and the coastal environment suffer. This project was developed to protect the people’s health and the environment by reducing hazardous toxic substances resulting from plastic incineration. This project aims to collect appropriate plastic materials from the 92 garbage containers and a major dumping sites in the city and to recycle the plastic wastes into plastic goods for every day uses, such as clothes hangers. As a result of this project, at least 100 tons of plastic waste products will be collected and utilized annually.

The project provided funds to a private company (Namys). Namys is using these funds to: prepare special bins for collecting plastic across the city, renovate a small workhouse and provide equipment to wash, crush and recycle plastic. GEF contributes $40,000 to the overall project budget of $97,200.

Direct observation The Evaluators visited the renovated workhouse and observed the special collection bins. The grantee was awaiting the delivery of the equipment.

Findings/Comments

Relevance

- The project addresses the issue of plastic-based pollution and pollution caused by burning plastic. This is an important issue in the TDA and SAP.

Transboundary Nature

- The project addresses the issue of solid waste, which is a problem across the region. The project addresses the problem of pollutants which are carried (by sea and wind) across borders.

Innovative/Pilot nature

- The issue of plastic waste burning is likely to be common across the Caspian region. Should the enterprise become commercially profitably, this project potentially has replication and dissemination value. However, no mechanisms seem to be in place to facilitate this dissemination;

- The project benefits from the support of the local Mayor. This increases the probability of success, however, it may decrease its replicability.

Impacts

- The business analysis conducted whilst preparing the project suggests that the recycling enterprise should be profitable. The MSGP helped reduce the risk associated with this innovative business enterprise. It also sped up the business development;

- Once operating, the plastic recycling enterprise should employ ten persons, thereby making a small contribution to employment in an area with high unemployment. Likewise, the project does contribute to reducing pollution;

- The grantee expressed some frustration with the grant delivery mechanism, suggesting there were considerable delays to issuing the first payment under the grant, and this almost made the project non-profitable.

Annex 6 – Evaluators Ratings of Indicators

The Evaluators rated progress towards each of the indicators as listed in the 2006/07 PIR. For each indicator, the Evaluators assessed:

- Has the target been reached?

- Was evidence available that the related project activities had had an impact – or are likely to have an impact in the medium-term future? Impact is determined as follows: (i) for a report, it should be clearly useful or used by significant stakeholders (ii) for a demonstration project, it should be replicated or influencing the design of future initiatives (iii) for a recommendation, it should be embedded in government workprogrammes.

The summary findings are provided in Table 1. The detailed findings are in Table 2.

Table 1: Summary of Progress towards PIR 2006/07 Indicators.

|  | Indicator Target Achieved | Evidence of Impact |
| --- | --- | --- |
|  | Score | Percentage | Score | Percentage |
| Outcome 1 | 630/800 | 79% | 90/800 | 11% |
| Outcome 2 | 200/300 | 66% | 90/300 | 30% |
| Outcome 3 | 270/600 | 45% | 190/600 | 32% |
| Outcome 4 | 160/400 | 40% | 100/400 | 25% |
| Outcome 5 | 470/700 | 67% | 240/700 | 37% |
| Objective 1 |  | 59% |  | 27% |
| Outcome 6 | 390/500 | 78% | 350/500 | 70% |
| Outcome 7 | 250/500 | 50% | 130/50 | 26% |
| Objective 2 |  | 64% |  | 48% |
| Outcome 8 | 370/500 | 74% | 270/500 | 54% |
| Objective 3 |  | 74% |  | 54% |
| Outcome 9 | 170/200 | 85% | 80/200 | 40% |
| Objective 4 |  | 85% |  | 40% |

Table 2: Detailed Findings of Evaluators Regarding Progress towards PIR 2006/07 Indicators.

| Project Objective and Outcomes | Description of Indicator | Baseline Level | Target Level | Achieved | Evidence of Impact |
| --- | --- | --- | --- | --- | --- |
| Objective I : To commence implementation of the SAP in three priority areas: Biodiversity, Invasive Species and Persistent Toxic Substances. |
| Outcome 1: A quantitative assessment of habitat loss in the Caspian and its coastal zone and verification of critically threatened areas, and, the design and establishment of a standardised monitoring methodology programme for the Caspian Sea in conjunction with the oil and gas industry | Information Gap Identification Survey Sensitivity & Threats Evaluation and Incorporated in the Coastal Sites Inventory Environmental Sensitive Data Index GIS Layers/IMPAS Updated Caspian Species Checklist species description and Bio Data base (BDB) data base Regional Biodiversity Monitoring Protocols Regional Biodiversity Monitoring Programme established and initiated Biodiversity training | 0 in 2004 10 in 2005 20 in 2004 60 in 2005 20 in 2004 40 in 2005 20 in 2004 30 in 2005 0 in 2004 20 in 2005 0 in 2004 0 in 2005 0in 2004 0 in 2005 0 in 2004 0 in 2005 | 100= National Reports on Coastal Sites 100= Completed Coastal Sites Inventory 100= Developed and calibrated indices 100= functional MPAS 100= Functional & calibrated BDB 100= Developed and agreed protocols 100= sites agreed, guidelines & protocols developed and support equipment procured 100= minimum three training sessions | 100 100 10 100 100 90 30 100 | 0 0 0 0 50 10 30 0 |
| Outcome II : Preliminary implementation of the Caspian Biodiversity Action Plan, focusing on compliance with existing nature protection regulations, implementation of species and habitat protection conservation action plans and targeted public awareness campaigns | Establishment of functional Caspian eco-net, annual Eco- net meetings, eco net bulletin Development and implementation of a Seals Conservation plan Seals Pilot lagoon identified and a Pilot Water Level fluctuation Adaptive Management Plan developed and initiated | 0 in 2004 30 in 2005 20 in 2004 80 in 2005 30 in 2004 40 in 2005 | 100=Eco-net formed, Quarterly reports by members, annual meetings, publications 100= annual population surveys, Regional Seals Advisory Group (SRAG),Agreed and initiated Seals Regional Action Plan, collaboration with industry 100= representative lagoon selected, stakeholders analysis conducted, TDA carried out, pilot management plan drafted and initiated | 20 80 100 | 0 20 70 |
| Outcome III: Implementation of the CEP invasive species action plan in close coordination with the GEF Globlast Ballast Waters project to address, in particular, the impact of the ctenophore Mnemiopsis on the Caspian ecosystem | Mnemiopsis Leidyi Monitoring programme carried out including reporting to the region Completion of Beroe studies and development of proposal for Beroe introduction approved Introduction of Beroe Formation of Regional authority to over see agreed introductions based on n national legislation reviewed and updated Invasive species training provided and data base created Assessment of ship borne traffic of Invasive species | 30 in 2004 50 in 2005 40 in 2004 50 in 2005 0 in 2004 20 in 2005 20 in 2004 30 in 2005 50 in 2004 60 in 2005 20 in 2004 30 in 2005 | 100= Regional monitoring initiated and supported , data and reports shred out regionally 100=Improved EIA and recommendations to BISRAG on introduction of Beroe , controlled release of Beroe 100= Ditto 100= Functional authority to oversee planned invasive species release, functional data base , review of national legislations as base for legislation update and possible regional authority 100= additional date from regional monitoring , additional training 100= Full pre feasibility study | 100 50 0 0 50 70 | 80 50 0 0 30 30 |
| Outcome IV: Assessment of the pollution loading of the Caspian and determination of distribution and composition of PTS (such as persistent organic pollutants, oil products, and heavy metals) in the riverine waters and sediments and coastal waters, in order to prioritise future interventions directed at amelioration of the environment. | Endorsed Regional Plan to combat LBS pollution Recommendation for flux management in major rivers Sea-wide survey of sediments in riverine and sea waters including Turkmenistan Pollution Monitoring programme developed and implemented including awareness programmes | 10 in 2004 20 in 2005 10 in 2004 50 in 2005 20 in 2004 40 in 2005 10 in 2004 40 in 2005 | 100=Regionally endorsed plan to be incorporated in revised SAP based on ground truthing reports and national and regional LBS pollution assessment reports 100= Flux reports on Volga and Kura , recommendations adapted by regional authorities 100= Regional Laboratory assessment completed, pollution analysis and assessment report for the Caspian Sea 100=Regional agreement on monitoring programme, results from first year of monitoring , training on rapid assessment programme, awareness programme designed and implemented | 0 40 70 50 | 0 20 30 50 |
| Outcome V: Regional (developed as part of the project) and National Action Plans addressing the activities contributing to transboundary Persistent Toxic Substances (PTS) including persistent organic pollutants, oil products, and heavy metal pollution (as only two of the five Caspian littoral states are presently signatories to the Stockholm Convention, assistance by UNEP in developing national support for signature and in developing enabling activities will be part of the project | Strengthened legislation and guidelines on usage of Agro -chemicals with each country committing five percent annual reduction Linkage to POPs national Enabling activities Developed POPs/PTS Regional Action Plan Report on pesticide stocks Pilot projects to reduce POPs Public awareness activities including IPM model farm and training of at least 400 affirmers and 50 officials At SCM request additional studies being under taken on Algae Bloom in southern Caspian | 0 in 2004 30 in 2005 0 in 2004 60 in 2005 0 in 2004 30 in 2005 10 in 2004 30 in 2005 0 in 2004 30in 2005 0 in 2004 20 in 2005 0 in 2004 0 in 2005 | 100=signed and ratified agreement on PTS , standardized plans in all countries 100= ditto 100= Approved Regional Plan 100=Reports on pesticide stock s 100= initially two pilot projects which at the request of the region were increased to potential five 100= reports on training conducted , IMPM model farm 100= Report on causes of a large 400 square km algae bloom in 2005 near the Iranian coast | 10 60 100 70 60 70 100 | 0 30 30 30 40 60 70 |

| Objective II : Continue with specific capacity building measures to ensure a regionally owed CEP coordination mechanism capable of full implementation of the SAP and regional coordination of the NCAPs and consolidate/update the TDA, SAP and NCAP’s following a series of information gap-filling measures. |
| --- |
| Project Objective and Outcomes | Description of Indicator | Baseline Level | Target Level | Achieved | Evidence of Impact |
| Outcome 1: A sustainable, strengthened, and regionally owned coordination mechanism for development and management of the Caspian Sea environment, in the form of a newly formed country-supported PCU located in the Islamic Republic of Iran capable of execution of regional projects, strong country-supported National Coordination Structures capable of execution of national projects, and a network of institutions addressing transboundary environmental issues as addressed in the NCAPs and SAP. | Established, functional and effective PCU including transfer of Data and Information system infrastructure from Baku to Tehran Training to PCU /National Caspian Structures Support to improved regional and national coordination SAP/NCAP Implementation monitoring and revision of CEP Concept Paper with reference to CEP /Convention Revisited TDA/NCAPs/SAP | 30 in 2004 100 in 2005 30 in 2004 50 in 2005 100 in 2004 100 in 2005 30 in 2004 50 in 2005 0 in 2004 30 in 2005 | 100=full time staffed PCU, web- based PCU work plan, functional website linked to other regional websites 100= Training need assessment report, workshop reports, improved delivery from PCU and National Caspian Structures (NSCs) 100= Recruited SAPICs, functional inter-sectoral national bodies, 100=reports on effectiveness of SAP implementation from SAPICs , improved coordination of SAP implementation, CVEP Concept Paper 100= Revisited TDA, NCAPs, SAP | 90 90 80 50 80 | 90 90 70 30 70 |
| Outcome II: Enhanced and informed stakeholder and inter- sectoral participation in the management of the Caspian environment | Development of Media kit for journalists / Strengthened NGOs capacities& Environmental awareness training initiatives Functional Caspian Concern Groups & Mayors Conference Enhanced private sector participation in CEP Developed and approved Public participation plan | 40 in 2004 100 in 2005 30 in 2004 50 in 2005 10 in 2004 30 in 2005 10 in 2004 40 in 2005 10 in 2004 50 in 2005 | 100=Developed Media kit, Media Database, NGO Database , Monthly E bulletin 100=NGO Database , press release mechanism in place, NGO participation in major meetings , training held for policy makers 100= Five Caspian Concern Groups one in each country supported by a Coastal Public Participations Advisor ( PPAs) , Mayors Conference held , Caspian NGOs networked 100= Private Sector Database, active private sector regional advisory group 100= Designed and approved and initiated Public Participation Strategy (PPS) | 70 20 20 40 100 | 60 20 0 40 10 |

| Objective III: Strengthen the environmental legal and policy frameworks operating at the regional and the national levels and where necessary improve implementation and compliance of those frameworks |
| --- |
| Project Objective and Outcomes | Description of Indicator | Baseline Level | Target Level | Achieved | Evidence of Impact |
| Outcome 1: Preparation of ancillary agreements to the Framework Convention and drafts of the major protocols targeting priority transboundary issues (biodiversity, persistent toxic substances, invasive species, land-based sources, marine and seabed pollution, and environmental impact assessment, data exchange) | Ancillary agreements to Tehran Convention Support to ratification process Preparation for functional Convention Secretariat /gap analysis Enhanced legal capacity pertaining to int environmental law Promotion of regional EIA and use of economic instruments in env management | 30 in 2004 60 in 2005 50 in 2004 100 in 2005 30 in 2004 50 in 2005 0 in 2004 60 in 2004 0 in 2004 60 in 2005 | 100= Draft agreed protocols 100= full ratification 100=detailed legislation gap analysis , Convention Rules and Procedure, supporting papers 100=targeted workshops , national Convention compliance capacity reviews 100=technical workshops on Espoo in all five countries , report on application of economic instruments , EIA In Transboundary Context protocol | 80 100 70 60 60 | 70 100 60 20 20 |

| Objective IV : Achieve tangible environmental improvements in SAP priority areas by implementation of small-scale investments supported by a small matched grants programme |
| --- |
| Project Objective and Outcomes | Description of Indicator | Baseline Level | Target Level | Achieved | Evidence of Impact |
| Outcome 1: Matched Funding of small-scale investments from the NGO, public and private sector, which target common or transboundary Caspian issues identified as priorities in the TDA/NCAPs/SAP and will result in tangible environmental improvements. This activity will be a continuation of the Matched Small Grants Programme currently being executed by the World Bank as part of the first GEF support project to the CEP. | MSGP Grants awarded | 50 in 2004 100 in 2005 | 100= Two rounds of Matched Grants through competitive basis dealing with pilot and small investment projects with strong bearing on Caspian environment issued as identified in TDA/NCAPs and SAP. | 100 | 50 |
|  | MSGP grants implemented | 30 in 2004 60 in 2005 | 100= Cost effective and timely implementation. | 70 | 30 |

Annex 7 – Summary Information on Expenditures

By Activity

| Activity | Related Outcome | Anticipated in Project Document | Final Total Amount (US$ ‘000s) |
| --- | --- | --- | --- |
| PCU Establishment and Support | Outcome F and distributed over all other Outcomes | 3,040 | 3, 423 |
| Prelim BSAP Implementation | Outcome B | 345 | 125 |
| Implementation of Invasive Species Action Plan | Outcome C | 356 | 359 |
| Assessment of Pollution Loading | Outcome D | 378 | 430 |
| Regional and National Action Plans for PTS | Outcome E | 64 | 144 |
| Quantitative Assessment of Habitat Loss | Outcome A | 291 | 325 |
| Enhancement of Stakeholder Participation | Outcome G | 356 | 119 |
| Protocols to the Framework Convention | Outcome H | 529 | 410 |
| Matched Small Grants Programme | Outcome I | 664 | 689 |
|  |  | 6,023 | 6,024 |

By Outcome

The following assumes that Activity 1 (PCU Establishment and Support) is 50% in support of Outcome F, and 50 % distributed equally across all other Outcomes. I.e., $1.712 million to Outcome F, and $0.214 million to each of the other eight Outcomes.

| Outcomes | Amount |
| --- | --- |
| Outcome A: A quantitative assessment of habitat loss in the Caspian and its coastal zone and verification of critically threatened areas, and, the design and establishment of a standardised monitoring methodology programme for the Caspian Sea in conjunction with the oil and gas industry. | 539 |
| Outcome B: Preliminary implementation of the Caspian Biodiversity Action Plan, focusing on compliance with existing nature protection regulations, implementation of species and habitat protection conservation action plans and targeted public awareness campaigns. | 339 |
| Outcome C: Implementation of the CEP invasive species action plan in close coordination with the GEF Global Ballast Waters project to address the impact of Mnemiopsis on the Caspian ecosystem. | 573 |
| Outcome D: Assessment of the pollution loading of the Caspian and determination of distribution and composition of Persistent Toxic Substances (PTS) in the riverine waters and sediments and coastal waters, in order to prioritise future interventions directed at amelioration of the environment. | 644 |
| Outcome E: Regional and National Action Plans addressing the activities contributing to transboundary PTS, including persistent organic pollutants, oil products, and heavy metal pollution. | 358 |
| Outcome F: A sustainable, strengthened, and regionally owned coordination mechanism for development and management of the Caspian Sea environment, in the form of a newly formed country-supported PCU located in the IR-Iran capable of execution of regional projects, strong country-supported National Coordination Structures capable of executing national projects, and a network of institutions addressing transboundary environmental issues as addressed in the NCAPs and SAP. | 1712 |
| Outcome G: Enhanced and informed stakeholder and inter-sectoral participation in the management of the Caspian environment | 333 |
| Outcome H: Preparation of ancillary agreements to the Framework Convention and drafts of the major protocols targeting priority transboundary issues (biodiversity, PTS, invasive species, land-based sources, marine and seabed pollution, EIA, data exchange) | 624 |
| Outcome I: Matched funding of small-scale investments from the NGO, public and private sector, which target common or transboundary Caspian issues identified as priorities in the TDA/NCAPs/SAP and will result in tangible environmental improvements. | 903 |

Annex 8 – Table of Co-Financing

The co-financing is summarized in the following table. The table is based on figures provided in the project document and on figures provided by the CEP-SAP PCU.

| Co-Financing (Type/source) | IA own financing (mill US$) | Government (mill US$) | Other2 (mill US$) | Total (mill US$) | Total Disbursement (mill US$) |
| --- | --- | --- | --- | --- | --- |
|  | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual |
| Grants |  |  |  |  | 4.66 | 13.21 | 4.66 | 13.21 |  |  |
| Loans/concessions (compared to market rates) |  |  |  |  |  |  |  |  |  |  |
| Credits |  |  |  |  |  |  |  |  |  |  |
| Equity investments |  |  |  |  |  |  |  |  |  |  |
| In-kind support |  |  | 2.3 | 0.35 |  |  | 2.30 | 0.35 |  |  |
| Other |  |  | 19.2 | 96.771 |  |  | 19.20 | 96.77 |  |  |
| TOTALS | 0 |  | 21.5 | 97.12 | 4.66 | 13.21 | 26.16 | 110.33 | 31.63 | 116.58 |

Accordingly, the calculated co-financing is approximately 400% of that anticipated at project start.

Government co-financing

This is mostly to parallel activities implementing the NCAPs and related activities in the period 2004-2006.  Parallel activities mean those activities would most likely have been funded in the absence of the project and may not have been leveraged by the project but are relevant to the project’s objective. These are broken down as follows:

|  | AZ | IR | KZ | RF | TK | Total by EQO |
| --- | --- | --- | --- | --- | --- | --- |
| EQO I | - | 22,576,000 | 575,000 | 3,700,000 | 2,554,000 | 29,405,000 |
| EQOII | 25,000 | 10,931,000 | 850,000 | 25,000 | 585,000 | 12,416,000 |
| EQO III | 6,220,000 | 11,738,000 | 15,668,000 | - | 12,433,000 | 46,059,000 |
| EQO IV | - | 20,000 | 23,000 | 6,000,000 | 225,000 | 6,286,000 |
| EQO V | - | 1,788,000 | - | - | 829,000 | 2,617,000 |
| Total SAP Expenditure by Country | 6,245,000 | 47,053,000 | 17,116,000 | 9,725,000 | 16,626,000 | 96,765,000 |

Other co-financing includes:

- EU: Sustainable Fisheries - Euro 0.9 million; Sustainable Coastal Area Development - Euro 2.4 millions; Support to CEP and Convention - Euro 2.5 millions.

- Darwin Fund has two Caspian projects namely: Seal Conservation Action Plan - £260,713; Environmental Education - £154,000.

- Japan International Cooperation Agency (JICA) has funded two Caspian projects namely: the Study on Integrated Management for Ecosystem Conservation of the Anzali Wetland - $ 400,000 (to be followed up soon with a second phase project of $ 600,000); Capacity Development for Pollution Prevention  and Control in the Petroleum Industry in Kazakhstan - $ 3,700,000.

- Oil industry. Logistical support by AGIPKCO to seals - $ 120,000; BP support to a regional workshops estimated - $ 30,000; IPIECA/OSPRI support to Emergency Reponses Regional Workshops estimated - $ 50.000.

- FAO: the $ 400,000 Caspian Fisheries Technical Cooperation project (just starting).

- World Bank: the $ 300,000 Caspian Fisheries projects (to begin soon).

Annex 9: Project Implementation Structure Diagram.

# Footnotes

PIRs 2006 and 2007 used the same list of indicators

The Criteria for the MSGP were: (i) relevance to TDA; (ii) trans-boundary nature; (iii) innovative and pilot nature; (iv) leading to concrete results; and (v) ‘matched’. This annex provides feedback related to the first four of these criteria, even for the Anzali project which is not a MSGP.

The first year of plantation included trees of a different species.

Several indicators in the original project document were not mentioned in the PIR 2006/07, these indicators were not assessed.

Based on latest information provided by UNOPS. It is noted that the expenditures for 2007 are a best estimate, as the expenditures are not yet finalised.

Differences due to rounding up of figures.

Includes co-financing and disbursed GEF funds.

# Text boxes

MPPA

Regional Advisory Groups

UNDP

UNOPS

UNEP, WB

SAPIC

International and

National Experts

Regional Structure

PCU

Country Structure

National Focal Point

Regional

Steering Cmte

Blue shaded boxes funded by project or other int’l partners;

Green shaded boxes funded by countries or provided in-kind by countries.

Collaboration

Work

Regional Meetings, Protocol Development, Field Surveys, Studies, Strategy Development, Matched Small Grant ID, Funding & Oversight, Program Development, Etc...