## Summary
Country: | Federated States of Micronesia
Programme Code & Title: | Country Programme Action Plan 2008-2012
Project Code & Title: | Project ID:00063283 & Pacific Adaptation to Climate Change Project (PACC)
Responsible Officer(s):
Implementing Partner: | Secretariat of the Pacific Regional Environment Programme (SPREP)
Currency: USD
Activity Description from AWP with Duration |  | UNDP Coding
|  |  |  | 2009 | 2010 | 2011 | 2012 | 2013 | Total
|  | Fund | Account | US $ Only | US $ Only | US $ Only | US $ Only | US $ Only | US $ Only
1. Policy Changes -International Consultants |  | GEF | 71200 | [5 empty] | 0
-Local consultants (including national staffing) |  | GEF | 71300 | [5 empty] | 0
-Contractual services-Individuals |  | GEF | 71400 | [5 empty] | 0
-Travel |  | GEF | 71600 | [5 empty] | 0
-Contractual servises-Companies |  | GEF | 72100 | [5 empty] | 0
-Equipment & Furniture |  | GEF | 72200 | [5 empty] | 0
-Communication & Audio Visual Equipment |  | GEF | 72400 | [5 empty] | 0
-Supplies |  | GEF | 72500 | [5 empty] | 0
-Hospitality |  | GEF | 72700 | [5 empty] | 0
-Information Technology Equipment |  | GEF | 72800 | [5 empty] | 0
-Rental & Maintenance - Premises |  | GEF | 73100 | [5 empty] | 0
-Rental & Maintenance of IT Equipment |  | GEF | 73300 | [5 empty] | 0
-Rental & Maintenance of Other Equipment |  | GEF | 73400 | [5 empty] | 0
-Audio Visual and Printing Prod. Costs |  | GEF | 74200 | [5 empty] | 0
-Miscellaneous |  | GEF | 74500 | [5 empty] | 0
2. Demonstration Measures-International Consultats |  | GEF | 71200 | [5 empty] | 0
-Local consultants |  | GEF | 71300 | [5 empty] | 0
-Contractual services-Individuals |  | GEF | 71400 | [5 empty] | 0
-Travel |  | GEF | 71600 | [5 empty] | 0
-Contractual servises-Companies |  | GEF | 72100 | [5 empty] | 0
-Materials & Goods |  | GEF | 72300 | [5 empty] | 0
-Equipment & Furniture |  | GEF | 72200 | [5 empty] | 0
-Communication & Audio Visual Equipment |  | GEF | 72400 | [5 empty] | 0
-Supplies |  | GEF | 72500 | [5 empty] | 0
-Hospitality |  | GEF | 72700 | [5 empty] | 0
-Information Technology Equipment |  | GEF | 72800 | [5 empty] | 0
-Rental & Maintenance - Premises |  | GEF | 73100 | [5 empty] | 0
-Rental & Maintenance of IT Equipment |  | GEF | 73300 | [5 empty] | 0
-Rental & Maintenance of Other Equipment |  | GEF | 73400 | [5 empty] | 0
-Audio Visual and Printing Prod. Costs |  | GEF | 74200 | [5 empty] | 0
3.Capacity to plan and respond to changes-International Consulatnts |  | GEF | 71200 | [5 empty] | 0
-Local consultants |  | GEF | 71300 | [5 empty] | 0
-Contractual services-Individuals |  | GEF | 71400 | [5 empty] | 0
-Travel |  | GEF | 71600 | [5 empty] | 0
-Contractual servises-Companies |  | GEF | 72100 | [5 empty] | 0
-Equipment & Furniture |  | GEF | 72200 | [5 empty] | 0
-Communication & Audio Visual Equipment |  | GEF | 72400 | [5 empty] | 0
-Supplies |  | GEF | 72500 | [5 empty] | 0
-Hospitality |  | GEF | 72700 | [5 empty] | 0
-Information technology Equipment and Outreach |  | GEF | 72800 | [5 empty] | 0
-Rental & Maintenance - Premises |  | GEF | 73100 | [5 empty] | 0
-Rental & Maintenance of IT Equipment |  | GEF | 73300 | [5 empty] | 0
-Rental & Maintenance of Other Equipment |  | GEF | 73400 | [5 empty] | 0
-Audio Visual and Printing Prod. Costs |  | GEF | 74200 | [5 empty] | 0
4. Project Management -Local consultants (including national staffing) |  | GEF | 71300 | [5 empty] | 0
-Contractual services-Individuals |  | GEF | 71400 | [5 empty] | 0
-Travel |  | GEF | 71600 | [5 empty] | 0
-Contractual servises-Companies |  | GEF | 72100 | [5 empty] | 0
-Equipment & Furniture |  | GEF | 72200 | [5 empty] | 0
-Communication & Audio Visual Equipment |  | GEF | 72400 | [5 empty] | 0
-Supplies |  | GEF | 72500 | [5 empty] | 0
-Hospitality |  | GEF | 72700 | [5 empty] | 0
-Information technology and Outreach |  | GEF | 72800 | [5 empty] | 0
-Rental & Maintenance - Premises |  | GEF | 73100 | [5 empty] | 0
-Rental & Maintenance of IT Equipment |  | GEF | 73300 | [5 empty] | 0
-Rental & Maintenance of Other Equipment |  | GEF | 73400 | [5 empty] | 0
-Professional Services |  | GEF | 74100 | [5 empty] | 0
-Audio Visual and Printing Prod. Costs |  | GEF | 74200 | [5 empty] | 0
Total |  |  |  | 0 | 0 | 0 | 0 | 0 | 0

## 2009
Note on I7: peni.leavai: REFER to Chart of Accounts (COA). A separate excel sheet from UNDP to fill in codes and budget descriptions. Fill in completely. Also refer to Project Document and or Inception Report
Note on I38: peni.leavai: refer to Chart of Accounts (separate excel document) OR the project document for guidance.
Note on I69: peni.leavai: refer to Chart of Accounts (separate excel document) OR the project document for guidance.
Note on I114: peni.leavai: refer to Chart of Accounts (separate excel document) OR the project document for guidance.
Note on J115: peni.leavai: NOTE six months advance salary as per FSM government policy
Note on B117: peni.leavai: Please clarify. What is the difference between this activity and activity 4.1.1.2?
Note on B124: peni.leavai: Please elaborate clearly
Note on J124: peni.leavai: There was no amount allocated for here. Please revise.

## 2010
ANNUAL WORK PLAN JANUARY - DECEMBER 2010
Country | FSM
Project | INTEGRATED COASTAL MANAGEMENT
EXPECTED OUTPUTS | PLANNED ACTIVITIES | TIMEFRAME |  |  |  | RESPONSIBLE PARTY | PLANNED BUDGET
Add baseline, indicators including annual targets | List activity results and associated actions | Q1 | Q2 | Q3 | Q4 |  | Funding Source | Budget Description | Amount in US Dollars
Output 1.1 Guideline to incorporate climate change into sectoral plans and policies developed | Activity 1.1.1 A Guide on how to incorporate climate change into sectoral plans and policies developed
| 1.1.1.1 Develop ToR for a consultant to develop a guide on how to incorporate cc into sectoral plans and policies | x |  |  |  | KIRMA & DT&I & AG's Office | INKIND |  | 0
| 1.1.1.2 Procurement of consultant | x |  |  |  | KIRMA & OEEM | GEF | 74500 | 5000
Indicator: Number of Plans that integrate climate change risk issues related to coastal, crop production and water sector management | 1.1.1.3 Consultant carry out work |  | x |  |  | KIRMA/DT&I/Consultant | GEF | 72500 | 7000
| 1.1.1.4 Review guide and demonstrate |  |  | x | x | KIRMA/DT&I/Consultant | GEF | 72500 | 2500
| 1.1.1.5 Steering/Core quarterly Committee meeting | x | x | x | x | KIRMA/DT&I/Consultant | GEF | 72500 | 3000
| 1.1.1.6 Provide efficient techical service & coordination by procurement of vehicle (Annex 2) |  |  | x |  | KIRMA & DT&I | GEF | 73100 | 9000
Baseline: Currenly not existed | 1.1.2.1
1.1.2.2
1.1.2.3
Target: By the end of the Project, Policy used for sectoral & national CC in place | 1.1.2.4
etc
use this entire row to insert more when needed
[7 empty] | (A) Total Output 1.1 |  | 26500
Output 1.2 (Click cell and press F2 to enter into each cell and paste the information from the 'logframe'. Delete this instruction.) | same as above
Indicator
Baseline
Target
[7 empty] | (B) Total Output 1.2 |  | 0
|  | (C) Total Outcome 1 |  |  |  |  | (C) = (A) + (B) |  | 26500
OUTCOME 2: Demonstration measures to reduce vulnerability in coastal areas in Kosrae, FSM implemented
Output 2.1a Guidelines to integrate climate risks (e.g intense rainfall and storm surges) into coastal road designs | 2.1a.1 Activity Result:
| Activity Result: Climate change assessment incorporated to existing roading design. | [7 empty] | 0
| 2.1a.1 Review existing road design |  |  | x | x | DOE & LWRM | GEF | 72500 | 1000
Indicator:No. of guidelines revised and applied | 2,1a,2 review the CLIMAP assesment |  |  | x |  | KIRMA & DT&I | GEF | 72500 | 300
| 2.1.3 Redesign road plan |  |  | x | x | DT&I |  | 71400 | 10000
| 2.1.4 Review by KPSC |  |  | x | x | KPSC | GEF | 71400 | 500
| 2.1.5 Procurement of Vehicle for technical visit to site (Annex 2) |  |  | x |  | KIRMA & DT&I | GEF | 73100 | 10000
Baseline: Guidelines for road design exist but not climate proofed | 2.2.1 Activity Result: Guideline finalized
| 2.2.1.1 Compile final guide |  |  |  | x | KIRMA & DT&I | GEF | 74200 | 500
| 2.2.1.2 Workshop to discuss guide |  | x |  |  | KIRMA & DT&I | GEF | 72500 | 1000
| 2.2.1.3 Cabinet paper prepared |  |  | x |  | KIRMA & DT&I | GEF | 72500 | 400
| 2.2.3 Approval by Gov. |  |  |  | x
Target: At the end of year three, a guidline is developed and integrated into one (1) national and one (1) State road management plan
[7 empty] | (D) Total Output 2.1a |  | 23700
Output 2.1b. Measures identified in the Guidelines (2.2.1a) demonstrated in Walung community, Kosrae (with co-financing support).) | 2.2b.1 Activity Result: Preliminary Site preparation completed
| 2.2b.1 mobilization eqiupments |  | x |  |  | KIRMA & DT&I | GEF | 72210 | 2500
| 2.2b.2 clearing and grubbing |  |  | x |  | KIRMA & DT&I | GEF | 71400 | 10000
Indicator: 2.2.1b At the end of year four, one (1) climate change resilient coastal road design system is in place. | 2.2b.3 site ditching |  |  | x |  | KIRMA & DT&I |  | 71400 | 5000
| 2.2b.4 resurfacing roadways |  |  | x | x | KIRMA & DT&I | GEF | 71400 | 50000
Baseline: Not existed | 2.2b.2 Activity Result: Bid documentation completed
| 2.2b.2.1 bid documents and specs. | x |  |  |  | KIRMA & DT&I | GEF | 72500 | 2500
| 2/2b/2.2 bidding advertised |  | x |  |  | KIRMA & DT&I | GEF | 74200 | 1000
Target: By the end of the project, at least one (1)design that in corporates climate change risk into coastal road systems is implemented. | 2.2b.2.3 Bid awarded and notice to proceed | [7 empty] | 0
[7 empty] | (E) Total Output 2.1b |  | 71000
|  | (F) Total Outcome 2 |  |  |  |  | (F) = (D) + (E) |  | 94700
OUTCOME 3: (Click cell and press F2 to enter into each cell and paste the information from the 'logframe'. Delet this instruction.)
Output 3.1 (Click cell and press F2 to enter into each cell and paste the information from the 'logframe'. Delete this instruction.) | 3.1.1 Activity Result (in past tense)
3.1.1.1 First activity
ETC
Indicator
3.1.2 Activity Result (in past tense)
Baseline | 3.1.2.1
etc
Target
use this entire row to insert more when needed
[7 empty] | (G) Total Output 3.1 |  | 0
Output 3.2 (Click cell and press F2 to enter into each cell and paste the information from the 'logframe'. Delete this instruction.) | same as above
Indicator
Baseline
Target
[7 empty] | (H) Total Output 3.2 |  | 0
Output 3.3 Conduct public awareness raising program on Climate Change | 3.3.1 Activity result: Public Awareness program(Technical guidance provided for implementation of National adaptation)
| 3.3.1.1 Prepare project revelent country specific newsletters & other dissemination materials |  | x | x | x | KIRMA & DT&I | GEF | 72500 | 3000
| 3.3.1.2 Conduct Road island wide roadshow to officially kickoff the FSM PACC Project |  |  | x |  | KIRMA & Women Group | GEF | 72500 | 3000
Indicator: Exchange knowledge and lesson learn | 3.3.2: Documentation creating publication on best practices and lessons
| 3.3.2.1 Create relevant policies & initiatives |  |  | x | x | KIRMA & DT&I | GEF | 71400 | 2000
Baseline: Ongoing awareness programs and activities | 3.3.2.2 Conduct 2 community assessment and data collection |  |  |  | x | KIRMA & DT&I | GEF | 73100 | 2000
Target: General Public
[7 empty] | (I) Total Output 3.3 |  | 10000
|  | (J) Total Outcome 3 |  |  |  |  | (J) = (G)+(H)+(I) |  | 10000
OUTCOME 4: Project Management
Output 4.1 Effective Project Management | 4.1.1.Activity result: PMU Established
Indicator: No of project activities succesfully implemented and outputs achieved | 4.1.1.1 Coordinator Salary |  | x | x | x | KIRMA & DT&I | GEF | 71400-Contractual services | 7000
Baseline: Existing resources not adequate to support a Project Management Unit | 4.1.1.2 PMU office Supplies | x | x |  |  | OEEM | GEF | 72500 | 2500
| 4.1.1.3 Develop and implement communication strategy |  | x | x | x | KIRMA & DT&I | GEF | 72500-supplies, 72800-information technology and outreach | 500
Target: All project activities completed and all outputs achieved within the project time frame | 4.1.2 Activity result: National Steering Committtee Support
| 4.1.2.1 Steering/Core Committee Meetings |  |  |  |  | KPSC | GEF | 71600-travel & 72500-supplies
4.1.3 Activity result: Project Steering Committee established
| 4.1.3.1 Establish & implement project steering committee meetings |  |  | x |  | KIRMA & DT&I | GEF | 72700 Hospitality | 500
4.1.4 Activity Result: Monitoring & Reporting
| 4.1.4.1 Develop quarterly reports | x | x | x | x | KIRMA & DT&I | Inkind
| 4.1.4.2 Audit |  |  |  | x | Audit | GEF
| 4.1.4.3 Regional PACC Meeting |  | x |  | x |  | GEF | 71600 Tripartite Review | 5000
[6 empty] | (K) Total Output 4.1 |  |  | 15500
Output 4.2 (Click cell and press F2 to enter into each cell and paste the information from the 'logframe'. Delete this instruction.) | same as above
Indicator
Baseline
Target
[7 empty] | (L) Total Output 4.2 |  | 0
|  | (M) Total Outcome 4 |  |  |  |  | (M) = (K)+(L) |  | 15500
| Total Planned Budget 2009 | [5 empty] | (N) = (C)+(F)+(J)+(M) |  | 146700
Note on I7: peni.leavai: REFER to Chart of Accounts (COA). A separate excel sheet from UNDP to fill in codes and budget descriptions. Fill in completely. Also refer to Project Document and or Inception Report
Note on I40: peni.leavai: refer to Chart of Accounts (separate excel document) OR the project document for guidance.
Note on I78: peni.leavai: refer to Chart of Accounts (separate excel document) OR the project document for guidance.

## 2011
2

## 2013
2011