## 3 QTR 2007
PIGGAREP
INCEPTION PHASE WORK PLAN AND BUDGET FOR GEF CONTRIBUTION
Third Quarter: Year 2007
Goal: The goal of the Inception Phase is confirm activities to be supported by the PIGGAREP and to put in place the management, financial and institutional structures required for the effective implementation
of the confirmed project activities.
Purpose: The Inception Phase is an opportunity for the stakeholders and partners to provide input on the work plan and to confirm implementation arrangements both at the regional and national levels. It provides an opportunity to finalize any outstanding implementation details and present them to UNDP and SPREP for clearance. The Inception Phase also brings new momentum to the project after the relatively quiet period during the project approval process.
#REF!
EXPECTED OUTPUTS & |  | TIMEFRAME |  |  | RESPONSIBLE | PLANNED BUDGET (US$)
MONITORING ACTIVITIES | KEY ACTIVITIES | July | Aug | Sept | PARTY | Budget Description (Account # and Budget Category) |  | Estimated Amount
Outcome 1: Established Country Teams and Project Advisory Committee
Output 1.1: Project Stakeholders advised of the commencement of the PIGGAREP | 1.1.1 Prepare and disseminate introductory circular | x |  |  | PMO | 71400 Contractual Services - Individuals |  | 1000
Output 1.2: Counry Teams Established | 1.2.1 Prepare and disseminate introductory circular | x |  |  | PMO | 71400 Contractual Services - Individuals |  | 1500
| 1.2.2 Invite members to the Country Teams | x | x | x | Project Contacts / National Host Agencies | 71600 Travel |  | 5000
| 1.2.3 Develop a template of rules and procedures for the Country Teams |  |  | x | Project Contacts/ PMO
| 1.2.4 Review, agree on, and finalize the role and responsibility of various national participants for achieving the national project outcome: |  |  | x | Country Teams
Output 1.3: Project Advisory Committee (PAC) formed | 1.3.1 Prepare and disseminate introductory circular | x |  |  | PMO | 71400 Contractual Services - Individuals |  | 2500
| 1.3.2 Invite members to the PAC | x |  |  | PMO
| 1.3.3 Finalize level of representation and individual membership of the PAC |  |  | x | PMO / UNDP
| 1.3.4 Develop rules of procedure for the PAC |  |  | x | PMO / UNDP
| 1.3.5 Clarify relationship between the PAC and the Multi-Partite Review |  |  | x | PMO / UNDP
Outcome 2: Agreed revised ProDoc
Output 2.1: Revised ProDoc | 2.1.1 Review the project management arrangements (organizational chart), including reporting lines. | x | x | x | PMO / UNDP / PICs | 71400 Contractual Services - Individuals |  | 2000
| 2.1.2 Review, and where necessary identify additional Project Risks | x | x | x | PMO
| 2.1.3 Prepare a detailed risk management strategy for project implementation | x | x | x | PMO
| 2.14 Review existing ToRs in the ProDoc |  | x | x | PMO
Output 2.2: Agreed national and project activities | 2.2.1 Prepare and disseminate introductory circular | x |  |  | PMO | 71400 Contractual Services - Individuals |  | 10000
| 2.2.2 Develop a template for project proposals to be supported by PIGGAREP | x |  |  | PMO | 71300 Local consultants |  | 5000
| 2.2.3 Develop operational criteria for screening project activities, including allocation of funds to individual countries as part of the project. | x |  |  | PMO / UNDP | 71600 Travel |  | 15000
| 2.2.4 Confirm and coordinate all co-financing sources with the project work plan. | x | x | x | PMO | 72000 General Operating Expenses |  | 23000
| 2.2.5 Conduct national consultative workshops with Country Teams to identify and confirm national project activities, review national capacity and project management plans. |  | x | x | PMO / Project Contacts/ Country Teams
| 2.2.6 Hold consultation meetings with Power Utility CEOs, members of the CROP EWG, REEEP Steering Committee, UNEP, World Bank SEFP, co-financing partners and donors |  | x | x | PMO
| 2.2.7 Prepare an overall work plan for the first year of implementation and revise the project budget if necessary. | x | x | x | PMO
| 2.2.8 Conduct Regional Inception Phase Workshop |  |  |  | PMO / UNDP
| 2.2.9 Sign MoUs with PICs, Co-financing Partners and Key Project Stakeholders |  |  |  | PMO / UNDP
Output 2.3: Agreed M & E Framework | 2.3.1 Review, agree on, and finalize the M & E framework for the implementation of the project, including: |  |  | x | PMO/ UNDP | 71400 Contractual Services - Individuals |  | 2500
| · Annual work plan/budget processes covering regional and in-country activities, linked to the overall rolling work plans/budget. (This will include the setting of yearly targets/milestones that are understood and agreed/endorsed by all stakeholders) |  | x | x
· Ongoing work plan/budget of monitoring and evaluation plans
· Links to project outcome indicators (impact indicators), progress indicators and the Logical Framework
· Practical, activity-level links to the PIFACC, PIEP and associated strategic plan
· Practical, activity-level links to national energy plans, where available
· Monitoring of progress of parallel activities of co-financing institutions, including the delivery of their committed co-financing
Outcome 3: Agreed Five Year Plan of Project Activities
Output 3.1: Capacity of National Coordinators and Country Teams reviewed and strengthened | 3.1.1 Review the capacity of the National Coordinators and Country Teams in providing and/or obtaining project execution services and day-to-day project management. |  | x | x | PMO | 71400 Contractual Services - Individuals |  | 3000
| 3.1.2 Provide training on required UNDP reporting and project management requirements, as well as general GEF expectations. |  |  |  | UNDP | 71600 Travel |  | 5000
Output 3.3: A Project Operations Manual (POM) | 3.3.1 Prepare a POM as supplement to the UNDP Results Management User Guide. |  |  | x | PMO/ UNDP | 71400 Contractual Services - Individuals |  | 1500
| 3.3.2 Share the POM with all project stakeholders and provide training as necessary. |  |  |  | PMO / UNDP
Outcome 4: PIGGAREP publicized and Internet-based link with PIREP established
Output 4.1: Improved appreciation of PIGGAREP | 4.1.1 Prepare press releases on PIGGAREP | x | x | x | PMO | 71400 Contractual Services - Individuals |  | 500
| 4.1.2 Prepare a PIGGAREP promotional flyer/leaflet |  |  |  | PMO / Local Consultant | 71300 Local consultants |  | 10000
| 4.1.3 Present the PIGGAREP to the National Communications Support Programme Workshop and share the PIREP reports with the participants | x |  |  | PMO
Output 4.2: Improved visibility of PIGGAREP in the SPREP home page | 4.2.1 Update the PIREP page by posting in it the ProDoc and Terminal Review Report | x |  |  | PMO | 71400 Contractual Services - Individuals |  | 500
| 4.2.2 Create a more easily accessible page for the PIGGAREP with a link to the PIREP’s and other related national and regional initiatives. | x | x | x | PMO
[7 empty] | Total | 88000
[7 empty] | 71300 Local consultants | 15000
[7 empty] | 71400 Contractual Services - Individuals | 25000
[7 empty] | 71600 Travel (PMO) | 25000
[7 empty] | 71600 Travel (Inception Workshop) | 0
[7 empty] | 72000 General Operating Expenses | 23000
Note on C52: Manuel Soriano: Delete this activity. Just ensure to appoint the right, qualified and capable people to the NC and CT member positions.

## 4 QTR 2007
PIGGAREP
INCEPTION PHASE WORK PLAN AND BUDGET FOR GEF CONTRIBUTION
Fourth Quarter: Year 2007
Goal: The goal of the Inception Phase is confirm activities to be supported by the PIGGAREP and to put in place the management, financial and institutional structures required for the effective implementation
of the confirmed project activities.
Purpose: The Inception Phase is an opportunity for the stakeholders and partners to provide input on the work plan and to confirm implementation arrangements both at the regional and national levels. It provides an opportunity to finalize any outstanding
#REF!
EXPECTED OUTPUTS & |  | TIMEFRAME |  |  | RESPONSIBLE | PLANNED BUDGET (US$)
MONITORING ACTIVITIES | KEY ACTIVITIES | Oct | Nov | Dec | PARTY | Budget Description (Account # and Budget Category) |  | Estimated Amount
Outcome 1: Established Country Teams and Project Advisory Committee
Output 1.1: Project Stakeholders advised of the commencement of the PIGGAREP | 1.1.1 Prepare and disseminate introductory circular |  |  |  | PMO | 71400 Contractual Services - Individuals
Output 1.2: Counry Teams Established | 1.2.1 Prepare and disseminate introductory circular |  |  |  | PMO | 71400 Contractual Services - Individuals |  | 2500
| 1.2.2 Invite members to the Country Teams | x | x |  | Project Contacts / National Host Agencies | 71600 Travel |  | 3000
| 1.2.3 Develop a template of rules and procedures for the Country Teams | x |  |  | Project Contacts/ PMO
| 1.2.4 Review, agree on, and finalize the role and responsibility of various national participants for achieving the national project outcome: | x | x | x | Country Teams
Output 1.3: Project Advisory Committee (PAC) formed | 1.3.1 Prepare and disseminate introductory circular |  |  |  | PMO | 71400 Contractual Services - Individuals |  | 2500
| 1.3.2 Invite members to the PAC | x |  |  | PMO
| 1.3.3 Finalize level of representation and individual membership of the PAC | x |  |  | PMO / UNDP
| 1.3.4 Develop rules of procedure for the PAC | x |  |  | PMO / UNDP
| 1.3.5 Clarify relationship between the PAC and the Multi-Partite Review | x |  |  | PMO / UNDP
Outcome 2: Agreed revised ProDoc
Output 2.1: Revised ProDoc | 2.1.1 Review the project management arrangements (organizational chart), including reporting lines. | x | x |  | PMO / UNDP / PICs | 71400 Contractual Services - Individuals |  | 2000
| 2.1.2 Review, and where necessary identify additional Project Risks | x | x |  | PMO
| 2.1.3 Prepare a detailed risk management strategy for project implementation | x | x |  | PMO
| 2.14 Review existing ToRs in the ProDoc | x | x | x | PMO
Output 2.2: Agreed national and project activities | 2.2.1 Prepare and disseminate introductory circular |  |  |  | PMO | 71400 Contractual Services - Individuals |  | 10000
| 2.2.2 Develop a template for project proposals to be supported by PIGGAREP | x |  |  | PMO | 71300 Local consultants |  | 2500
| 2.2.3 Develop operational criteria for screening project activities, including allocation of funds to individual countries as part of the project. | x |  |  | PMO / UNDP | 71600 Travel |  | 70000
| 2.2.4 Confirm and coordinate all co-financing sources with the project work plan. | x | x | x | PMO | 72000 General Operating Expenses |  | 7000
| 2.2.5 Conduct national consultative workshops with Country Teams to identify and confirm national project activities, review national capacity and project management plans. | x |  |  | PMO / Project Contacts/ Country Teams
| 2.2.6 Hold consultation meetings with Power Utility CEOs, members of the CROP EWG, REEEP Steering Committee, UNEP, World Bank SEFP, co-financing partners and donors | x | x |  | PMO
| 2.2.7 Prepare an overall work plan for the first year of implementation and revise the project budget if necessary. | x | x | x | PMO
| 2.2.8 Conduct Regional Inception Phase Workshop |  | x |  | PMO / UNDP
| 2.2.9 Sign MoUs with PICs, Co-financing Partners and Key Project Stakeholders |  |  | x | PMO / UNDP
Output 2.3: Agreed M & E Framework | 2.3.1 Review, agree on, and finalize the M & E framework for the implementation of the project, including: | x |  |  | PMO/ UNDP | 71400 Contractual Services - Individuals |  | 2500
| · Annual work plan/budget processes covering regional and in-country activities, linked to the overall rolling work plans/budget. (This will include the setting of yearly targets/milestones that are understood and agreed/endorsed by all stakeholder | x | x
· Ongoing work plan/budget of monitoring and evaluation plans
· Links to project outcome indicators (impact indicators), progress indicators and the Logical Framework
· Practical, activity-level links to the PIFACC, PIEP and associated strategic plan
· Practical, activity-level links to national energy plans, where available
· Monitoring of progress of parallel activities of co-financing institutions, including the delivery of their committed co-financing
Outcome 3: Agreed Five Year Plan of Project Activities
Output 3.1: Capacity of National Coordinators and Country Teams reviewed and strengthened | 3.1.1 Review the capacity of the National Coordinators and Country Teams in providing and/or obtaining project execution services and day-to-day project management. | x | x |  | PMO | 71400 Contractual Services - Individuals |  | 3000
| 3.1.2 Provide training on required UNDP reporting and project management requirements, as well as general GEF expectations. |  | x | x | UNDP | 71600 Travel |  | 2000
Output 3.3: A Project Operations Manual (POM) | 3.3.1 Prepare a POM as supplement to the UNDP Results Management User Guide. | x | x |  | PMO/ UNDP | 71400 Contractual Services - Individuals |  | 1500
| 3.3.2 Share the POM with all project stakeholders and provide training as necessary. | x | x |  | PMO / UNDP
Outcome 4: PIGGAREP publicized and Internet-based link with PIREP established
Output 4.1: Improved appreciation of PIGGAREP | 4.1.1 Prepare press releases on PIGGAREP | x | x | x | PMO | 71400 Contractual Services - Individuals |  | 500
| 4.1.2 Prepare a PIGGAREP promotional flyer/leaflet |  | x | x | PMO / Local Consultant | 71300 Local consultants |  | 2500
| 4.1.3 Present the PIGGAREP to the National Communications Support Programme Workshop and share the PIREP reports with the participants |  |  |  | PMO
Output 4.2: Improved visibility of PIGGAREP in the SPREP home page | 4.2.1 Update the PIREP page by posting in it the ProDoc and Terminal Review Report | x | x | x | PMO | 71400 Contractual Services - Individuals |  | 500
| 4.2.2 Create a more easily accessible page for the PIGGAREP with a link to the PIREP’s and other related national and regional initiatives. | x | x | x | PMO
[7 empty] | Total | 112000
[7 empty] | 71300 Local consultants | 5000
[7 empty] | 71400 Contractual Services - Individuals | 25000
[7 empty] | 71600 Travel (PMO) | 5000
[7 empty] | 71600 Travel (Inception Workshop) | 70000
[7 empty] | 72000 General Operating Expenses | 7000
Note on C52: Manuel Soriano: Delete this activity. Just ensure to appoint the right, qualified and capable people to the NC and CT member positions.

## 2007
PIGGAREP
2007-2012 WORK PLAN AND BUDGET FOR GEF CONTRIBUTION
Year 2007
#REF!
EXPECTED OUTPUTS & |  | TIMEFRAME |  |  |  | RESPONSIBLE | PLANNED BUDGET (US$)
MONITORING ACTIVITIES | KEY ACTIVITIES | Q1 | Q2 | Q3 | Q4 | PARTY | Budget Description (Account # and Budget Category) |  | Estimated Amount
Output 1. Technical Capacity Building & Technical Support | 1.1 Provide support to RE resource assessments and demonstration projects | [5 empty] | 71200 International Personnel
71300 Local consultants
71400 Contractual Services - Individuals
71600 Travel
Output 2. Market Development | 2.1 Support market development | [5 empty] | 71200 International Personnel
71300 Local consultants
71400 Contractual Services - Individuals
71600 Travel
Output 3. Institutional Strengthening | 3.1 Provide institutional strengthening | [5 empty] | 71200 International Personnel
71300 Local consultants
71400 Contractual Services - Individuals
71600 Travel
Output 4. Financing Support | 4.1 Provide support to establish and enhance existing financing mechanisms | [5 empty] | 71200 International Personnel
71300 Local consultants
71400 Contractual Services - Individuals
71600 Travel
Output 5. Policy and Regulatory Support | 5.1 Provide assistance to establish and enhance existing policy and regulatory structures | [5 empty] | 71200 International Personnel
71300 Local consultants
71400 Contractual Services - Individuals
71600 Travel
Output 6. Information and Awareness Enhancement | 6.1. Provide support to increased information and awareness in the area of RE | [5 empty] | 71200 International Personnel
71300 Local consultants
71400 Contractual Services - Individuals
71600 Travel
Output 7. Efficient and Effective Project Management | 7.1 National Consutlative Workshops |  |  | x | x | PIGGAREP Project Team | 71300 Local consultants |  | 20000
| 7.2 Project Manager |  |  | x | x |  | 71400 Contractual Services - Individuals |  | 50000
|  |  |  | x | x |  | 71600 Travel |  | 30000
| 7.3 Administrative/Financial Officer |  |  | x | x |  | 71400 Service Contracts - Individuals |  | 0
| 7.4 SPREP Project Team miscellaneous |  |  | x | x |  | 72000 General Operating Expenses |  | 30000
| 7.5 Inception Meeting | [5 empty] | 71600 Travel |  | 70000
[8 empty] | SUB-TOTAL 2007 | 200000